## Sheet1
Sl | WBS_Elements_Info. |  |  | Total of years |  |  |  |  | Previous years |  |  |  |  | 2024 |  |  |  |  | 2025 |  |  |  |  | 2026 |  |  |  |  | 2027 and Following |  |  |  |  | Overall values
No. | Level | Description | ID_No | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available
0 | 5* | TPS-II LEP Stage I & II Non Plan CAPEX | NL-N-TS2-002 | 5969761119.73 | 2006063265.68 | 2105381000.82 | 4111454987.49 | 1858306132.24 | 1918756322.84 | 1916246637.51 | 1651044.03 | 1917908402.53 | 847920.31 | 4051004796.89 | 89816628.17 | 2103729956.79 | 2193546584.96 | 1857458211.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5969761119.73 | 2006063265.68 | 2105381000.82 | 4111454987.49 | 1858306132.24
1 | 4* | TPS-II LEP Stage I & II Non Plan CAPEX | NL-N-TS2-002 | 5969761119.73 | 2006063265.68 | 2105381000.82 | 4111454987.49 | 1858306132.24 | 1918756322.84 | 1916246637.51 | 1651044.03 | 1917908402.53 | 847920.31 | 4051004796.89 | 89816628.17 | 2103729956.79 | 2193546584.96 | 1857458211.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5969761119.73 | 2006063265.68 | 2105381000.82 | 4111454987.49 | 1858306132.24
2 | *** | AHS | NL-N-TS2-002-01 | 160803448.51 | 51827103.41 | 94651273.7 | 146478377.11 | 14325071.4 | 38446256.28 | 38446256.27 | 0 | 38446256.27 | 0.01 | 122357192.23 | 13380847.14 | 94651273.7 | 108032120.84 | 14325071.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160803448.51 | 51827103.41 | 94651273.7 | 146478377.11 | 14325071.4
3 | ** | ESP-UNIT-2 | NL-N-TS2-002-01-01 | 22310264.97 | 22310264.97 | 0 | 22310264.97 | 0 | 18105132.11 | 18105132.11 | 0 | 18105132.11 | 0 | 4205132.86 | 4205132.86 | 0 | 4205132.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22310264.97 | 22310264.97 | 0 | 22310264.97 | 0
4 | ** | CS Seamless pipe size 8 &10 inch | NL-N-TS2-002-01-03 | 11370400 | 11361324.16 | 9075.84 | 11370400 | 0 | 11361324.16 | 11361324.16 | 0 | 11361324.16 | 0 | 9075.84 | 0 | 9075.84 | 9075.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11370400 | 11361324.16 | 9075.84 | 11370400 | 0
5 | ** | Purchase of ceramic lined fittings&pipes | NL-N-TS2-002-01-04 | 2149912.78 | 254914.28 | 1894998.49 | 2149912.77 | 0.01 | 0.01 | 0 | 0 | 0 | 0.01 | 2149912.77 | 254914.28 | 1894998.49 | 2149912.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2149912.78 | 254914.28 | 1894998.49 | 2149912.77 | 0.01
6 | ** | GS Plain Grating for ESP | NL-N-TS2-002-01-05 | 6515074.25 | 0 | 6515074.25 | 6515074.25 | 0 | 0 | 0 | 0 | 0 | 0 | 6515074.25 | 0 | 6515074.25 | 6515074.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6515074.25 | 0 | 6515074.25 | 6515074.25 | 0
7 | ** | Air BLOCK 1ST STAGE COVN AIR COMPRESSOR | NL-N-TS2-002-01-06 | 8979800 | 8979800 | 0 | 8979800 | 0 | 8979800 | 8979800 | 0 | 8979800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8979800 | 8979800 | 0 | 8979800 | 0
8 | ** | LEP ESP uint-5 | NL-N-TS2-002-01-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | ** | Air Block 1st &2nd stage for compressor | NL-N-TS2-002-01-08 | 8920800 | 8920800 | 0 | 8920800 | 0 | 0 | 0 | 0 | 0 | 0 | 8920800 | 8920800 | 0 | 8920800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8920800 | 8920800 | 0 | 8920800 | 0
10 | ** | Purchase of Ash inlet Cup valves in DAS | NL-N-TS2-002-01-09 | 2903049.59 | 0 | 2903049.59 | 2903049.59 | 0 | 0 | 0 | 0 | 0 | 0 | 2903049.59 | 0 | 2903049.59 | 2903049.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2903049.59 | 0 | 2903049.59 | 2903049.59 | 0
11 | ** | Purchase of ceramic lined bends & Spool | NL-N-TS2-002-01-10 | 2316263.85 | 0 | 2316263.85 | 2316263.85 | 0 | 0 | 0 | 0 | 0 | 0 | 2316263.85 | 0 | 2316263.85 | 2316263.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2316263.85 | 0 | 2316263.85 | 2316263.85 | 0
12 | ** | CSS Pipe 8/10 Inch ASTM A106 | NL-N-TS2-002-01-12 | 43980500 | 0 | 43980500 | 43980500 | 0 | 0 | 0 | 0 | 0 | 0 | 43980500 | 0 | 43980500 | 43980500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43980500 | 0 | 43980500 | 43980500 | 0
13 | ** | ASH INLET CUPVALVE ASSEMBLY WITH ACTUATO | NL-N-TS2-002-01-14 | 51357383.07 | 0 | 37032311.68 | 37032311.68 | 14325071.39 | 0 | 0 | 0 | 0 | 0 | 51357383.07 | 0 | 37032311.68 | 37032311.68 | 14325071.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51357383.07 | 0 | 37032311.68 | 37032311.68 | 14325071.39
14 | *** | CIVIL | NL-N-TS2-002-02 | 245842512.14 | 139147055.73 | 80799134.4 | 219946190.13 | 25896322.01 | 138248926.05 | 137506011.13 | 0 | 137506011.13 | 742914.92 | 107593586.09 | 1641044.6 | 80799134.4 | 82440179 | 25153407.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245842512.14 | 139147055.73 | 80799134.4 | 219946190.13 | 25896322.01
15 | ** | galvaume sheets- transformer-esp fields | NL-N-TS2-002-02-41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | ** | Rehabilitation works to CT-5 outside | NL-N-TS2-002-02-02 | 18780348.93 | 18780348.93 | 0 | 18780348.93 | 0 | 18780348.93 | 18780348.93 | 0 | 18780348.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18780348.93 | 18780348.93 | 0 | 18780348.93 | 0
17 | ** | Rehabilitation work in Stage-II Chimmney | NL-N-TS2-002-02-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | ** | Facelifting of Balance of the plant | NL-N-TS2-002-02-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | ** | Water Proofing works to Main Building | NL-N-TS2-002-02-05 | 8848487.13 | 6281602.93 | 2566884.2 | 8848487.13 | 0 | 6049556.7 | 6305947.33 | 0 | 6305947.33 | -256390.63 | 2798930.43 | -24344.4 | 2566884.2 | 2542539.8 | 256390.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8848487.13 | 6281602.93 | 2566884.2 | 8848487.13 | 0
20 | ** | Paver block pavement&fencing around CTs | NL-N-TS2-002-02-06 | 6082931.41 | 6082931.41 | 0 | 6082931.41 | 0 | 6082931.41 | 6082931.41 | 0 | 6082931.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6082931.41 | 6082931.41 | 0 | 6082931.41 | 0
21 | ** | Rehabilitation works to CT-1 - Outside | NL-N-TS2-002-02-07 | 20904541.88 | 20680612.08 | 0 | 20680612.08 | 223929.8 | 20904541.88 | 20680612.08 | 0 | 20680612.08 | 223929.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20904541.88 | 20680612.08 | 0 | 20680612.08 | 223929.8
22 | ** | Improvement works to water supply | NL-N-TS2-002-02-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | ** | Roof& cladding to JT-1& sloping conveyor | NL-N-TS2-002-02-09 | 3186642.45 | 3186642.45 | 0 | 3186642.45 | 0 | 3186642.45 | 3186642.45 | 0 | 3186642.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3186642.45 | 3186642.45 | 0 | 3186642.45 | 0
24 | ** | Painting of Boiler structures U-5,6 & 7 | NL-N-TS2-002-02-10 | 1838450.46 | 1283419.04 | 0 | 1283419.04 | 555031.42 | 1838450.46 | 1283419.04 | 0 | 1283419.04 | 555031.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1838450.46 | 1283419.04 | 0 | 1283419.04 | 555031.42
25 | ** | Repair& painting of Stage II Boiler Lift | NL-N-TS2-002-02-11 | 3896420.89 | 3896420.89 | 0 | 3896420.89 | 0 | 3896420.89 | 3896420.89 | 0 | 3896420.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3896420.89 | 3896420.89 | 0 | 3896420.89 | 0
26 | ** | Coat over existing bituminous roads | NL-N-TS2-002-02-12 | 1813726.51 | 1813726.51 | 0 | 1813726.51 | 0 | 1813726.51 | 1813726.51 | 0 | 1813726.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813726.51 | 1813726.51 | 0 | 1813726.51 | 0
27 | ** | Providing golvelume sheet of Lift-6&7 | NL-N-TS2-002-02-13 | 1517070.85 | 1517070.85 | 0 | 1517070.85 | 0 | 1517070.85 | 1517070.85 | 0 | 1517070.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517070.85 | 1517070.85 | 0 | 1517070.85 | 0
28 | ** | Collecting scrap at bunker of Stage-II | NL-N-TS2-002-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | ** | Partition & False ceiling work in AC/TS2 | NL-N-TS2-002-02-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | ** | LHS yard Rails civil works | NL-N-TS2-002-02-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | ** | Restoration sheets Boiler ST-II/Phase-I | NL-N-TS2-002-02-17 | 13102798.15 | 12373433.2 | 653761.17 | 13027194.37 | 75603.78 | 12449036.98 | 12373433.2 | 0 | 12373433.2 | 75603.78 | 653761.17 | 0 | 653761.17 | 653761.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13102798.15 | 12373433.2 | 653761.17 | 13027194.37 | 75603.78
32 | ** | Restoration sheet Boiler ST-II/Phase-II | NL-N-TS2-002-02-18 | 12685552.22 | 12685552.16 | 0.06 | 12685552.22 | 0 | 12685552.16 | 12685552.16 | 0 | 12685552.16 | 0 | 0.06 | 0 | 0.06 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12685552.22 | 12685552.16 | 0.06 | 12685552.22 | 0
33 | ** | Rehabiltation of CT-4 inside & Outside | NL-N-TS2-002-02-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | ** | Prepatory works for FGD | NL-N-TS2-002-02-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | ** | Installation&Commissioning of STP | NL-N-TS2-002-02-21 | 14181240.06 | 7944114 | 6237126.06 | 14181240.06 | 0 | 7944114 | 7944114 | 0 | 7944114 | 0 | 6237126.06 | 0 | 6237126.06 | 6237126.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14181240.06 | 7944114 | 6237126.06 | 14181240.06 | 0
36 | ** | Upgraditaion of Weighbridge to 100 T | NL-N-TS2-002-02-22 | 457123.76 | 430495.86 | 13313.96 | 443809.82 | 13313.94 | 443809.8 | 430495.86 | 0 | 430495.86 | 13313.94 | 13313.96 | 0 | 13313.96 | 13313.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457123.76 | 430495.86 | 13313.96 | 443809.82 | 13313.94
37 | ** | Retrofit outside platform of Stage-I CTs | NL-N-TS2-002-02-24 | 19026910.03 | 18928675 | 98235.03 | 19026910.03 | 0 | 18928675 | 18928675 | 0 | 18928675 | 0 | 98235.03 | 0 | 98235.03 | 98235.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19026910.03 | 18928675 | 98235.03 | 19026910.03 | 0
38 | ** | Laterite Platform for Reclaimer erection | NL-N-TS2-002-02-25 | 8065282.96 | 8065282.96 | 0 | 8065282.96 | 0 | 8065282.96 | 8065282.96 | 0 | 8065282.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8065282.96 | 8065282.96 | 0 | 8065282.96 | 0
39 | ** | Civil & Structural works for VIP Lift | NL-N-TS2-002-02-26 | 1619421.75 | 1619421.75 | 0 | 1619421.75 | 0 | 1619421.75 | 1619421.75 | 0 | 1619421.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1619421.75 | 1619421.75 | 0 | 1619421.75 | 0
40 | ** | Cover Shed for ESP Transformer -Stage-II | NL-N-TS2-002-02-27 | 1719385.54 | 1692145.84 | 0 | 1692145.84 | 27239.7 | 1719385.54 | 1692145.84 | 0 | 1692145.84 | 27239.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1719385.54 | 1692145.84 | 0 | 1692145.84 | 27239.7
41 | ** | Unit-5 Lift enclose with MS,Galva Sheet | NL-N-TS2-002-02-28 | 2921029.03 | 2520119.44 | 400909.59 | 2921029.03 | 0 | 2520119.44 | 2520119.44 | 0 | 2520119.44 | 0 | 400909.59 | 0 | 400909.59 | 400909.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2921029.03 | 2520119.44 | 400909.59 | 2921029.03 | 0
42 | ** | Repair of J-Row Walls in Stage-II | NL-N-TS2-002-02-30 | 1550838.98 | 840520.82 | 606131.25 | 1446652.07 | 104186.91 | 944707.73 | 840520.82 | 0 | 840520.82 | 104186.91 | 606131.25 | 0 | 606131.25 | 606131.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550838.98 | 840520.82 | 606131.25 | 1446652.07 | 104186.91
43 | ** | Intermediate Settling Tank | NL-N-TS2-002-02-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | ** | Modification of Power Monitoring centre | NL-N-TS2-002-02-33 | 383179.44 | 383179.44 | 0 | 383179.44 | 0 | 383179.44 | 383179.44 | 0 | 383179.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383179.44 | 383179.44 | 0 | 383179.44 | 0
45 | ** | REPAIR OF LHS TRACKS STOCKYARD | NL-N-TS2-002-02-34 | 26770284 | 0 | 26770284 | 26770284 | 0 | 0 | 0 | 0 | 0 | 0 | 26770284 | 0 | 26770284 | 26770284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26770284 | 0 | 26770284 | 26770284 | 0
46 | ** | Manu.&supply of sleepers & REpair in LHS | NL-N-TS2-002-02-35 | 8902303.21 | 6475951.17 | 2426352.04 | 8902303.21 | 0 | 6475951.17 | 6475951.17 | 0 | 6475951.17 | 0 | 2426352.04 | 0 | 2426352.04 | 2426352.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8902303.21 | 6475951.17 | 2426352.04 | 8902303.21 | 0
47 | ** | Formation of new WBM road over embakment | NL-N-TS2-002-02-38 | 42691526 | 1665389 | 41026137.04 | 42691526.04 | -0.04 | 0 | 0 | 0 | 0 | 0 | 42691526 | 1665389 | 41026137.04 | 42691526.04 | -0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42691526 | 1665389 | 41026137.04 | 42691526.04 | -0.04
48 | ** | IMPROVE BT ROAD TO MAKE UP WATER LAKE | NL-N-TS2-002-02-39 | 11569555.86 | 0 | 0 | 0 | 11569555.86 | 0 | 0 | 0 | 0 | 0 | 11569555.86 | 0 | 0 | 0 | 11569555.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11569555.86 | 0 | 0 | 0 | 11569555.86
49 | ** | WIDEN EXISTING OUTER ROAD-RCC WALL-2EXPN | NL-N-TS2-002-02-40 | 13327460.64 | 0 | 0 | 0 | 13327460.64 | 0 | 0 | 0 | 0 | 0 | 13327460.64 | 0 | 0 | 0 | 13327460.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13327460.64 | 0 | 0 | 0 | 13327460.64
50 | *** | ELECTRICAL O & S | NL-N-TS2-002-03 | 50385253.95 | 31854503.39 | 18530750.56 | 50385253.95 | 0 | 31854503.39 | 31854503.39 | 0 | 31854503.39 | 0 | 18530750.56 | 0 | 18530750.56 | 18530750.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50385253.95 | 31854503.39 | 18530750.56 | 50385253.95 | 0
51 | ** | Retrofit of relay for 6.6KV incomers,Tie | NL-N-TS2-002-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | ** | Battery charger 220V 300A sets | NL-N-TS2-002-03-02 | 4476239.99 | 4476239.99 | 0 | 4476239.99 | 0 | 4476239.99 | 4476239.99 | 0 | 4476239.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4476239.99 | 4476239.99 | 0 | 4476239.99 | 0
53 | ** | Replace 1180AH cap battery bank Stage-I | NL-N-TS2-002-03-03 | 18489989.03 | 18489989.03 | 0 | 18489989.03 | 0 | 18489989.03 | 18489989.03 | 0 | 18489989.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18489989.03 | 18489989.03 | 0 | 18489989.03 | 0
54 | ** | Replace 1285AH cap battery bank Stage-II | NL-N-TS2-002-03-04 | 6552405.79 | 6552405.79 | 0 | 6552405.79 | 0 | 6552405.79 | 6552405.79 | 0 | 6552405.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6552405.79 | 6552405.79 | 0 | 6552405.79 | 0
55 | ** | Upgradition of 0.4KV I/C & standby break | NL-N-TS2-002-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | ** | Upgradation of 0.4KV ADPH I/C Sby I/C & | NL-N-TS2-002-03-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | ** | Replacement of IACs & SACs Control panel | NL-N-TS2-002-03-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | ** | Retrofitting of Seal Oil System & Stator | NL-N-TS2-002-03-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | ** | Dry fly ash Battery bank | NL-N-TS2-002-03-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | ** | Swyrd PLCC 48V/ 300A Battery charger | NL-N-TS2-002-03-10 | 2543985.6 | 0 | 2543985.6 | 2543985.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2543985.6 | 0 | 2543985.6 | 2543985.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2543985.6 | 0 | 2543985.6 | 2543985.6 | 0
61 | ** | Swyrd Source 220V/ 150A Battery charger | NL-N-TS2-002-03-11 | 2932252.8 | 0 | 2932252.8 | 2932252.8 | 0 | 0 | 0 | 0 | 0 | 0 | 2932252.8 | 0 | 2932252.8 | 2932252.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2932252.8 | 0 | 2932252.8 | 2932252.8 | 0
62 | ** | Dry ash UPS 2 numbers | NL-N-TS2-002-03-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | ** | Reserve | NL-N-TS2-002-03-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | ** | 48V Thyrister based FCBC Battery Charger | NL-N-TS2-002-03-14 | 324999.99 | 324999.99 | 0 | 324999.99 | 0 | 324999.99 | 324999.99 | 0 | 324999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324999.99 | 324999.99 | 0 | 324999.99 | 0
65 | ** | feeder relays | NL-N-TS2-002-03-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | ** | Relays | NL-N-TS2-002-03-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | ** | Control cable 4 core & 2 core-1.1KV | NL-N-TS2-002-03-21 | 730707.73 | 730707.73 | 0 | 730707.73 | 0 | 730707.73 | 730707.73 | 0 | 730707.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730707.73 | 730707.73 | 0 | 730707.73 | 0
68 | ** | Battery Operated platform trolley 4000kg | NL-N-TS2-002-03-22 | 719080 | 719080 | 0 | 719080 | 0 | 719080 | 719080 | 0 | 719080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719080 | 719080 | 0 | 719080 | 0
69 | ** | 1.1kV FRLS-Cu cable 7CX1.5 sqmm | NL-N-TS2-002-03-23 | 561080.86 | 561080.86 | 0 | 561080.86 | 0 | 561080.86 | 561080.86 | 0 | 561080.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561080.86 | 561080.86 | 0 | 561080.86 | 0
70 | ** | 1.1 KV FRLS Cu Cables | NL-N-TS2-002-03-24 | 1559940 | 0 | 1559940 | 1559940 | 0 | 0 | 0 | 0 | 0 | 0 | 1559940 | 0 | 1559940 | 1559940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559940 | 0 | 1559940 | 1559940 | 0
71 | ** | Instrument Air Compressor Dryer Panel | NL-N-TS2-002-03-25 | 2235644 | 0 | 2235644 | 2235644 | 0 | 0 | 0 | 0 | 0 | 0 | 2235644 | 0 | 2235644 | 2235644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2235644 | 0 | 2235644 | 2235644 | 0
72 | ** | GT Cooler Control Panel for Stage-2 | NL-N-TS2-002-03-26 | 3300837.6 | 0 | 3300837.6 | 3300837.6 | 0 | 0 | 0 | 0 | 0 | 0 | 3300837.6 | 0 | 3300837.6 | 3300837.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300837.6 | 0 | 3300837.6 | 3300837.6 | 0
73 | ** | Clamp Meter | NL-N-TS2-002-03-27 | 357760.56 | 0 | 357760.56 | 357760.56 | 0 | 0 | 0 | 0 | 0 | 0 | 357760.56 | 0 | 357760.56 | 357760.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357760.56 | 0 | 357760.56 | 357760.56 | 0
74 | ** | 2X20KVA UPS FOR DRY FLY ASH SYSTEM | NL-N-TS2-002-03-28 | 5600330 | 0 | 5600330 | 5600330 | 0 | 0 | 0 | 0 | 0 | 0 | 5600330 | 0 | 5600330 | 5600330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600330 | 0 | 5600330 | 5600330 | 0
75 | *** | ELECTRICAL MAINTENANCE | NL-N-TS2-002-04 | 1370753484.58 | 371109753.21 | 947749755.99 | 1318859509.2 | 51893975.38 | 330417930.88 | 330417930.88 | 0 | 330417930.88 | 0 | 1040335553.7 | 40691822.33 | 947749755.99 | 988441578.32 | 51893975.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1370753484.58 | 371109753.21 | 947749755.99 | 1318859509.2 | 51893975.38
76 | ** | LHS CONTROLS | NL-N-TS2-002-04-01 | 18720152.77 | 5831140.02 | 12266562.35 | 18097702.37 | 622450.4 | 5831140.02 | 5831140.02 | 0 | 5831140.02 | 0 | 12889012.75 | 0 | 12266562.35 | 12266562.35 | 622450.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18720152.77 | 5831140.02 | 12266562.35 | 18097702.37 | 622450.4
77 | * | Bunker Level Transmitter stage-II | NL-N-TS2-002-04-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | * | TPS-II Emerson PLC Upgradation for DAS | NL-N-TS2-002-04-01-02 | 5130640 | 5130640 | 0 | 5130640 | 0 | 5130640 | 5130640 | 0 | 5130640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5130640 | 5130640 | 0 | 5130640 | 0
79 | * | Energy Management System for LHS | NL-N-TS2-002-04-01-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | * | HMI Hardware Workstation | NL-N-TS2-002-04-01-04 | 700500.02 | 700500.02 | 0 | 700500.02 | 0 | 700500.02 | 700500.02 | 0 | 700500.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700500.02 | 700500.02 | 0 | 700500.02 | 0
81 | * | Magnetic Separator | NL-N-TS2-002-04-01-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | * | Upgrade ST-II Bunker Automation System | NL-N-TS2-002-04-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | * | Upgrade FPS (AMVWSS) for LHS Conveyors | NL-N-TS2-002-04-01-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | * | Yard conveyor PLC conversion | NL-N-TS2-002-04-01-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | * | Addressable pull cord switch | NL-N-TS2-002-04-01-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | * | Retrofit EM type protective relays | NL-N-TS2-002-04-01-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | * | Procurement of Magnetic Separators | NL-N-TS2-002-04-01-13 | 9192000 | 0 | 9192000 | 9192000 | 0 | 0 | 0 | 0 | 0 | 0 | 9192000 | 0 | 9192000 | 9192000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9192000 | 0 | 9192000 | 9192000 | 0
88 | * | 2T capacity Battery Operated platform Tr | NL-N-TS2-002-04-01-14 | 690950 | 0 | 690950 | 690950 | 0 | 0 | 0 | 0 | 0 | 0 | 690950 | 0 | 690950 | 690950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 690950 | 0 | 690950 | 690950 | 0
89 | * | Linear Heat Sensing (LHS) Cable | NL-N-TS2-002-04-01-15 | 1472050 | 0 | 849600 | 849600 | 622450 | 0 | 0 | 0 | 0 | 0 | 1472050 | 0 | 849600 | 849600 | 622450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1472050 | 0 | 849600 | 849600 | 622450
90 | * | Rotex 2/2 Direct Acting Solenoid Valve | NL-N-TS2-002-04-01-16 | 124895.75 | 0 | 124895.75 | 124895.75 | 0 | 0 | 0 | 0 | 0 | 0 | 124895.75 | 0 | 124895.75 | 124895.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124895.75 | 0 | 124895.75 | 124895.75 | 0
91 | * | Procurement of Infra red Detector (IRD) | NL-N-TS2-002-04-01-17 | 1409117 | 0 | 1409116.6 | 1409116.6 | 0.4 | 0 | 0 | 0 | 0 | 0 | 1409117 | 0 | 1409116.6 | 1409116.6 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409117 | 0 | 1409116.6 | 1409116.6 | 0.4
92 | ** | ESP CONTROLS | NL-N-TS2-002-04-02 | 21324866.55 | 19146271.9 | 2178594.65 | 21324866.55 | 0 | 19146271.9 | 19146271.9 | 0 | 19146271.9 | 0 | 2178594.65 | 0 | 2178594.65 | 2178594.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21324866.55 | 19146271.9 | 2178594.65 | 21324866.55 | 0
93 | * | Boiler Lift-5 & 6 | NL-N-TS2-002-04-02-01 | 15340000 | 14572999.99 | 767000.01 | 15340000 | 0 | 14572999.99 | 14572999.99 | 0 | 14572999.99 | 0 | 767000.01 | 0 | 767000.01 | 767000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15340000 | 14572999.99 | 767000.01 | 15340000 | 0
94 | * | EOT crane Revamping | NL-N-TS2-002-04-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | * | DG Sets AMF Panel | NL-N-TS2-002-04-02-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | * | Boiler lift- 2,4 & 7 | NL-N-TS2-002-04-02-04 | 2060704.8 | 2060704.8 | 0 | 2060704.8 | 0 | 2060704.8 | 2060704.8 | 0 | 2060704.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060704.8 | 2060704.8 | 0 | 2060704.8 | 0
97 | * | ESP -4 Electronic controllers | NL-N-TS2-002-04-02-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | * | ESP -5 Electronic controllers | NL-N-TS2-002-04-02-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | * | Supply,Erection&Commisioning of New Lift | NL-N-TS2-002-04-02-07 | 1400000.38 | 1400000.38 | 0 | 1400000.38 | 0 | 1400000.38 | 1400000.38 | 0 | 1400000.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000.38 | 1400000.38 | 0 | 1400000.38 | 0
100 | * | Retrofitting of Unit-3 ACP | NL-N-TS2-002-04-02-08 | 1112566.73 | 1112566.73 | 0 | 1112566.73 | 0 | 1112566.73 | 1112566.73 | 0 | 1112566.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1112566.73 | 1112566.73 | 0 | 1112566.73 | 0
101 | * | Procurement and inst of 6 passenger lift | NL-N-TS2-002-04-02-09 | 1411594.64 | 0 | 1411594.64 | 1411594.64 | 0 | 0 | 0 | 0 | 0 | 0 | 1411594.64 | 0 | 1411594.64 | 1411594.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411594.64 | 0 | 1411594.64 | 1411594.64 | 0
102 | ** | ELECTRICAL MAINTENANCE-I | NL-N-TS2-002-04-03 | 353326423.16 | 168526902.09 | 184799521.07 | 353326423.16 | 0 | 152783839.18 | 152783839.18 | 0 | 152783839.18 | 0 | 200542583.98 | 15743062.91 | 184799521.07 | 200542583.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353326423.16 | 168526902.09 | 184799521.07 | 353326423.16 | 0
103 | * | ESP Hoist for stage I Units | NL-N-TS2-002-04-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | * | Generator Transformer | NL-N-TS2-002-04-03-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | * | 1600KVA UST transformer for stage I | NL-N-TS2-002-04-03-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | * | 20 MVA UAT s | NL-N-TS2-002-04-03-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | * | 6.6Kv, 710KW, 590 rpm class F, Squirrel | NL-N-TS2-002-04-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | * | 6.6 KV 515KW,3 ph, SQ IM,Ins.class' F' , | NL-N-TS2-002-04-03-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | * | 6.6Kv, 600KW, 590 rpm class F, Squirrel | NL-N-TS2-002-04-03-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | * | 6.6 KV 600KW,3 ph, SQ IM,Ins.class' F' , | NL-N-TS2-002-04-03-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | * | Retrofitting of 6.6KV Breaker-Stage-II | NL-N-TS2-002-04-03-09 | 11578597.04 | 9625317.16 | 1953279.88 | 11578597.04 | 0 | 0 | 0 | 0 | 0 | 0 | 11578597.04 | 9625317.16 | 1953279.88 | 11578597.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11578597.04 | 9625317.16 | 1953279.88 | 11578597.04 | 0
112 | * | Erection, commissioning of New 6.6KV/3.3 | NL-N-TS2-002-04-03-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | * | GENERATOR STATOR END WINDING SPARES | NL-N-TS2-002-04-03-11 | 6826717.25 | 6826717.25 | 0 | 6826717.25 | 0 | 6826717.25 | 6826717.25 | 0 | 6826717.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6826717.25 | 6826717.25 | 0 | 6826717.25 | 0
114 | * | OIP 400 KV Bushing - Stage-2 GT | NL-N-TS2-002-04-03-12 | 4309907.75 | 4309907.75 | 0 | 4309907.75 | 0 | 0 | 0 | 0 | 0 | 0 | 4309907.75 | 4309907.75 | 0 | 4309907.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4309907.75 | 4309907.75 | 0 | 4309907.75 | 0
115 | * | LVBushing for Stage-1 GT with metal part | NL-N-TS2-002-04-03-13 | 1947000 | 0 | 1947000 | 1947000 | 0 | 0 | 0 | 0 | 0 | 0 | 1947000 | 0 | 1947000 | 1947000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1947000 | 0 | 1947000 | 1947000 | 0
116 | * | LV Bushing for Stage-1 GT porcelien only | NL-N-TS2-002-04-03-14 | 251233.8 | 0 | 251233.8 | 251233.8 | 0 | 0 | 0 | 0 | 0 | 0 | 251233.8 | 0 | 251233.8 | 251233.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251233.8 | 0 | 251233.8 | 251233.8 | 0
117 | * | LV Bushing for Stage-2 GT metal part | NL-N-TS2-002-04-03-15 | 2920500 | 0 | 2920500 | 2920500 | 0 | 0 | 0 | 0 | 0 | 0 | 2920500 | 0 | 2920500 | 2920500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2920500 | 0 | 2920500 | 2920500 | 0
118 | * | LV Bushing for Stage-2 GT porcelien only | NL-N-TS2-002-04-03-16 | 502467.6 | 0 | 502467.6 | 502467.6 | 0 | 0 | 0 | 0 | 0 | 0 | 502467.6 | 0 | 502467.6 | 502467.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502467.6 | 0 | 502467.6 | 502467.6 | 0
119 | * | Oil Pump for stage-1 GT | NL-N-TS2-002-04-03-17 | 389400 | 0 | 389400 | 389400 | 0 | 0 | 0 | 0 | 0 | 0 | 389400 | 0 | 389400 | 389400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389400 | 0 | 389400 | 389400 | 0
120 | * | Oil Pump for stage-2 GT | NL-N-TS2-002-04-03-18 | 389400 | 0 | 389400 | 389400 | 0 | 0 | 0 | 0 | 0 | 0 | 389400 | 0 | 389400 | 389400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389400 | 0 | 389400 | 389400 | 0
121 | * | 160 KVA LDB Transformer | NL-N-TS2-002-04-03-19 | 1402289.81 | 1402289.81 | 0 | 1402289.81 | 0 | 1402289.81 | 1402289.81 | 0 | 1402289.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1402289.81 | 1402289.81 | 0 | 1402289.81 | 0
122 | * | Retrofitting of Tadiran Exchange TPS-2 | NL-N-TS2-002-04-03-21 | 2400000 | 2400000 | 0 | 2400000 | 0 | 2400000 | 2400000 | 0 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 2400000 | 0 | 2400000 | 0
123 | * | Purchase of 12 KV,2500A VCBs | NL-N-TS2-002-04-03-22 | 3841472.82 | 3841472.82 | 0 | 3841472.82 | 0 | 3841472.82 | 3841472.82 | 0 | 3841472.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3841472.82 | 3841472.82 | 0 | 3841472.82 | 0
124 | * | Generator Seal Rings Turbine&Exiter Ends | NL-N-TS2-002-04-03-23 | 1517272 | 1517272 | 0 | 1517272 | 0 | 1517272 | 1517272 | 0 | 1517272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517272 | 1517272 | 0 | 1517272 | 0
125 | * | 100KVA LTG Transformer R&R Work | NL-N-TS2-002-04-03-24 | 446040.03 | 423738 | 22302.03 | 446040.03 | 0 | 423738 | 423738 | 0 | 423738 | 0 | 22302.03 | 0 | 22302.03 | 22302.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446040.03 | 423738 | 22302.03 | 446040.03 | 0
126 | * | 400KVA Bore Well Transformer R&R Work | NL-N-TS2-002-04-03-25 | 472000.03 | 472000 | 0.03 | 472000.03 | 0 | 472000 | 472000 | 0 | 472000 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472000.03 | 472000 | 0.03 | 472000.03 | 0
127 | * | Field over voltage circuit assembly DSES | NL-N-TS2-002-04-03-26 | 325385 | 325385 | 0 | 325385 | 0 | 325385 | 325385 | 0 | 325385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325385 | 325385 | 0 | 325385 | 0
128 | * | Differential Pressure Regulator A & B | NL-N-TS2-002-04-03-27 | 3581659.62 | 3581659.62 | 0 | 3581659.62 | 0 | 3581659.62 | 3581659.62 | 0 | 3581659.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3581659.62 | 3581659.62 | 0 | 3581659.62 | 0
129 | * | Radio Remote Control for TG EOT Crane | NL-N-TS2-002-04-03-28 | 304463.6 | 304463.6 | 0 | 304463.6 | 0 | 304463.6 | 304463.6 | 0 | 304463.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304463.6 | 304463.6 | 0 | 304463.6 | 0
130 | * | Dielectric Coating at 6.6 KV SWGR Panel | NL-N-TS2-002-04-03-29 | 1688344 | 1688344 | 0 | 1688344 | 0 | 1688344 | 1688344 | 0 | 1688344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1688344 | 1688344 | 0 | 1688344 | 0
131 | * | Carbon brush holder & Coil spring | NL-N-TS2-002-04-03-30 | 2041926.68 | 2041926.68 | 0 | 2041926.68 | 0 | 2041926.68 | 2041926.68 | 0 | 2041926.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2041926.68 | 2041926.68 | 0 | 2041926.68 | 0
132 | * | AC Drive suitable for 4 & 5.5KW Motors | NL-N-TS2-002-04-03-32 | 1716500.1 | 1716500.1 | 0 | 1716500.1 | 0 | 1716500.1 | 1716500.1 | 0 | 1716500.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1716500.1 | 1716500.1 | 0 | 1716500.1 | 0
133 | * | Erection & Commissioning of UAT-4B | NL-N-TS2-002-04-03-33 | 525100 | 525100 | 0 | 525100 | 0 | 525100 | 525100 | 0 | 525100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525100 | 525100 | 0 | 525100 | 0
134 | * | Complete Overhauling of UAT | NL-N-TS2-002-04-03-34 | 222548 | 222548 | 0 | 222548 | 0 | 222548 | 222548 | 0 | 222548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222548 | 222548 | 0 | 222548 | 0
135 | * | Rectification of NGR of ST-1&2 | NL-N-TS2-002-04-03-36 | 283200 | 283200 | 0 | 283200 | 0 | 283200 | 283200 | 0 | 283200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283200 | 283200 | 0 | 283200 | 0
136 | * | Generator Spares | NL-N-TS2-002-04-03-45 | 550980 | 550980 | 0 | 550980 | 0 | 550980 | 550980 | 0 | 550980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550980 | 550980 | 0 | 550980 | 0
137 | * | Transformer Spares | NL-N-TS2-002-04-03-46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | * | HT Motors & HT Switch Gears Spares | NL-N-TS2-002-04-03-47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | * | Dry Type Indoor Excitation Transformer | NL-N-TS2-002-04-03-51 | 8341426.72 | 8341426.72 | 0 | 8341426.72 | 0 | 8341426.72 | 8341426.72 | 0 | 8341426.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8341426.72 | 8341426.72 | 0 | 8341426.72 | 0
140 | * | Inter Connecting Transformer | NL-N-TS2-002-04-03-52 | 2322594.03 | 2322594 | 0.03 | 2322594.03 | 0 | 2322594 | 2322594 | 0 | 2322594 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2322594.03 | 2322594 | 0.03 | 2322594.03 | 0
141 | * | Generator Rotor Turning Roll-50 Tons | NL-N-TS2-002-04-03-55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | * | Main & Stuffing Bellows for DPRV | NL-N-TS2-002-04-03-56 | 631717.39 | 631717.39 | 0 | 631717.39 | 0 | 631717.39 | 631717.39 | 0 | 631717.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631717.39 | 631717.39 | 0 | 631717.39 | 0
143 | * | Split AC 2 Ton Capacity 5 Star rating | NL-N-TS2-002-04-03-57 | 1024960 | 1024960 | 0 | 1024960 | 0 | 1024960 | 1024960 | 0 | 1024960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024960 | 1024960 | 0 | 1024960 | 0
144 | * | Rejuvenation of ESP STr Earth Pits | NL-N-TS2-002-04-03-58 | 552239.98 | 552239.68 | 0.3 | 552239.98 | 0 | 552239.68 | 552239.68 | 0 | 552239.68 | 0 | 0.3 | 0 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552239.98 | 552239.68 | 0.3 | 552239.98 | 0
145 | * | Refregirant H2 Gas Dryer-ST II Generator | NL-N-TS2-002-04-03-59 | 2468559.99 | 2057133 | 411426.99 | 2468559.99 | 0 | 2057133 | 2057133 | 0 | 2057133 | 0 | 411426.99 | 0 | 411426.99 | 411426.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2468559.99 | 2057133 | 411426.99 | 2468559.99 | 0
146 | * | Vacuum Cleaner for HT Panel | NL-N-TS2-002-04-03-60 | 18336.1 | 18336.1 | 0 | 18336.1 | 0 | 18336.1 | 18336.1 | 0 | 18336.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18336.1 | 18336.1 | 0 | 18336.1 | 0
147 | * | REFREGIRANT TYPE H2GAS DRIYER FOR GENER | NL-N-TS2-002-04-03-61 | 2095500 | 1676400 | 419100 | 2095500 | 0 | 1676400 | 1676400 | 0 | 1676400 | 0 | 419100 | 0 | 419100 | 419100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2095500 | 1676400 | 419100 | 2095500 | 0
148 | * | refurishment of Rotor of Unit -3 ,Gen | NL-N-TS2-002-04-03-62 | 96027635.01 | 0 | 96027635.01 | 96027635.01 | 0 | 0 | 0 | 0 | 0 | 0 | 96027635.01 | 0 | 96027635.01 | 96027635.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96027635.01 | 0 | 96027635.01 | 96027635.01 | 0
149 | * | Rectification of Unit-5 Generator | NL-N-TS2-002-04-03-63 | 25075000 | 25075000 | 0 | 25075000 | 0 | 25075000 | 25075000 | 0 | 25075000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25075000 | 25075000 | 0 | 25075000 | 0
150 | * | digital Tachometer for speed mes C&PBF M | NL-N-TS2-002-04-03-64 | 51174.01 | 51174.01 | 0 | 51174.01 | 0 | 51174.01 | 51174.01 | 0 | 51174.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51174.01 | 51174.01 | 0 | 51174.01 | 0
151 | * | Top panel mount cooler for VFD | NL-N-TS2-002-04-03-65 | 2200500 | 2200500 | 0 | 2200500 | 0 | 2200500 | 2200500 | 0 | 2200500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200500 | 2200500 | 0 | 2200500 | 0
152 | * | 11/0.433kv transformer rep rectification | NL-N-TS2-002-04-03-66 | 584640.03 | 501500 | 83140.03 | 584640.03 | 0 | 501500 | 501500 | 0 | 501500 | 0 | 83140.03 | 0 | 83140.03 | 83140.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584640.03 | 501500 | 83140.03 | 584640.03 | 0
153 | * | Seal oil pump for stage-2 Generator | NL-N-TS2-002-04-03-67 | 1337576.56 | 1337576.56 | 0 | 1337576.56 | 0 | 1337576.56 | 1337576.56 | 0 | 1337576.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1337576.56 | 1337576.56 | 0 | 1337576.56 | 0
154 | * | tranformer movement rail support | NL-N-TS2-002-04-03-68 | 3223763.56 | 2379429.56 | 844334 | 3223763.56 | 0 | 2379429.56 | 2379429.56 | 0 | 2379429.56 | 0 | 844334 | 0 | 844334 | 844334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3223763.56 | 2379429.56 | 844334 | 3223763.56 | 0
155 | * | Arresting oil leaks in LV bushings GT-2 | NL-N-TS2-002-04-03-69 | 323480.03 | 231280 | 92200.03 | 323480.03 | 0 | 231280 | 231280 | 0 | 231280 | 0 | 92200.03 | 0 | 92200.03 | 92200.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323480.03 | 231280 | 92200.03 | 323480.03 | 0
156 | * | 3X240 sqmm XLPE cable | NL-N-TS2-002-04-03-70 | 6101753.79 | 6101753.79 | 0 | 6101753.79 | 0 | 6101753.79 | 6101753.79 | 0 | 6101753.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6101753.79 | 6101753.79 | 0 | 6101753.79 | 0
157 | * | Purchase of 420 KV OIP bushing for ICT | NL-N-TS2-002-04-03-71 | 5748960 | 0 | 5748960 | 5748960 | 0 | 0 | 0 | 0 | 0 | 0 | 5748960 | 0 | 5748960 | 5748960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5748960 | 0 | 5748960 | 5748960 | 0
158 | * | Overhauling work of 6.6 kv Motor in TP2 | NL-N-TS2-002-04-03-72 | 4029700.01 | 3109300 | 920400.01 | 4029700.01 | 0 | 3109300 | 3109300 | 0 | 3109300 | 0 | 920400.01 | 0 | 920400.01 | 920400.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4029700.01 | 3109300 | 920400.01 | 4029700.01 | 0
159 | * | DCS 800 converter FOR U-2 DSES | NL-N-TS2-002-04-03-73 | 1911600 | 1911600 | 0 | 1911600 | 0 | 1911600 | 1911600 | 0 | 1911600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1911600 | 1911600 | 0 | 1911600 | 0
160 | * | Purchase of 2 T battery platform truck | NL-N-TS2-002-04-03-74 | 505000 | 505000 | 0 | 505000 | 0 | 0 | 0 | 0 | 0 | 0 | 505000 | 505000 | 0 | 505000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 505000 | 505000 | 0 | 505000 | 0
161 | * | Replacement of 2650 KVA Transformer | NL-N-TS2-002-04-03-75 | 1633545.02 | 1563795 | 69750.02 | 1633545.02 | 0 | 1563795 | 1563795 | 0 | 1563795 | 0 | 69750.02 | 0 | 69750.02 | 69750.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1633545.02 | 1563795 | 69750.02 | 1633545.02 | 0
162 | * | Transformer Oil IS335/1993 | NL-N-TS2-002-04-03-76 | 12190001.8 | 0 | 12190001.8 | 12190001.8 | 0 | 0 | 0 | 0 | 0 | 0 | 12190001.8 | 0 | 12190001.8 | 12190001.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12190001.8 | 0 | 12190001.8 | 12190001.8 | 0
163 | * | Stator water centrifugal pump-Gen Mtce | NL-N-TS2-002-04-03-77 | 586090 | 0 | 586090 | 586090 | 0 | 0 | 0 | 0 | 0 | 0 | 586090 | 0 | 586090 | 586090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586090 | 0 | 586090 | 586090 | 0
164 | * | ST-Repair & RC of 3.3/6.6 KV HT motors | NL-N-TS2-002-04-03-78 | 6941940.03 | 6941940 | 0.03 | 6941940.03 | 0 | 6941940 | 6941940 | 0 | 6941940 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6941940.03 | 6941940 | 0.03 | 6941940.03 | 0
165 | * | Purchase of St-I Digital Exitation Spare | NL-N-TS2-002-04-03-79 | 1803653.6 | 1803653.6 | 0 | 1803653.6 | 0 | 396975.6 | 396975.6 | 0 | 396975.6 | 0 | 1406678 | 1406678 | 0 | 1406678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803653.6 | 1803653.6 | 0 | 1803653.6 | 0
166 | * | Seal rings Tubine&Exiter end 210 MW | NL-N-TS2-002-04-03-80 | 6192367.66 | 0 | 6192367.66 | 6192367.66 | 0 | 0 | 0 | 0 | 0 | 0 | 6192367.66 | 0 | 6192367.66 | 6192367.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6192367.66 | 0 | 6192367.66 | 6192367.66 | 0
167 | * | Megger make Coulometric Karl Fisher Titr | NL-N-TS2-002-04-03-81 | 1714446.56 | 0 | 1714446.56 | 1714446.56 | 0 | 0 | 0 | 0 | 0 | 0 | 1714446.56 | 0 | 1714446.56 | 1714446.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1714446.56 | 0 | 1714446.56 | 1714446.56 | 0
168 | * | MURR make power supply unit for stage-I | NL-N-TS2-002-04-03-83 | 307941.06 | 307941.06 | 0 | 307941.06 | 0 | 307941.06 | 307941.06 | 0 | 307941.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307941.06 | 307941.06 | 0 | 307941.06 | 0
169 | * | Generator Stator Winding Bar of BHEL mak | NL-N-TS2-002-04-03-84 | 17006868 | 0 | 17006868 | 17006868 | 0 | 0 | 0 | 0 | 0 | 0 | 17006868 | 0 | 17006868 | 17006868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17006868 | 0 | 17006868 | 17006868 | 0
170 | * | Rotor Fan blades for 210 MW Turbo Genera | NL-N-TS2-002-04-03-85 | 29557734.47 | 29557734.47 | 0 | 29557734.47 | 0 | 29557734.47 | 29557734.47 | 0 | 29557734.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29557734.47 | 29557734.47 | 0 | 29557734.47 | 0
171 | * | Proc of Submersible pump | NL-N-TS2-002-04-03-86 | 204299.99 | 204299.99 | 0 | 204299.99 | 0 | 204299.99 | 204299.99 | 0 | 204299.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204299.99 | 204299.99 | 0 | 204299.99 | 0
172 | * | Purchase of Mill Motors for stage-I & II | NL-N-TS2-002-04-03-87 | 22978497 | 0 | 22978497 | 22978497 | 0 | 0 | 0 | 0 | 0 | 0 | 22978497 | 0 | 22978497 | 22978497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22978497 | 0 | 22978497 | 22978497 | 0
173 | * | Retrofitting of Public Address System | NL-N-TS2-002-04-03-88 | 1820650.01 | 0 | 1820650.01 | 1820650.01 | 0 | 0 | 0 | 0 | 0 | 0 | 1820650.01 | 0 | 1820650.01 | 1820650.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1820650.01 | 0 | 1820650.01 | 1820650.01 | 0
174 | * | Refurbishment of seal oil coolers | NL-N-TS2-002-04-03-90 | 1056000.01 | 0 | 1056000.01 | 1056000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000.01 | 0 | 1056000.01 | 1056000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000.01 | 0 | 1056000.01 | 1056000.01 | 0
175 | * | SCISSOR LIFT | NL-N-TS2-002-04-03-91 | 846450 | 0 | 846450 | 846450 | 0 | 0 | 0 | 0 | 0 | 0 | 846450 | 0 | 846450 | 846450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 846450 | 0 | 846450 | 846450 | 0
176 | * | ST work repair and rect of welding M/C | NL-N-TS2-002-04-03-92 | 1108280.03 | 687940 | 420340.03 | 1108280.03 | 0 | 791780 | 791780 | 0 | 791780 | 0 | 316500.03 | -103840 | 420340.03 | 316500.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108280.03 | 687940 | 420340.03 | 1108280.03 | 0
177 | * | Electrolytic Cells in Stage- 2 Hyd plant | NL-N-TS2-002-04-03-93 | 3630510.04 | 3590720.53 | 39789.51 | 3630510.04 | 0 | 3590720.53 | 3590720.53 | 0 | 3590720.53 | 0 | 39789.51 | 0 | 39789.51 | 39789.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3630510.04 | 3590720.53 | 39789.51 | 3630510.04 | 0
178 | * | Hydraulic Torque wrench | NL-N-TS2-002-04-03-94 | 1534639.15 | 1534639.15 | 0 | 1534639.15 | 0 | 1534639.15 | 1534639.15 | 0 | 1534639.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534639.15 | 1534639.15 | 0 | 1534639.15 | 0
179 | * | 10 KV Insulation Tester | NL-N-TS2-002-04-03-95 | 802164 | 0 | 802164 | 802164 | 0 | 0 | 0 | 0 | 0 | 0 | 802164 | 0 | 802164 | 802164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802164 | 0 | 802164 | 802164 | 0
180 | * | Retrofit & Upgrade the existing GPS syst | NL-N-TS2-002-04-03-96 | 2408843.82 | 2360666.95 | 48176.87 | 2408843.82 | 0 | 2360666.95 | 2360666.95 | 0 | 2360666.95 | 0 | 48176.87 | 0 | 48176.87 | 48176.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2408843.82 | 2360666.95 | 48176.87 | 2408843.82 | 0
181 | * | Hydogen gas Compressor 25 NM3/Hr | NL-N-TS2-002-04-03-97 | 18488300.73 | 15408300.74 | 3079999.99 | 18488300.73 | 0 | 15408300.74 | 15408300.74 | 0 | 15408300.74 | 0 | 3079999.99 | 0 | 3079999.99 | 3079999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18488300.73 | 15408300.74 | 3079999.99 | 18488300.73 | 0
182 | * | Supply,insta and comm of Digital Wireles | NL-N-TS2-002-04-03-98 | 2477528 | 2477528 | 0 | 2477528 | 0 | 2477528 | 2477528 | 0 | 2477528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2477528 | 2477528 | 0 | 2477528 | 0
183 | * | 1cX1000 Sq mm Al XLPE insulated cable | NL-N-TS2-002-04-03-99 | 3025149.84 | 0 | 3025149.84 | 3025149.84 | 0 | 0 | 0 | 0 | 0 | 0 | 3025149.84 | 0 | 3025149.84 | 3025149.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3025149.84 | 0 | 3025149.84 | 3025149.84 | 0
184 | ** | ELECTRICAL MAINTENANCE-II | NL-N-TS2-002-04-04 | 71363826.31 | 14244104.81 | 57119701.5 | 71363806.31 | 20 | 14244104.81 | 14244104.81 | 0 | 14244104.81 | 0 | 57119721.5 | 0 | 57119701.5 | 57119701.5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71363826.31 | 14244104.81 | 57119701.5 | 71363806.31 | 20
185 | * | Retrofitting of Stage-1 WTP MCC panel | NL-N-TS2-002-04-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | * | Retrofit of Stage-II UCB AC plant MCC | NL-N-TS2-002-04-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | * | Retrofitting of stage-1 ESP AHU MCC | NL-N-TS2-002-04-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | * | Procurement of critical LT motors | NL-N-TS2-002-04-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | * | Indigeneous lignite damper Stage-II | NL-N-TS2-002-04-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | * | Procurement of chimney Aviation Lights(S | NL-N-TS2-002-04-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | * | Revamping of lighting System | NL-N-TS2-002-04-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | * | Stage-I Soot blower system Modules revam | NL-N-TS2-002-04-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | * | Purchase of Switchgear Components-U2/U3 | NL-N-TS2-002-04-04-09 | 5707638.41 | 5707638.41 | 0 | 5707638.41 | 0 | 5707638.41 | 5707638.41 | 0 | 5707638.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5707638.41 | 5707638.41 | 0 | 5707638.41 | 0
194 | * | Retrofit of Switchgear Components-U2/U3 | NL-N-TS2-002-04-04-10 | 2259373.83 | 2239533.8 | 19840.03 | 2259373.83 | 0 | 2239533.8 | 2239533.8 | 0 | 2239533.8 | 0 | 19840.03 | 0 | 19840.03 | 19840.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2259373.83 | 2239533.8 | 19840.03 | 2259373.83 | 0
195 | * | PMCC panel for Stage-I AC plant | NL-N-TS2-002-04-04-11 | 12824240 | 0 | 12824240 | 12824240 | 0 | 0 | 0 | 0 | 0 | 0 | 12824240 | 0 | 12824240 | 12824240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12824240 | 0 | 12824240 | 12824240 | 0
196 | * | Supply & Retrofit of ACBs in Unit-4 & 5 | NL-N-TS2-002-04-04-12 | 29666591.81 | 0 | 29666591.81 | 29666591.81 | 0 | 0 | 0 | 0 | 0 | 0 | 29666591.81 | 0 | 29666591.81 | 29666591.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29666591.81 | 0 | 29666591.81 | 29666591.81 | 0
197 | * | Supply of spares&Replacement in ACBs/TS2 | NL-N-TS2-002-04-04-13 | 1873579.53 | 1873456.5 | 123.03 | 1873579.53 | 0 | 1873456.5 | 1873456.5 | 0 | 1873456.5 | 0 | 123.03 | 0 | 123.03 | 123.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1873579.53 | 1873456.5 | 123.03 | 1873579.53 | 0
198 | * | Refurbish of Festooning-ST2 Bunker Hoist | NL-N-TS2-002-04-04-14 | 1430560.05 | 1429791.84 | 768.21 | 1430560.05 | 0 | 1429791.84 | 1429791.84 | 0 | 1429791.84 | 0 | 768.21 | 0 | 768.21 | 768.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430560.05 | 1429791.84 | 768.21 | 1430560.05 | 0
199 | * | Retrofitting of Airwasher MCC | NL-N-TS2-002-04-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | * | Retrofitting of Borewell Pums LT Panels | NL-N-TS2-002-04-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | * | Rejuvenation of Cables | NL-N-TS2-002-04-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | * | Electrical for SSBs | NL-N-TS2-002-04-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | * | Indigeneous lignite damper Stage-I | NL-N-TS2-002-04-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | * | Retrofit ofLHS MCC | NL-N-TS2-002-04-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | * | Retrofit of UNIT-1 LT MCC | NL-N-TS2-002-04-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | * | High MAST lighting Towers | NL-N-TS2-002-04-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | * | Rewamping of Cable Trays | NL-N-TS2-002-04-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | * | Revamping of Motor Installations | NL-N-TS2-002-04-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | * | Revamping of Valve Switchgear | NL-N-TS2-002-04-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | * | 2 ton Battery powered I P Truck | NL-N-TS2-002-04-04-26 | 514985 | 514985 | 0 | 514985 | 0 | 514985 | 514985 | 0 | 514985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514985 | 514985 | 0 | 514985 | 0
211 | * | 2 Ton Battery powered I P Truck | NL-N-TS2-002-04-04-27 | 516669.62 | 516669.62 | 0 | 516669.62 | 0 | 516669.62 | 516669.62 | 0 | 516669.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516669.62 | 516669.62 | 0 | 516669.62 | 0
212 | * | Refurbish of 3.5cX300 Sq.mm Al cable | NL-N-TS2-002-04-04-28 | 525864.3 | 0 | 525864.3 | 525864.3 | 0 | 0 | 0 | 0 | 0 | 0 | 525864.3 | 0 | 525864.3 | 525864.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525864.3 | 0 | 525864.3 | 525864.3 | 0
213 | * | Procurement of Dewatering Pump | NL-N-TS2-002-04-04-29 | 136731.95 | 136731.95 | 0 | 136731.95 | 0 | 136731.95 | 136731.95 | 0 | 136731.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136731.95 | 136731.95 | 0 | 136731.95 | 0
214 | * | Procurement of MCM Measuring instrument | NL-N-TS2-002-04-04-30 | 190000.06 | 190000.06 | 0 | 190000.06 | 0 | 190000.06 | 190000.06 | 0 | 190000.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000.06 | 190000.06 | 0 | 190000.06 | 0
215 | * | Rotork make actuators spares Forty items | NL-N-TS2-002-04-04-31 | 1635297.63 | 1635297.63 | 0 | 1635297.63 | 0 | 1635297.63 | 1635297.63 | 0 | 1635297.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635297.63 | 1635297.63 | 0 | 1635297.63 | 0
216 | * | Procurement of Stage-I & II motors | NL-N-TS2-002-04-04-32 | 1753587.38 | 0 | 1753587.38 | 1753587.38 | 0 | 0 | 0 | 0 | 0 | 0 | 1753587.38 | 0 | 1753587.38 | 1753587.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1753587.38 | 0 | 1753587.38 | 1753587.38 | 0
217 | * | Procurement of motors (LEP)for stg1&2 | NL-N-TS2-002-04-04-33 | 2278347.54 | 0 | 2278347.54 | 2278347.54 | 0 | 0 | 0 | 0 | 0 | 0 | 2278347.54 | 0 | 2278347.54 | 2278347.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2278347.54 | 0 | 2278347.54 | 2278347.54 | 0
218 | * | 1100 V greade 3Cx2.5 sq mm copper cable | NL-N-TS2-002-04-04-34 | 2280000 | 0 | 2280000 | 2280000 | 0 | 0 | 0 | 0 | 0 | 0 | 2280000 | 0 | 2280000 | 2280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2280000 | 0 | 2280000 | 2280000 | 0
219 | * | Purchase of 12"/15"/18"/24" Exhaust fan | NL-N-TS2-002-04-04-35 | 1348335.2 | 0 | 1348335.2 | 1348335.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1348335.2 | 0 | 1348335.2 | 1348335.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1348335.2 | 0 | 1348335.2 | 1348335.2 | 0
220 | * | 1100V grade,3.5C*35 Sqmm Aluminium, XLPE | NL-N-TS2-002-04-04-36 | 967500 | 0 | 967500 | 967500 | 0 | 0 | 0 | 0 | 0 | 0 | 967500 | 0 | 967500 | 967500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 967500 | 0 | 967500 | 967500 | 0
221 | * | 1100V grade , 3.5 C X 70 Sqmm Al cable | NL-N-TS2-002-04-04-39 | 2264000 | 0 | 2264000 | 2264000 | 0 | 0 | 0 | 0 | 0 | 0 | 2264000 | 0 | 2264000 | 2264000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2264000 | 0 | 2264000 | 2264000 | 0
222 | * | 1100V grade 3CX4sqmm Cu XLPE Cable | NL-N-TS2-002-04-04-40 | 384000 | 0 | 384000 | 384000 | 0 | 0 | 0 | 0 | 0 | 0 | 384000 | 0 | 384000 | 384000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384000 | 0 | 384000 | 384000 | 0
223 | * | WBS-Budget-Repair& Restore of CT pump br | NL-N-TS2-002-04-04-41 | 395064 | 0 | 395064 | 395064 | 0 | 0 | 0 | 0 | 0 | 0 | 395064 | 0 | 395064 | 395064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395064 | 0 | 395064 | 395064 | 0
224 | * | FIRE SURVIVAL CABLES | NL-N-TS2-002-04-04-42 | 2411460 | 0 | 2411440 | 2411440 | 20 | 0 | 0 | 0 | 0 | 0 | 2411460 | 0 | 2411440 | 2411440 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2411460 | 0 | 2411440 | 2411440 | 20
225 | ** | SWITCH YARD | NL-N-TS2-002-04-05 | 230842719.07 | 86276388.04 | 143004801.05 | 229281189.09 | 1561529.98 | 86276388.04 | 86276388.04 | 0 | 86276388.04 | 0 | 144566331.03 | 0 | 143004801.05 | 143004801.05 | 1561529.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230842719.07 | 86276388.04 | 143004801.05 | 229281189.09 | 1561529.98
226 | * | Secondphase 400kV Isolator rejuvenation | NL-N-TS2-002-04-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | * | Wave(Line) Traps Spares for 230KV 8 Nos | NL-N-TS2-002-04-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | * | Thermal Imaging Camera | NL-N-TS2-002-04-05-03 | 3657174 | 3657174 | 0 | 3657174 | 0 | 3657174 | 3657174 | 0 | 3657174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3657174 | 3657174 | 0 | 3657174 | 0
229 | * | Self propelled Scissor Lift | NL-N-TS2-002-04-05-04 | 465000 | 465000 | 0 | 465000 | 0 | 465000 | 465000 | 0 | 465000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465000 | 465000 | 0 | 465000 | 0
230 | * | SF6 gas Analyzer | NL-N-TS2-002-04-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | * | Circuit breaker Analyzer | NL-N-TS2-002-04-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | * | Amp Clamp Tool | NL-N-TS2-002-04-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | * | RCC concrete shed of size 40 ft x 30 ft | NL-N-TS2-002-04-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | * | Discharge Rods | NL-N-TS2-002-04-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | * | Cable tray replacement | NL-N-TS2-002-04-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | * | 360KV 20KA DISCHARGE CLASS IV GAPLESS ZN | NL-N-TS2-002-04-05-11 | 1505225.72 | 1505225.72 | 0 | 1505225.72 | 0 | 1505225.72 | 1505225.72 | 0 | 1505225.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1505225.72 | 1505225.72 | 0 | 1505225.72 | 0
237 | * | 245KV CTs Type-I & II | NL-N-TS2-002-04-05-12 | 8544755.11 | 8544755.11 | 0 | 8544755.11 | 0 | 8544755.11 | 8544755.11 | 0 | 8544755.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8544755.11 | 8544755.11 | 0 | 8544755.11 | 0
238 | * | Clamps for HTLS Conductors | NL-N-TS2-002-04-05-13 | 873047.05 | 873047.05 | 0 | 873047.05 | 0 | 873047.05 | 873047.05 | 0 | 873047.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 873047.05 | 873047.05 | 0 | 873047.05 | 0
239 | * | Self propelled Articulating Boom Lift | NL-N-TS2-002-04-05-14 | 11867364 | 0 | 11867364 | 11867364 | 0 | 0 | 0 | 0 | 0 | 0 | 11867364 | 0 | 11867364 | 11867364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11867364 | 0 | 11867364 | 11867364 | 0
240 | * | 245KV SPRING OPERATEDSF6 CIRCUIT BREAKER | NL-N-TS2-002-04-05-15 | 1659478.89 | 1659478.89 | 0 | 1659478.89 | 0 | 1659478.89 | 1659478.89 | 0 | 1659478.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659478.89 | 1659478.89 | 0 | 1659478.89 | 0
241 | * | Retrofit of 245KV Isolators | NL-N-TS2-002-04-05-16 | 8254704 | 0 | 8254704 | 8254704 | 0 | 0 | 0 | 0 | 0 | 0 | 8254704 | 0 | 8254704 | 8254704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8254704 | 0 | 8254704 | 8254704 | 0
242 | * | 245KV SF6 Gas Current Transformer | NL-N-TS2-002-04-05-17 | 8989240 | 0 | 8989240 | 8989240 | 0 | 0 | 0 | 0 | 0 | 0 | 8989240 | 0 | 8989240 | 8989240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8989240 | 0 | 8989240 | 8989240 | 0
243 | * | 400KV Capacitance Voltage Transformer | NL-N-TS2-002-04-05-18 | 2458379.79 | 2458379.79 | 0 | 2458379.79 | 0 | 2458379.79 | 2458379.79 | 0 | 2458379.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2458379.79 | 2458379.79 | 0 | 2458379.79 | 0
244 | * | Replacement of faulty cables in SWYD | NL-N-TS2-002-04-05-19 | 634910 | 618910 | 16000 | 634910 | 0 | 618910 | 618910 | 0 | 618910 | 0 | 16000 | 0 | 16000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634910 | 618910 | 16000 | 634910 | 0
245 | * | Dead end & Suspension Clamp for HTLS | NL-N-TS2-002-04-05-20 | 687595.24 | 687595.24 | 0 | 687595.24 | 0 | 687595.24 | 687595.24 | 0 | 687595.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687595.24 | 687595.24 | 0 | 687595.24 | 0
246 | * | Extension of ABT EMS large screen to UCB | NL-N-TS2-002-04-05-21 | 1592946.6 | 1592946.6 | 0 | 1592946.6 | 0 | 1592946.6 | 1592946.6 | 0 | 1592946.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1592946.6 | 1592946.6 | 0 | 1592946.6 | 0
247 | * | 400kV SF6 gas Current Transformers | NL-N-TS2-002-04-05-23 | 3781897.12 | 3781897.12 | 0 | 3781897.12 | 0 | 3781897.12 | 3781897.12 | 0 | 3781897.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3781897.12 | 3781897.12 | 0 | 3781897.12 | 0
248 | * | Retrofitting of 400KV Bus Bar Protection | NL-N-TS2-002-04-05-24 | 21776116.6 | 21776116.6 | 0 | 21776116.6 | 0 | 21776116.6 | 21776116.6 | 0 | 21776116.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21776116.6 | 21776116.6 | 0 | 21776116.6 | 0
249 | * | Replacement of 420 KV CT | NL-N-TS2-002-04-05-25 | 191160 | 191160 | 0 | 191160 | 0 | 191160 | 191160 | 0 | 191160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191160 | 191160 | 0 | 191160 | 0
250 | * | 400KV Spring OperatedSF6 Circuit Breaker | NL-N-TS2-002-04-05-26 | 19846903.4 | 19846903.4 | 0 | 19846903.4 | 0 | 19846903.4 | 19846903.4 | 0 | 19846903.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19846903.4 | 19846903.4 | 0 | 19846903.4 | 0
251 | * | ABT Based Energy Meters | NL-N-TS2-002-04-05-27 | 10469303.28 | 8724273.78 | 1745029.5 | 10469303.28 | 0 | 8724273.78 | 8724273.78 | 0 | 8724273.78 | 0 | 1745029.5 | 0 | 1745029.5 | 1745029.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10469303.28 | 8724273.78 | 1745029.5 | 10469303.28 | 0
252 | * | 11KV 120KN Anti FOg insulator | NL-N-TS2-002-04-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | * | Retrofit of ABT EMS Server System | NL-N-TS2-002-04-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | * | ST work for Repl of 400KV CB and SF6 gas | NL-N-TS2-002-04-05-31 | 818520.03 | 547520 | 271000.03 | 818520.03 | 0 | 547520 | 547520 | 0 | 547520 | 0 | 271000.03 | 0 | 271000.03 | 271000.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 818520.03 | 547520 | 271000.03 | 818520.03 | 0
255 | * | Reconductoring Existing ACSR with HTLS | NL-N-TS2-002-04-05-32 | 2147600.03 | 1342250 | 805350.03 | 2147600.03 | 0 | 1342250 | 1342250 | 0 | 1342250 | 0 | 805350.03 | 0 | 805350.03 | 805350.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2147600.03 | 1342250 | 805350.03 | 2147600.03 | 0
256 | * | Supply & Servicing of Opera Boxes 245 KV | NL-N-TS2-002-04-05-33 | 9446573.21 | 8003754.74 | 1442818.47 | 9446573.21 | 0 | 8003754.74 | 8003754.74 | 0 | 8003754.74 | 0 | 1442818.47 | 0 | 1442818.47 | 1442818.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9446573.21 | 8003754.74 | 1442818.47 | 9446573.21 | 0
257 | * | Supply and installation of Earth pits | NL-N-TS2-002-04-05-34 | 9956000 | 0 | 9956000 | 9956000 | 0 | 0 | 0 | 0 | 0 | 0 | 9956000 | 0 | 9956000 | 9956000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9956000 | 0 | 9956000 | 9956000 | 0
258 | * | Comm of 230 kv 1200 Sqmm XLPE copper cab | NL-N-TS2-002-04-05-35 | 82604759 | 0 | 82604759 | 82604759 | 0 | 0 | 0 | 0 | 0 | 0 | 82604759 | 0 | 82604759 | 82604759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82604759 | 0 | 82604759 | 82604759 | 0
259 | * | PUR OF 360KV 20KA LIGHTINING ARRESTOR | NL-N-TS2-002-04-05-36 | 3805856 | 0 | 3805856 | 3805856 | 0 | 0 | 0 | 0 | 0 | 0 | 3805856 | 0 | 3805856 | 3805856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3805856 | 0 | 3805856 | 3805856 | 0
260 | * | Purchase of 230 KV SF6 Current Transform | NL-N-TS2-002-04-05-37 | 13246680 | 0 | 13246680.02 | 13246680.02 | -0.02 | 0 | 0 | 0 | 0 | 0 | 13246680 | 0 | 13246680.02 | 13246680.02 | -0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13246680 | 0 | 13246680.02 | 13246680.02 | -0.02
261 | * | purchase of cables for emergency & retro | NL-N-TS2-002-04-05-38 | 1561530 | 0 | 0 | 0 | 1561530 | 0 | 0 | 0 | 0 | 0 | 1561530 | 0 | 0 | 0 | 1561530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1561530 | 0 | 0 | 0 | 1561530
262 | ** | MRT | NL-N-TS2-002-04-06 | 19665637.94 | 1148068.01 | 18481922.65 | 19629990.66 | 35647.28 | 1148068.01 | 1148068.01 | 0 | 1148068.01 | 0 | 18517569.93 | 0 | 18481922.65 | 18481922.65 | 35647.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19665637.94 | 1148068.01 | 18481922.65 | 19629990.66 | 35647.28
263 | * | Multi Testing Kit-Transformer,SWYD&UCB | NL-N-TS2-002-04-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | * | Numerical Motor Protec Relay & Display | NL-N-TS2-002-04-06-02 | 1088627.88 | 0 | 1088627.88 | 1088627.88 | 0 | 0 | 0 | 0 | 0 | 0 | 1088627.88 | 0 | 1088627.88 | 1088627.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088627.88 | 0 | 1088627.88 | 1088627.88 | 0
265 | * | Insulation Resistance Tester-Megger | NL-N-TS2-002-04-06-03 | 1148068.01 | 1148068.01 | 0 | 1148068.01 | 0 | 1148068.01 | 1148068.01 | 0 | 1148068.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148068.01 | 1148068.01 | 0 | 1148068.01 | 0
266 | * | Procurement of Breaker Contact Multiplie | NL-N-TS2-002-04-06-04 | 106500.03 | 0 | 106500.03 | 106500.03 | 0 | 0 | 0 | 0 | 0 | 0 | 106500.03 | 0 | 106500.03 | 106500.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106500.03 | 0 | 106500.03 | 106500.03 | 0
267 | * | DELTA 4110 Megger make Tan Delta test | NL-N-TS2-002-04-06-05 | 5895516 | 0 | 5859868.72 | 5859868.72 | 35647.28 | 0 | 0 | 0 | 0 | 0 | 5895516 | 0 | 5859868.72 | 5859868.72 | 35647.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5895516 | 0 | 5859868.72 | 5859868.72 | 35647.28
268 | * | Over current/Neutral Voltage Relay | NL-N-TS2-002-04-06-06 | 785560.02 | 0 | 785560.02 | 785560.02 | 0 | 0 | 0 | 0 | 0 | 0 | 785560.02 | 0 | 785560.02 | 785560.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785560.02 | 0 | 785560.02 | 785560.02 | 0
269 | * | Procurement of new ICT protection System | NL-N-TS2-002-04-06-07 | 8283726 | 0 | 8283726 | 8283726 | 0 | 0 | 0 | 0 | 0 | 0 | 8283726 | 0 | 8283726 | 8283726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8283726 | 0 | 8283726 | 8283726 | 0
270 | * | purchase of 3 phase Combined Relay | NL-N-TS2-002-04-06-08 | 2357640 | 0 | 2357640 | 2357640 | 0 | 0 | 0 | 0 | 0 | 0 | 2357640 | 0 | 2357640 | 2357640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2357640 | 0 | 2357640 | 2357640 | 0
271 | ** | ELECTRICAL MAINTENANCE -I-CONTINUATION | NL-N-TS2-002-04-07 | 655509858.78 | 75936878.34 | 529898652.72 | 605835531.06 | 49674327.72 | 50988118.92 | 50988118.92 | 0 | 50988118.92 | 0 | 604521739.86 | 24948759.42 | 529898652.72 | 554847412.14 | 49674327.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655509858.78 | 75936878.34 | 529898652.72 | 605835531.06 | 49674327.72
272 | * | DSES-Field discharge resistor for STG-I | NL-N-TS2-002-04-07-01 | 1852052.04 | 1852052.04 | 0 | 1852052.04 | 0 | 1852052.04 | 1852052.04 | 0 | 1852052.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1852052.04 | 1852052.04 | 0 | 1852052.04 | 0
273 | * | BHEL HVR T/F ESP STG-2 | NL-N-TS2-002-04-07-02 | 18069345.84 | 0 | 18069345.84 | 18069345.84 | 0 | 0 | 0 | 0 | 0 | 0 | 18069345.84 | 0 | 18069345.84 | 18069345.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18069345.84 | 0 | 18069345.84 | 18069345.84 | 0
274 | * | Upgradation of DSES STG1 | NL-N-TS2-002-04-07-03 | 46656770.01 | 0 | 180000 | 180000 | 46476770.01 | 0 | 0 | 0 | 0 | 0 | 46656770.01 | 0 | 180000 | 180000 | 46476770.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46656770.01 | 0 | 180000 | 180000 | 46476770.01
275 | * | Monorail of stage 1 Millmotor | NL-N-TS2-002-04-07-04 | 950000.01 | 0 | 950000.01 | 950000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 950000.01 | 0 | 950000.01 | 950000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000.01 | 0 | 950000.01 | 950000.01 | 0
276 | * | Purchase of Motorola Walkie Talkie Set | NL-N-TS2-002-04-07-05 | 2349380 | 0 | 2349380 | 2349380 | 0 | 0 | 0 | 0 | 0 | 0 | 2349380 | 0 | 2349380 | 2349380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349380 | 0 | 2349380 | 2349380 | 0
277 | * | Tranformer oil BDV test Kit | NL-N-TS2-002-04-07-06 | 997510.01 | 997510.01 | 0 | 997510.01 | 0 | 997510.01 | 997510.01 | 0 | 997510.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997510.01 | 997510.01 | 0 | 997510.01 | 0
278 | * | SES and VFD | NL-N-TS2-002-04-07-07 | 27373050 | 0 | 27373050 | 27373050 | 0 | 0 | 0 | 0 | 0 | 0 | 27373050 | 0 | 27373050 | 27373050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27373050 | 0 | 27373050 | 27373050 | 0
279 | * | Rectifier Spares of Hydrogen plant | NL-N-TS2-002-04-07-08 | 255262 | 0 | 255262 | 255262 | 0 | 0 | 0 | 0 | 0 | 0 | 255262 | 0 | 255262 | 255262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255262 | 0 | 255262 | 255262 | 0
280 | * | ST contract work for repair 6,6 KV motor | NL-N-TS2-002-04-07-09 | 8150000.01 | 0 | 6360200.03 | 6360200.03 | 1789799.98 | 0 | 0 | 0 | 0 | 0 | 8150000.01 | 0 | 6360200.03 | 6360200.03 | 1789799.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8150000.01 | 0 | 6360200.03 | 6360200.03 | 1789799.98
281 | * | Pur of self propelled Atricul boom lift | NL-N-TS2-002-04-07-10 | 6276455.4 | 0 | 6276455.4 | 6276455.4 | 0 | 0 | 0 | 0 | 0 | 0 | 6276455.4 | 0 | 6276455.4 | 6276455.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6276455.4 | 0 | 6276455.4 | 6276455.4 | 0
282 | * | ST work for Overhauling of 6.6 kv motors | NL-N-TS2-002-04-07-11 | 2399322.3 | 0 | 2399322.3 | 2399322.3 | 0 | 0 | 0 | 0 | 0 | 0 | 2399322.3 | 0 | 2399322.3 | 2399322.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399322.3 | 0 | 2399322.3 | 2399322.3 | 0
283 | * | Purchase of Thermal Imaging Camera | NL-N-TS2-002-04-07-12 | 834963.41 | 834963.41 | 0 | 834963.41 | 0 | 0 | 0 | 0 | 0 | 0 | 834963.41 | 834963.41 | 0 | 834963.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834963.41 | 834963.41 | 0 | 834963.41 | 0
284 | * | Retrofitting of stage-I mill motor hoist | NL-N-TS2-002-04-07-13 | 6985743.9 | 0 | 6985743.9 | 6985743.9 | 0 | 0 | 0 | 0 | 0 | 0 | 6985743.9 | 0 | 6985743.9 | 6985743.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6985743.9 | 0 | 6985743.9 | 6985743.9 | 0
285 | * | HT Motor and cable maintenance | NL-N-TS2-002-04-07-14 | 5470800.01 | 0 | 5470800.01 | 5470800.01 | 0 | 0 | 0 | 0 | 0 | 0 | 5470800.01 | 0 | 5470800.01 | 5470800.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5470800.01 | 0 | 5470800.01 | 5470800.01 | 0
286 | * | 11000V grade 1C X630 Sq mm Al cable | NL-N-TS2-002-04-07-15 | 10349955 | 0 | 10349955 | 10349955 | 0 | 0 | 0 | 0 | 0 | 0 | 10349955 | 0 | 10349955 | 10349955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10349955 | 0 | 10349955 | 10349955 | 0
287 | * | Megger make Micro ohm meter | NL-N-TS2-002-04-07-16 | 1382257.14 | 1382257.14 | 0 | 1382257.14 | 0 | 0 | 0 | 0 | 0 | 0 | 1382257.14 | 1382257.14 | 0 | 1382257.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1382257.14 | 1382257.14 | 0 | 1382257.14 | 0
288 | * | Online partial discharge scanner | NL-N-TS2-002-04-07-17 | 1887858 | 0 | 1887858 | 1887858 | 0 | 0 | 0 | 0 | 0 | 0 | 1887858 | 0 | 1887858 | 1887858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887858 | 0 | 1887858 | 1887858 | 0
289 | * | Retrofitting of 6.6 KV 1250 A MOCB's | NL-N-TS2-002-04-07-18 | 24458246.68 | 20386167.54 | 4072079.14 | 24458246.68 | 0 | 268316.87 | 268316.87 | 0 | 268316.87 | 0 | 24189929.81 | 20117850.67 | 4072079.14 | 24189929.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24458246.68 | 20386167.54 | 4072079.14 | 24458246.68 | 0
290 | * | CEP Motor for St-I 6600Volts 515 KW | NL-N-TS2-002-04-07-19 | 5623571 | 0 | 5623571 | 5623571 | 0 | 0 | 0 | 0 | 0 | 0 | 5623571 | 0 | 5623571 | 5623571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5623571 | 0 | 5623571 | 5623571 | 0
291 | * | CAC Motor for DRY ash 6600 Volts 250 KW | NL-N-TS2-002-04-07-20 | 12551070 | 0 | 12551070 | 12551070 | 0 | 0 | 0 | 0 | 0 | 0 | 12551070 | 0 | 12551070 | 12551070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12551070 | 0 | 12551070 | 12551070 | 0
292 | * | Condition assesment of HT cable & HT mot | NL-N-TS2-002-04-07-21 | 1386240.03 | 963635.2 | 422604.83 | 1386240.03 | 0 | 1024240 | 1024240 | 0 | 1024240 | 0 | 362000.03 | -60604.8 | 422604.83 | 362000.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1386240.03 | 963635.2 | 422604.83 | 1386240.03 | 0
293 | * | AC drive for 3 phase induction motor | NL-N-TS2-002-04-07-22 | 16916268 | 0 | 16916268 | 16916268 | 0 | 0 | 0 | 0 | 0 | 0 | 16916268 | 0 | 16916268 | 16916268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16916268 | 0 | 16916268 | 16916268 | 0
294 | * | Single Core XLPE cable X1000 Sq mm | NL-N-TS2-002-04-07-23 | 22554870 | 0 | 22554870 | 22554870 | 0 | 0 | 0 | 0 | 0 | 0 | 22554870 | 0 | 22554870 | 22554870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22554870 | 0 | 22554870 | 22554870 | 0
295 | * | Rectifi,OH and Testing of Generator- U-I | NL-N-TS2-002-04-07-25 | 50236990 | 49520293 | 700000.05 | 50220293.05 | 16696.95 | 46846000 | 46846000 | 0 | 46846000 | 0 | 3390990 | 2674293 | 700000.05 | 3374293.05 | 16696.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50236990 | 49520293 | 700000.05 | 50220293.05 | 16696.95
296 | * | Servicing of Siemens make 11 KV Ring | NL-N-TS2-002-04-07-26 | 1222081 | 0 | 1222081 | 1222081 | 0 | 0 | 0 | 0 | 0 | 0 | 1222081 | 0 | 1222081 | 1222081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1222081 | 0 | 1222081 | 1222081 | 0
297 | * | Supply insta &comm of hydrogen gas leak | NL-N-TS2-002-04-07-27 | 2051035.98 | 0 | 2051035.98 | 2051035.98 | 0 | 0 | 0 | 0 | 0 | 0 | 2051035.98 | 0 | 2051035.98 | 2051035.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2051035.98 | 0 | 2051035.98 | 2051035.98 | 0
298 | * | Procure and commissioning of 01 no ICT | NL-N-TS2-002-04-07-28 | 286747270 | 0 | 286747270 | 286747270 | 0 | 0 | 0 | 0 | 0 | 0 | 286747270 | 0 | 286747270 | 286747270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286747270 | 0 | 286747270 | 286747270 | 0
299 | * | Refurb & rewinding of St-2 UAT LTE basis | NL-N-TS2-002-04-07-29 | 14856000.01 | 0 | 14856000.01 | 14856000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 14856000.01 | 0 | 14856000.01 | 14856000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14856000.01 | 0 | 14856000.01 | 14856000.01 | 0
300 | * | Purchase of 3 cX240 Sq mm 6.35 KV/11 KV | NL-N-TS2-002-04-07-30 | 12180000 | 0 | 12180000 | 12180000 | 0 | 0 | 0 | 0 | 0 | 0 | 12180000 | 0 | 12180000 | 12180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12180000 | 0 | 12180000 | 12180000 | 0
301 | * | Purchase of Circuit Breaker T I Meter | NL-N-TS2-002-04-07-31 | 160015 | 0 | 160015 | 160015 | 0 | 0 | 0 | 0 | 0 | 0 | 160015 | 0 | 160015 | 160015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160015 | 0 | 160015 | 160015 | 0
302 | * | Retrofitting and Upgradation of DSES | NL-N-TS2-002-04-07-32 | 44132000 | 0 | 44132000 | 44132000 | 0 | 0 | 0 | 0 | 0 | 0 | 44132000 | 0 | 44132000 | 44132000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44132000 | 0 | 44132000 | 44132000 | 0
303 | * | DCS 800 Converter unit for stage-I | NL-N-TS2-002-04-07-33 | 1970600 | 0 | 1970600 | 1970600 | 0 | 0 | 0 | 0 | 0 | 0 | 1970600 | 0 | 1970600 | 1970600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1970600 | 0 | 1970600 | 1970600 | 0
304 | * | Repair and Rectification of Mill Motors | NL-N-TS2-002-04-07-34 | 6242000 | 0 | 5290000.1 | 5290000.1 | 951999.9 | 0 | 0 | 0 | 0 | 0 | 6242000 | 0 | 5290000.1 | 5290000.1 | 951999.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6242000 | 0 | 5290000.1 | 5290000.1 | 951999.9
305 | * | RETROFITTING OF VCs FOR LHS HT CONVEYORS | NL-N-TS2-002-04-07-35 | 4001616 | 0 | 4001616 | 4001616 | 0 | 0 | 0 | 0 | 0 | 0 | 4001616 | 0 | 4001616 | 4001616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4001616 | 0 | 4001616 | 4001616 | 0
306 | * | 6 NOS OF MOTORIZED HOIST WITH MANUAL MOV | NL-N-TS2-002-04-07-36 | 5549260 | 0 | 5540199.12 | 5540199.12 | 9060.88 | 0 | 0 | 0 | 0 | 0 | 5549260 | 0 | 5540199.12 | 5540199.12 | 9060.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5549260 | 0 | 5540199.12 | 5540199.12 | 9060.88
307 | * | REPAIR-RECTIFICATION-6.6KV 420KW CONVEYO | NL-N-TS2-002-04-07-37 | 430000 | 0 | 0 | 0 | 430000 | 0 | 0 | 0 | 0 | 0 | 430000 | 0 | 0 | 0 | 430000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430000 | 0 | 0 | 0 | 430000
308 | *** | BOILER MAINTENANCE | NL-N-TS2-002-05 | 828726175.01 | 236474322.81 | 585818204.6 | 822303248.4 | 6422926.61 | 223232578.12 | 221496079.69 | 0 | 221506800.68 | 1725777.44 | 605493596.89 | 14978243.12 | 585818204.6 | 600796447.72 | 4697149.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 828726175.01 | 236474322.81 | 585818204.6 | 822303248.4 | 6422926.61
309 | ** | SLAG CONVEYOR,ABG & FEEDER | NL-N-TS2-002-05-01 | 149613116.8 | 78060407.65 | 71537188.86 | 149597596.51 | 15520.29 | 73804866.88 | 73804866.88 | 0 | 73804866.88 | 0 | 75808249.92 | 4255540.77 | 71537188.86 | 75792729.63 | 15520.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149613116.8 | 78060407.65 | 71537188.86 | 149597596.51 | 15520.29
310 | * | SLAG CONVEYOR CHAIN,PIV CHAIN AND ABG | NL-N-TS2-002-05-01-01 | 17118894.93 | 10762694.93 | 6356200 | 17118894.93 | 0 | 10762694.93 | 10762694.93 | 0 | 10762694.93 | 0 | 6356200 | 0 | 6356200 | 6356200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17118894.93 | 10762694.93 | 6356200 | 17118894.93 | 0
311 | * | Replace Str & Chequered plates-Boilers | NL-N-TS2-002-05-01-02 | 3132330 | 3132330 | 0 | 3132330 | 0 | 3132330 | 3132330 | 0 | 3132330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3132330 | 3132330 | 0 | 3132330 | 0
312 | * | Procurement of PB Elements Part - I | NL-N-TS2-002-05-01-03 | 2436741.11 | 2436741.11 | 0 | 2436741.11 | 0 | 2436741.11 | 2436741.11 | 0 | 2436741.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2436741.11 | 2436741.11 | 0 | 2436741.11 | 0
313 | * | Rectification of Unit-5 Boiler Girder | NL-N-TS2-002-05-01-04 | 4598035.2 | 4598035.2 | 0 | 4598035.2 | 0 | 4598035.2 | 4598035.2 | 0 | 4598035.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4598035.2 | 4598035.2 | 0 | 4598035.2 | 0
314 | * | Replacement of liner plates in B Bunker | NL-N-TS2-002-05-01-05 | 2419000 | 0 | 2419000 | 2419000 | 0 | 0 | 0 | 0 | 0 | 0 | 2419000 | 0 | 2419000 | 2419000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2419000 | 0 | 2419000 | 2419000 | 0
315 | * | procurement of ABG link chain | NL-N-TS2-002-05-01-06 | 1995944.86 | 0 | 1995944.86 | 1995944.86 | 0 | 0 | 0 | 0 | 0 | 0 | 1995944.86 | 0 | 1995944.86 | 1995944.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995944.86 | 0 | 1995944.86 | 1995944.86 | 0
316 | * | link chain size 22*86 having 59links SC | NL-N-TS2-002-05-01-07 | 33254760 | 33254760 | 0 | 33254760 | 0 | 33254760 | 33254760 | 0 | 33254760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33254760 | 33254760 | 0 | 33254760 | 0
317 | * | Round link Chain-14X64 For SPBF | NL-N-TS2-002-05-01-08 | 993504.14 | 993504.14 | 0 | 993504.14 | 0 | 993504.14 | 993504.14 | 0 | 993504.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 993504.14 | 993504.14 | 0 | 993504.14 | 0
318 | * | Side/Intermediate Grate bar supp for ABG | NL-N-TS2-002-05-01-09 | 4160393.6 | 4160393.6 | 0 | 4160393.6 | 0 | 4160393.6 | 4160393.6 | 0 | 4160393.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4160393.6 | 4160393.6 | 0 | 4160393.6 | 0
319 | * | Roller for ABG 355mm long as per drawing | NL-N-TS2-002-05-01-10 | 1509025.32 | 1509025.32 | 0 | 1509025.32 | 0 | 1509025.32 | 1509025.32 | 0 | 1509025.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509025.32 | 1509025.32 | 0 | 1509025.32 | 0
320 | * | Connecting pin for ABG Supports | NL-N-TS2-002-05-01-11 | 411500.01 | 411500.01 | 0 | 411500.01 | 0 | 411500.01 | 411500.01 | 0 | 411500.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 411500.01 | 411500.01 | 0 | 411500.01 | 0
321 | * | Louver Type Grate Bar Having Length397mm | NL-N-TS2-002-05-01-12 | 6761525.1 | 1690754.66 | 5070770.44 | 6761525.1 | 0 | 1690754.66 | 1690754.66 | 0 | 1690754.66 | 0 | 5070770.44 | 0 | 5070770.44 | 5070770.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6761525.1 | 1690754.66 | 5070770.44 | 6761525.1 | 0
322 | * | ABG CAP BEARING A180 | NL-N-TS2-002-05-01-13 | 929790.96 | 929790.96 | 0 | 929790.96 | 0 | 929790.96 | 929790.96 | 0 | 929790.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929790.96 | 929790.96 | 0 | 929790.96 | 0
323 | * | ABG plate link chain complete set | NL-N-TS2-002-05-01-14 | 3051478.28 | 3051478.28 | 0 | 3051478.28 | 0 | 3051478.28 | 3051478.28 | 0 | 3051478.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3051478.28 | 3051478.28 | 0 | 3051478.28 | 0
324 | * | Repl & Recti of Supporting Struct & Cheq | NL-N-TS2-002-05-01-15 | 5908590 | 3727802.83 | 2180781.14 | 5908583.97 | 6.03 | 3239720.49 | 3239720.49 | 0 | 3239720.49 | 0 | 2668869.51 | 488082.34 | 2180781.14 | 2668863.48 | 6.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5908590 | 3727802.83 | 2180781.14 | 5908583.97 | 6.03
325 | * | Belt Conveyor Idler 108X300,108X310 | NL-N-TS2-002-05-01-16 | 1710969.63 | 428599.22 | 1282370.41 | 1710969.63 | 0 | 428599.22 | 428599.22 | 0 | 428599.22 | 0 | 1282370.41 | 0 | 1282370.41 | 1282370.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1710969.63 | 428599.22 | 1282370.41 | 1710969.63 | 0
326 | * | Replacement of damaged Chequred plate | NL-N-TS2-002-05-01-17 | 123408.32 | 123408.32 | 0 | 123408.32 | 0 | 123408.32 | 123408.32 | 0 | 123408.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123408.32 | 123408.32 | 0 | 123408.32 | 0
327 | * | ABG Drive Shaft Chain Wheel | NL-N-TS2-002-05-01-18 | 1230545.54 | 1230545.53 | 0 | 1230545.53 | 0.01 | 123087.12 | 123087.12 | 0 | 123087.12 | 0 | 1107458.42 | 1107458.41 | 0 | 1107458.41 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230545.54 | 1230545.53 | 0 | 1230545.53 | 0.01
328 | * | Complete set of Spacer Bar and Tube Asse | NL-N-TS2-002-05-01-19 | 1064049.66 | 1064049.66 | 0 | 1064049.66 | 0 | 1064049.66 | 1064049.66 | 0 | 1064049.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1064049.66 | 1064049.66 | 0 | 1064049.66 | 0
329 | * | ST contract 5 nos ABG overhaul in TPS-II | NL-N-TS2-002-05-01-20 | 5377765.3 | 1894993.86 | 3482771.44 | 5377765.3 | 0 | 1894993.86 | 1894993.86 | 0 | 1894993.86 | 0 | 3482771.44 | 0 | 3482771.44 | 3482771.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5377765.3 | 1894993.86 | 3482771.44 | 5377765.3 | 0
330 | * | RUD Chain coupling connector size 22X86 | NL-N-TS2-002-05-01-21 | 2660000.02 | 2660000.02 | 0 | 2660000.02 | 0 | 0 | 0 | 0 | 0 | 0 | 2660000.02 | 2660000.02 | 0 | 2660000.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2660000.02 | 2660000.02 | 0 | 2660000.02 | 0
331 | * | ST work for fabrication,erection in ABG | NL-N-TS2-002-05-01-22 | 4137010 | 0 | 4137010 | 4137010 | 0 | 0 | 0 | 0 | 0 | 0 | 4137010 | 0 | 4137010 | 4137010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4137010 | 0 | 4137010 | 4137010 | 0
332 | * | Louvre Type Grate bar Having Length 347 | NL-N-TS2-002-05-01-23 | 19608696 | 0 | 19608696 | 19608696 | 0 | 0 | 0 | 0 | 0 | 0 | 19608696 | 0 | 19608696 | 19608696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19608696 | 0 | 19608696 | 19608696 | 0
333 | * | Changing /Rectifi of Damaged Chequ plate | NL-N-TS2-002-05-01-24 | 5130529.52 | 0 | 5130529.52 | 5130529.52 | 0 | 0 | 0 | 0 | 0 | 0 | 5130529.52 | 0 | 5130529.52 | 5130529.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5130529.52 | 0 | 5130529.52 | 5130529.52 | 0
334 | * | Side/Intermediate Grate bar support | NL-N-TS2-002-05-01-25 | 7396127.86 | 0 | 7396127.86 | 7396127.86 | 0 | 0 | 0 | 0 | 0 | 0 | 7396127.86 | 0 | 7396127.86 | 7396127.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7396127.86 | 0 | 7396127.86 | 7396127.86 | 0
335 | * | ABG Plate Link Chain | NL-N-TS2-002-05-01-26 | 4438657.44 | 0 | 4438657.44 | 4438657.44 | 0 | 0 | 0 | 0 | 0 | 0 | 4438657.44 | 0 | 4438657.44 | 4438657.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4438657.44 | 0 | 4438657.44 | 4438657.44 | 0
336 | * | ABG- COMPLETE SET OF SPACER BAR AND TUBE | NL-N-TS2-002-05-01-27 | 3138049 | 0 | 3132004 | 3132004 | 6045 | 0 | 0 | 0 | 0 | 0 | 3138049 | 0 | 3132004 | 3132004 | 6045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3138049 | 0 | 3132004 | 3132004 | 6045
337 | * | ABG-ROLLER-305MM | NL-N-TS2-002-05-01-28 | 1200979 | 0 | 1198665.75 | 1198665.75 | 2313.25 | 0 | 0 | 0 | 0 | 0 | 1200979 | 0 | 1198665.75 | 1198665.75 | 2313.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200979 | 0 | 1198665.75 | 1198665.75 | 2313.25
338 | * | ABG-ROLLER-355MM | NL-N-TS2-002-05-01-29 | 3714816 | 0 | 3707660 | 3707660 | 7156 | 0 | 0 | 0 | 0 | 0 | 3714816 | 0 | 3707660 | 3707660 | 7156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3714816 | 0 | 3707660 | 3707660 | 7156
339 | ** | MILL MAINTENANCE | NL-N-TS2-002-05-02 | 90882669.26 | 43706306.12 | 45766035.15 | 89472341.27 | 1410327.99 | 43405718.58 | 43705847.1 | 0 | 43705847.1 | -300128.52 | 47476950.68 | 459.02 | 45766035.15 | 45766494.17 | 1710456.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90882669.26 | 43706306.12 | 45766035.15 | 89472341.27 | 1410327.99
340 | * | MILLS AND PF DUCTS | NL-N-TS2-002-05-02-01 | 23126260.1 | 20507859.74 | 2618400.36 | 23126260.1 | 0 | 20507859.74 | 20507859.74 | 0 | 20507859.74 | 0 | 2618400.36 | 0 | 2618400.36 | 2618400.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23126260.1 | 20507859.74 | 2618400.36 | 23126260.1 | 0
341 | * | Helical Spring &Visco DamperUnit | NL-N-TS2-002-05-02-02 | 8138236.21 | 8138236.21 | 0 | 8138236.21 | 0 | 8138236.21 | 8138236.21 | 0 | 8138236.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8138236.21 | 8138236.21 | 0 | 8138236.21 | 0
342 | * | Mill double bearing bed frame | NL-N-TS2-002-05-02-03 | 890100 | 890100 | 0 | 890100 | 0 | 890100 | 890100 | 0 | 890100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890100 | 890100 | 0 | 890100 | 0
343 | * | PF Duct lifting & Aligning work sup Ibm | NL-N-TS2-002-05-02-04 | 2320200.03 | 1486800 | 833400.03 | 2320200.03 | 0 | 1486800 | 1486800 | 0 | 1486800 | 0 | 833400.03 | 0 | 833400.03 | 833400.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2320200.03 | 1486800 | 833400.03 | 2320200.03 | 0
344 | * | replace of spring units & visco dampers | NL-N-TS2-002-05-02-05 | 2534640.02 | 2534640 | 0.02 | 2534640.02 | 0 | 2534640 | 2534640 | 0 | 2534640 | 0 | 0.02 | 0 | 0.02 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2534640.02 | 2534640 | 0.02 | 2534640.02 | 0
345 | * | Replace recti classifier platform,Gratin | NL-N-TS2-002-05-02-06 | 4619667.15 | 1849483.44 | 2770183.71 | 4619667.15 | 0 | 1548895.9 | 1849024.42 | 0 | 1849024.42 | -300128.52 | 3070771.25 | 459.02 | 2770183.71 | 2770642.73 | 300128.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4619667.15 | 1849483.44 | 2770183.71 | 4619667.15 | 0
346 | * | Spring unit/visco damper | NL-N-TS2-002-05-02-07 | 8299186.73 | 8299186.73 | 0 | 8299186.73 | 0 | 8299186.73 | 8299186.73 | 0 | 8299186.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8299186.73 | 8299186.73 | 0 | 8299186.73 | 0
347 | * | Replace of Spring Visco dampers st-II | NL-N-TS2-002-05-02-08 | 2148000.01 | 0 | 2148000.01 | 2148000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 2148000.01 | 0 | 2148000.01 | 2148000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2148000.01 | 0 | 2148000.01 | 2148000.01 | 0
348 | * | Mill Door seal collar assemblyfor N110.6 | NL-N-TS2-002-05-02-09 | 11446000 | 0 | 11446000 | 11446000 | 0 | 0 | 0 | 0 | 0 | 0 | 11446000 | 0 | 11446000 | 11446000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11446000 | 0 | 11446000 | 11446000 | 0
349 | * | Voith Turbo/EPK Connecting Coupling | NL-N-TS2-002-05-02-10 | 9676524.01 | 0 | 9182685.01 | 9182685.01 | 493839 | 0 | 0 | 0 | 0 | 0 | 9676524.01 | 0 | 9182685.01 | 9182685.01 | 493839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9676524.01 | 0 | 9182685.01 | 9182685.01 | 493839
350 | * | MILL DOUBLE BEARING SHAFT | NL-N-TS2-002-05-02-11 | 11825145 | 0 | 11802366 | 11802366 | 22779 | 0 | 0 | 0 | 0 | 0 | 11825145 | 0 | 11802366 | 11802366 | 22779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11825145 | 0 | 11802366 | 11802366 | 22779
351 | * | REVAMPING-MILL DOOR SEAL COLLAR ASSEMBLY | NL-N-TS2-002-05-02-12 | 5858710 | 0 | 4965000.01 | 4965000.01 | 893709.99 | 0 | 0 | 0 | 0 | 0 | 5858710 | 0 | 4965000.01 | 4965000.01 | 893709.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5858710 | 0 | 4965000.01 | 4965000.01 | 893709.99
352 | ** | PRESSURE PARTS | NL-N-TS2-002-05-03 | 326779829.11 | 65381984.23 | 258411849.37 | 323793833.6 | 2985995.51 | 56269984.48 | 56255161.34 | 0 | 56255161.34 | 14823.14 | 270509844.63 | 9126822.89 | 258411849.37 | 267538672.26 | 2971172.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326779829.11 | 65381984.23 | 258411849.37 | 323793833.6 | 2985995.51
353 | * | SH3 Outlet Header (Stage-1) | NL-N-TS2-002-05-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | * | RH2 Outlet Header (Stage-1) | NL-N-TS2-002-05-03-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | * | RH1 Outlet Header (Stage-2) | NL-N-TS2-002-05-03-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | * | Drum Safety Valves (Stage-2) | NL-N-TS2-002-05-03-04 | 7916890.6 | 0 | 7916890.6 | 7916890.6 | 0 | 0 | 0 | 0 | 0 | 0 | 7916890.6 | 0 | 7916890.6 | 7916890.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7916890.6 | 0 | 7916890.6 | 7916890.6 | 0
357 | * | 10% SH Safety Valve (Stage-1) | NL-N-TS2-002-05-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | * | Temperature Control Valves (Stage-2) | NL-N-TS2-002-05-03-06 | 2257641 | 0 | 2257641 | 2257641 | 0 | 0 | 0 | 0 | 0 | 0 | 2257641 | 0 | 2257641 | 2257641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2257641 | 0 | 2257641 | 2257641 | 0
359 | * | Resln Fibroscope , digital ,data & rev | NL-N-TS2-002-05-03-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | * | Sky climber Assembly | NL-N-TS2-002-05-03-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | * | Water Lance Pump | NL-N-TS2-002-05-03-09 | 1813850.98 | 1813850.98 | 0 | 1813850.98 | 0 | 1813850.98 | 1813850.98 | 0 | 1813850.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813850.98 | 1813850.98 | 0 | 1813850.98 | 0
362 | * | Portable Motorised Scissor Platform | NL-N-TS2-002-05-03-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | * | Water Lance Assembly | NL-N-TS2-002-05-03-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | * | Automatic Stress Relieving Machine | NL-N-TS2-002-05-03-12 | 372880 | 372880 | 0 | 372880 | 0 | 372880 | 372880 | 0 | 372880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372880 | 372880 | 0 | 372880 | 0
365 | * | Portable Rebound Hardness tester | NL-N-TS2-002-05-03-13 | 198240 | 198240 | 0 | 198240 | 0 | 198240 | 198240 | 0 | 198240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198240 | 198240 | 0 | 198240 | 0
366 | * | Water Wall Tube & Panel Replacement U-4 | NL-N-TS2-002-05-03-14 | 595145.97 | 595145.97 | 0 | 595145.97 | 0 | 595145.97 | 595145.97 | 0 | 595145.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595145.97 | 595145.97 | 0 | 595145.97 | 0
367 | * | Boiler-5 Hanger Inspection&Rectification | NL-N-TS2-002-05-03-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | * | Water Wall Tube,Panel Replacement U-6&2 | NL-N-TS2-002-05-03-16 | 1651570.5 | 1651570.5 | 0 | 1651570.5 | 0 | 1651570.5 | 1651570.5 | 0 | 1651570.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1651570.5 | 1651570.5 | 0 | 1651570.5 | 0
369 | * | Replace of Drain,Vent,Impulse Line&Valve | NL-N-TS2-002-05-03-17 | 3788242.53 | 998841.12 | 2789401.41 | 3788242.53 | 0 | 1013664.26 | 998841.12 | 0 | 998841.12 | 14823.14 | 2774578.27 | 0 | 2789401.41 | 2789401.41 | -14823.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3788242.53 | 998841.12 | 2789401.41 | 3788242.53 | 0
370 | * | Replacement of WW Panels in Stage-1&2 | NL-N-TS2-002-05-03-18 | 2204377.3 | 2204377.3 | 0 | 2204377.3 | 0 | 2204377.3 | 2204377.3 | 0 | 2204377.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2204377.3 | 2204377.3 | 0 | 2204377.3 | 0
371 | * | HRH Safety Valve Tap-Off Line Bend Pipe | NL-N-TS2-002-05-03-19 | 1828205.99 | 1828205.99 | 0 | 1828205.99 | 0 | 1828205.99 | 1828205.99 | 0 | 1828205.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1828205.99 | 1828205.99 | 0 | 1828205.99 | 0
372 | * | Jack Inflatable | NL-N-TS2-002-05-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | * | Safety Valve Spares | NL-N-TS2-002-05-03-24 | 2088271.46 | 2088271.46 | 0 | 2088271.46 | 0 | 2088271.46 | 2088271.46 | 0 | 2088271.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2088271.46 | 2088271.46 | 0 | 2088271.46 | 0
374 | * | Thickness Survey -Boiler pressure Parts | NL-N-TS2-002-05-03-25 | 1258352.83 | 1258352.83 | 0 | 1258352.83 | 0 | 1258352.83 | 1258352.83 | 0 | 1258352.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258352.83 | 1258352.83 | 0 | 1258352.83 | 0
375 | * | Replacement of WW Panels/ST-1&2(2022-23) | NL-N-TS2-002-05-03-26 | 13658210 | 13658204.49 | 0 | 13658204.49 | 5.51 | 13393000.16 | 13393000.16 | 0 | 13393000.16 | 0 | 265209.84 | 265204.33 | 0 | 265204.33 | 5.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13658210 | 13658204.49 | 0 | 13658204.49 | 5.51
376 | * | Refractory Work inside RSD for 7 Boilers | NL-N-TS2-002-05-03-27 | 1387542.48 | 1387542.48 | 0 | 1387542.48 | 0 | 1387542.48 | 1387542.48 | 0 | 1387542.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1387542.48 | 1387542.48 | 0 | 1387542.48 | 0
377 | * | Procurement of fuel oil line pipes | NL-N-TS2-002-05-03-29 | 6590010.92 | 6584693.82 | 5317.1 | 6590010.92 | 0 | 6584693.82 | 6584693.82 | 0 | 6584693.82 | 0 | 5317.1 | 0 | 5317.1 | 5317.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6590010.92 | 6584693.82 | 5317.1 | 6590010.92 | 0
378 | * | Replacement of Insulation and Cladding | NL-N-TS2-002-05-03-30 | 74278330.83 | 9005229.57 | 65273101.26 | 74278330.83 | 0 | 9005229.57 | 9005229.57 | 0 | 9005229.57 | 0 | 65273101.26 | 0 | 65273101.26 | 65273101.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74278330.83 | 9005229.57 | 65273101.26 | 74278330.83 | 0
379 | * | Procurement of FCS MOVs for replacement | NL-N-TS2-002-05-03-31 | 2485080 | 2485080 | 0 | 2485080 | 0 | 2485080 | 2485080 | 0 | 2485080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2485080 | 2485080 | 0 | 2485080 | 0
380 | * | Hopper S type &Corner WW Panels for St-I | NL-N-TS2-002-05-03-32 | 7375592.01 | 7375592.01 | 0 | 7375592.01 | 0 | 0 | 0 | 0 | 0 | 0 | 7375592.01 | 7375592.01 | 0 | 7375592.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7375592.01 | 7375592.01 | 0 | 7375592.01 | 0
381 | * | Replacement of ECO outer bend St-I | NL-N-TS2-002-05-03-33 | 7523680.03 | 5168282 | 2355398.03 | 7523680.03 | 0 | 5168282 | 5168282 | 0 | 5168282 | 0 | 2355398.03 | 0 | 2355398.03 | 2355398.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7523680.03 | 5168282 | 2355398.03 | 7523680.03 | 0
382 | * | Water lance casing Top/bottom/Vertical | NL-N-TS2-002-05-03-34 | 546893.1 | 0 | 546893.1 | 546893.1 | 0 | 0 | 0 | 0 | 0 | 0 | 546893.1 | 0 | 546893.1 | 546893.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546893.1 | 0 | 546893.1 | 546893.1 | 0
383 | * | Procurement of FAS MOVs for stage I&II | NL-N-TS2-002-05-03-35 | 2450860 | 2450860 | 0 | 2450860 | 0 | 2450860 | 2450860 | 0 | 2450860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450860 | 2450860 | 0 | 2450860 | 0
384 | * | Replacement of HRH SV Tap off bend U-3 | NL-N-TS2-002-05-03-37 | 1568696.03 | 1105896 | 462800.03 | 1568696.03 | 0 | 1105896 | 1105896 | 0 | 1105896 | 0 | 462800.03 | 0 | 462800.03 | 462800.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568696.03 | 1105896 | 462800.03 | 1568696.03 | 0
385 | * | Replacement of HRH SV Tap off bend U-1 | NL-N-TS2-002-05-03-38 | 552948.03 | 552948 | 0.03 | 552948.03 | 0 | 552948 | 552948 | 0 | 552948 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552948.03 | 552948 | 0.03 | 552948.03 | 0
386 | * | Procurement of SSB Chains | NL-N-TS2-002-05-03-39 | 1893895.08 | 0 | 1893895.08 | 1893895.08 | 0 | 0 | 0 | 0 | 0 | 0 | 1893895.08 | 0 | 1893895.08 | 1893895.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1893895.08 | 0 | 1893895.08 | 1893895.08 | 0
387 | * | Procu of St-II SSB Puppet valve lever | NL-N-TS2-002-05-03-40 | 4773265.2 | 0 | 4773265.2 | 4773265.2 | 0 | 0 | 0 | 0 | 0 | 0 | 4773265.2 | 0 | 4773265.2 | 4773265.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4773265.2 | 0 | 4773265.2 | 4773265.2 | 0
388 | * | Procure of fuel oil line pipe fittings | NL-N-TS2-002-05-03-41 | 747223.4 | 0 | 747223.4 | 747223.4 | 0 | 0 | 0 | 0 | 0 | 0 | 747223.4 | 0 | 747223.4 | 747223.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747223.4 | 0 | 747223.4 | 747223.4 | 0
389 | * | Purchase of pipes and tubes for drains | NL-N-TS2-002-05-03-42 | 7511605 | 0 | 7511605 | 7511605 | 0 | 0 | 0 | 0 | 0 | 0 | 7511605 | 0 | 7511605 | 7511605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7511605 | 0 | 7511605 | 7511605 | 0
390 | * | Conducting Thickness survey and oxide | NL-N-TS2-002-05-03-43 | 1291038.01 | 318954.21 | 972083.8 | 1291038.01 | 0 | 318954.22 | 318954.22 | 0 | 318954.22 | 0 | 972083.79 | -0.01 | 972083.8 | 972083.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1291038.01 | 318954.21 | 972083.8 | 1291038.01 | 0
391 | * | Replacement of W/w Tubes and panels | NL-N-TS2-002-05-03-44 | 9976875.02 | 0 | 9976875.02 | 9976875.02 | 0 | 0 | 0 | 0 | 0 | 0 | 9976875.02 | 0 | 9976875.02 | 9976875.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9976875.02 | 0 | 9976875.02 | 9976875.02 | 0
392 | * | Procurement of water lancefunnel,Dogplat | NL-N-TS2-002-05-03-45 | 1486026.56 | 1486026.56 | 0 | 1486026.56 | 0 | 0 | 0 | 0 | 0 | 0 | 1486026.56 | 1486026.56 | 0 | 1486026.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1486026.56 | 1486026.56 | 0 | 1486026.56 | 0
393 | * | RLA Study in TPS-II Boiler of Unit-5 | NL-N-TS2-002-05-03-46 | 824937.8 | 792938.94 | 31998.86 | 824937.8 | 0 | 792938.94 | 792938.94 | 0 | 792938.94 | 0 | 31998.86 | 0 | 31998.86 | 31998.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824937.8 | 792938.94 | 31998.86 | 824937.8 | 0
394 | * | Replacement of Eco coil outer loop bend | NL-N-TS2-002-05-03-47 | 12415800.01 | 0 | 12415800.01 | 12415800.01 | 0 | 0 | 0 | 0 | 0 | 0 | 12415800.01 | 0 | 12415800.01 | 12415800.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12415800.01 | 0 | 12415800.01 | 12415800.01 | 0
395 | * | Replacement of Boiler drain,Vent& Impuls | NL-N-TS2-002-05-03-48 | 8744700.01 | 0 | 8744700.01 | 8744700.01 | 0 | 0 | 0 | 0 | 0 | 0 | 8744700.01 | 0 | 8744700.01 | 8744700.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8744700.01 | 0 | 8744700.01 | 8744700.01 | 0
396 | * | Procurement of economiser Outer Bend | NL-N-TS2-002-05-03-49 | 8913720 | 0 | 8913720 | 8913720 | 0 | 0 | 0 | 0 | 0 | 0 | 8913720 | 0 | 8913720 | 8913720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8913720 | 0 | 8913720 | 8913720 | 0
397 | * | Procurement of economiser long Bends | NL-N-TS2-002-05-03-50 | 9196776.96 | 0 | 9196776.96 | 9196776.96 | 0 | 0 | 0 | 0 | 0 | 0 | 9196776.96 | 0 | 9196776.96 | 9196776.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9196776.96 | 0 | 9196776.96 | 9196776.96 | 0
398 | * | Procurement of High Pressure HOV for PRP | NL-N-TS2-002-05-03-51 | 24179843.3 | 0 | 24179843.3 | 24179843.3 | 0 | 0 | 0 | 0 | 0 | 0 | 24179843.3 | 0 | 24179843.3 | 24179843.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24179843.3 | 0 | 24179843.3 | 24179843.3 | 0
399 | * | Water Lance 8 stage centrifugal pump | NL-N-TS2-002-05-03-52 | 2481348.12 | 0 | 2481348.12 | 2481348.12 | 0 | 0 | 0 | 0 | 0 | 0 | 2481348.12 | 0 | 2481348.12 | 2481348.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2481348.12 | 0 | 2481348.12 | 2481348.12 | 0
400 | * | Boiler J row pipe supporting Structure | NL-N-TS2-002-05-03-53 | 6205500.01 | 0 | 6205500.01 | 6205500.01 | 0 | 0 | 0 | 0 | 0 | 0 | 6205500.01 | 0 | 6205500.01 | 6205500.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6205500.01 | 0 | 6205500.01 | 6205500.01 | 0
401 | * | Damaged Boiler Auxiliary Structures Rect | NL-N-TS2-002-05-03-54 | 750000.01 | 0 | 750000.01 | 750000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 750000.01 | 0 | 750000.01 | 750000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000.01 | 0 | 750000.01 | 750000.01 | 0
402 | * | Purchase of Seamless Carbon Steel pipes | NL-N-TS2-002-05-03-55 | 31581166 | 0 | 31581166 | 31581166 | 0 | 0 | 0 | 0 | 0 | 0 | 31581166 | 0 | 31581166 | 31581166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31581166 | 0 | 31581166 | 31581166 | 0
403 | * | Procurement of Water wall S panel St-I | NL-N-TS2-002-05-03-56 | 24101976 | 0 | 24101976 | 24101976 | 0 | 0 | 0 | 0 | 0 | 0 | 24101976 | 0 | 24101976 | 24101976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24101976 | 0 | 24101976 | 24101976 | 0
404 | * | Replacement of Economiser Coil Bend-St-I | NL-N-TS2-002-05-03-57 | 9992640.01 | 0 | 9992640.01 | 9992640.01 | 0 | 0 | 0 | 0 | 0 | 0 | 9992640.01 | 0 | 9992640.01 | 9992640.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9992640.01 | 0 | 9992640.01 | 9992640.01 | 0
405 | * | Rep of damaged water wall tubes&Panels | NL-N-TS2-002-05-03-58 | 12333990.02 | 0 | 12333990.02 | 12333990.02 | 0 | 0 | 0 | 0 | 0 | 0 | 12333990.02 | 0 | 12333990.02 | 12333990.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12333990.02 | 0 | 12333990.02 | 12333990.02 | 0
406 | * | SSB SPARES PURCHASE | NL-N-TS2-002-05-03-59 | 2985990 | 0 | 0 | 0 | 2985990 | 0 | 0 | 0 | 0 | 0 | 2985990 | 0 | 0 | 0 | 2985990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2985990 | 0 | 0 | 0 | 2985990
407 | ** | RAPH & FANS | NL-N-TS2-002-05-04 | 261450559.84 | 49325624.81 | 210103131.22 | 259439477.02 | 2011082.82 | 49752008.18 | 47730204.37 | 0 | 47740925.36 | 2011082.82 | 211698551.66 | 1595420.44 | 210103131.22 | 211698551.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261450559.84 | 49325624.81 | 210103131.22 | 259439477.02 | 2011082.82
408 | * | RAPH BASKETS AND BEARINGS | NL-N-TS2-002-05-04-01 | 29453703.18 | 20105055.28 | 9348647.9 | 29453703.18 | 0 | 20105055.28 | 20105055.28 | 0 | 20105055.28 | 0 | 9348647.9 | 0 | 9348647.9 | 9348647.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29453703.18 | 20105055.28 | 9348647.9 | 29453703.18 | 0
409 | * | Lub Oil Pump for RAPH | NL-N-TS2-002-05-04-02 | 702336 | 702336 | 0 | 702336 | 0 | 702336 | 702336 | 0 | 702336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702336 | 702336 | 0 | 702336 | 0
410 | * | Electric operate Hydrulic Synhns of RAPH | NL-N-TS2-002-05-04-03 | 1618272 | 1618272 | 0 | 1618272 | 0 | 1618272 | 1618272 | 0 | 1618272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1618272 | 1618272 | 0 | 1618272 | 0
411 | * | Single Bellow Compensator Corner Piece | NL-N-TS2-002-05-04-04 | 446438.08 | 446438.08 | 0 | 446438.08 | 0 | 446438.08 | 446438.08 | 0 | 446438.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446438.08 | 446438.08 | 0 | 446438.08 | 0
412 | * | Electric Power Winch - 5 Ton Capacity | NL-N-TS2-002-05-04-06 | 1087716 | 1087716 | 0 | 1087716 | 0 | 1087716 | 1087716 | 0 | 1087716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1087716 | 1087716 | 0 | 1087716 | 0
413 | * | Spiral Bevel Gear and Pinion | NL-N-TS2-002-05-04-07 | 95968.82 | 95968.82 | 0 | 95968.82 | 0 | 95968.82 | 95968.82 | 0 | 95968.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95968.82 | 95968.82 | 0 | 95968.82 | 0
414 | * | RAPH Stage-I Gear Box | NL-N-TS2-002-05-04-10 | 1065370.35 | 1060060.32 | 5310.03 | 1065370.35 | 0 | 1060060.32 | 1060060.32 | 0 | 1060060.32 | 0 | 5310.03 | 0 | 5310.03 | 5310.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1065370.35 | 1060060.32 | 5310.03 | 1065370.35 | 0
415 |  | Bore corre work GB housing of Raph st-I | NL-N-TS2-002-05-04-10-01 | 354000.03 | 348690 | 5310.03 | 354000.03 | 0 | 348690 | 348690 | 0 | 348690 | 0 | 5310.03 | 0 | 5310.03 | 5310.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354000.03 | 348690 | 5310.03 | 354000.03 | 0
416 |  | Gear Box spares for stage-1 | NL-N-TS2-002-05-04-10-02 | 711370.32 | 711370.32 | 0 | 711370.32 | 0 | 711370.32 | 711370.32 | 0 | 711370.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711370.32 | 711370.32 | 0 | 711370.32 | 0
417 | * | ID/FD Bearing Assmbly Shaft | NL-N-TS2-002-05-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | * | ID fan Blades with Countersunk Screws | NL-N-TS2-002-05-04-14 | 7827311.03 | 5805507.22 | 0 | 5816228.21 | 2011082.82 | 7827311.03 | 5805507.22 | 0 | 5816228.21 | 2011082.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7827311.03 | 5805507.22 | 0 | 5816228.21 | 2011082.82
419 |  |  | open | 0 | 2781318.51 | 0 | 2781318.51 | -2781318.51 | 0 | 2781318.51 | 0 | 2781318.51 | -2781318.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781318.51 | 0 | 2781318.51 | -2781318.51
420 |  |  | ope | 0 | 3024188.71 | 0 | 3024188.71 | -3024188.71 | 0 | 3024188.71 | 0 | 3024188.71 | -3024188.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3024188.71 | 0 | 3024188.71 | -3024188.71
421 | * | RSD & Other Ducts | NL-N-TS2-002-05-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | * | ID/FD Impellers spares | NL-N-TS2-002-05-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | * | Knee Toggle Lever For ID | NL-N-TS2-002-05-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | * | Bearing Assembly | NL-N-TS2-002-05-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | * | RAPH LOPs | NL-N-TS2-002-05-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | * | RAPH Bisectors | NL-N-TS2-002-05-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | * | RAPH HE Basket | NL-N-TS2-002-05-04-21 | 9991927.13 | 9991927.13 | 0 | 9991927.13 | 0 | 9991927.13 | 9991927.13 | 0 | 9991927.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9991927.13 | 9991927.13 | 0 | 9991927.13 | 0
428 | * | FD Impeller Blades | NL-N-TS2-002-05-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | * | Hopper Air Dambers | NL-N-TS2-002-05-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | * | Dambers Gearbox | NL-N-TS2-002-05-04-24 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0
431 |  | Damper Gear box-AD2/GD1/GD2/AD3,4&5 | NL-N-TS2-002-05-04-24-01 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0
432 | * | Fan & RAPH Collers | NL-N-TS2-002-05-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | * | ID impeller Assembly | NL-N-TS2-002-05-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | * | RAPH Support Bearing | NL-N-TS2-002-05-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | * | thochoid lub oil pump for St-II gear box | NL-N-TS2-002-05-04-28 | 375240 | 375240 | 0 | 375240 | 0 | 375240 | 375240 | 0 | 375240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375240 | 375240 | 0 | 375240 | 0
436 | * | Lub oil pump for SB&GB of RAPH Stage-II | NL-N-TS2-002-05-04-29 | 1974000.62 | 1974000.02 | 0.6 | 1974000.62 | 0 | 1974000.02 | 1974000.02 | 0 | 1974000.02 | 0 | 0.6 | 0 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1974000.62 | 1974000.02 | 0.6 | 1974000.62 | 0
437 | * | Disman and Erection of RSD below 15 ML | NL-N-TS2-002-05-04-30 | 9412800.03 | 778800 | 8634000.03 | 9412800.03 | 0 | 778800 | 778800 | 0 | 778800 | 0 | 8634000.03 | 0 | 8634000.03 | 8634000.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9412800.03 | 778800 | 8634000.03 | 9412800.03 | 0
438 | * | Single/Double fold bellow and corner pie | NL-N-TS2-002-05-04-31 | 1595420.44 | 1595420.44 | 0 | 1595420.44 | 0 | 0 | 0 | 0 | 0 | 0 | 1595420.44 | 1595420.44 | 0 | 1595420.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1595420.44 | 1595420.44 | 0 | 1595420.44 | 0
439 | * | ID Fan Blades | NL-N-TS2-002-05-04-32 | 10974000 | 0 | 10974000 | 10974000 | 0 | 0 | 0 | 0 | 0 | 0 | 10974000 | 0 | 10974000 | 10974000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10974000 | 0 | 10974000 | 10974000 | 0
440 | * | Replacement of Support & Guide bearing | NL-N-TS2-002-05-04-33 | 2474516.67 | 1237258.32 | 1237258.35 | 2474516.67 | 0 | 1237258.32 | 1237258.32 | 0 | 1237258.32 | 0 | 1237258.35 | 0 | 1237258.35 | 1237258.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2474516.67 | 1237258.32 | 1237258.35 | 2474516.67 | 0
441 | * | ID Fan Bearing shaft | NL-N-TS2-002-05-04-34 | 4600000 | 0 | 4600000 | 4600000 | 0 | 0 | 0 | 0 | 0 | 0 | 4600000 | 0 | 4600000 | 4600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600000 | 0 | 4600000 | 4600000 | 0
442 | * | FD fan Impeller blades with Cylindrical | NL-N-TS2-002-05-04-35 | 7209999.99 | 0 | 7209999.99 | 7209999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 7209999.99 | 0 | 7209999.99 | 7209999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7209999.99 | 0 | 7209999.99 | 7209999.99 | 0
443 | * | ID Fan Pressure Releif valves | NL-N-TS2-002-05-04-36 | 2489373.24 | 0 | 2489373.24 | 2489373.24 | 0 | 0 | 0 | 0 | 0 | 0 | 2489373.24 | 0 | 2489373.24 | 2489373.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2489373.24 | 0 | 2489373.24 | 2489373.24 | 0
444 | * | SEISA GEAR BOX FOR STAGE-II RAPH MAIN DR | NL-N-TS2-002-05-04-37 | 37524000 | 0 | 37524000 | 37524000 | 0 | 0 | 0 | 0 | 0 | 0 | 37524000 | 0 | 37524000 | 37524000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37524000 | 0 | 37524000 | 37524000 | 0
445 | * | Stage-I RAPH BASKETS Spares | NL-N-TS2-002-05-04-38 | 62644448.64 | 0 | 62644448.64 | 62644448.64 | 0 | 0 | 0 | 0 | 0 | 0 | 62644448.64 | 0 | 62644448.64 | 62644448.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62644448.64 | 0 | 62644448.64 | 62644448.64 | 0
446 | * | Assembly of heating Element Hot and cold | NL-N-TS2-002-05-04-39 | 62972101.2 | 0 | 62972101.2 | 62972101.2 | 0 | 0 | 0 | 0 | 0 | 0 | 62972101.2 | 0 | 62972101.2 | 62972101.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62972101.2 | 0 | 62972101.2 | 62972101.2 | 0
447 | * | ID/FD fan lub oil cooler-satage-II | NL-N-TS2-002-05-04-40 | 2463991.24 | 0 | 2463991.24 | 2463991.24 | 0 | 0 | 0 | 0 | 0 | 0 | 2463991.24 | 0 | 2463991.24 | 2463991.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2463991.24 | 0 | 2463991.24 | 2463991.24 | 0
448 | *** | C & I | NL-N-TS2-002-06 | 360240006.58 | 257635196.28 | 102538048.3 | 360173244.58 | 66762 | 248457747.03 | 248425296.28 | 0 | 248425296.28 | 32450.75 | 111782259.55 | 9209900 | 102538048.3 | 111747948.3 | 34311.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360240006.58 | 257635196.28 | 102538048.3 | 360173244.58 | 66762
449 | ** | Slag Conveyor camera and TV replaceme | NL-N-TS2-002-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | ** | Temperature transmitter | NL-N-TS2-002-06-02 | 1684056.08 | 1684056.08 | 0 | 1684056.08 | 0 | 1684056.08 | 1684056.08 | 0 | 1684056.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684056.08 | 1684056.08 | 0 | 1684056.08 | 0
451 | ** | Turbine Trip SOV – Stage-II | NL-N-TS2-002-06-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | ** | Stator Water Conductivity - Stage-II | NL-N-TS2-002-06-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | ** | Oil Burners spares – Ignition gun & tran | NL-N-TS2-002-06-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | ** | Oil Burner Atomising Steam valve Stage-I | NL-N-TS2-002-06-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | ** | Purge Steam valve Stage-I | NL-N-TS2-002-06-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | ** | Control valve and ICV position F/B xrs f | NL-N-TS2-002-06-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | ** | Water Lance spares- BV, Freq conv, Choke | NL-N-TS2-002-06-09 | 2360924 | 0 | 2360924 | 2360924 | 0 | 0 | 0 | 0 | 0 | 0 | 2360924 | 0 | 2360924 | 2360924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2360924 | 0 | 2360924 | 2360924 | 0
458 | ** | CWP alarm & protection cables | NL-N-TS2-002-06-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | ** | CO Analyser | NL-N-TS2-002-06-11 | 2076405 | 0 | 2076405 | 2076405 | 0 | 0 | 0 | 0 | 0 | 0 | 2076405 | 0 | 2076405 | 2076405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2076405 | 0 | 2076405 | 2076405 | 0
460 | ** | Furnace monitoring Camera | NL-N-TS2-002-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | ** | Flame Scanner (OIL) | NL-N-TS2-002-06-13 | 2277375.9 | 2277375.9 | 0 | 2277375.9 | 0 | 2277375.9 | 2277375.9 | 0 | 2277375.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2277375.9 | 2277375.9 | 0 | 2277375.9 | 0
462 | ** | Thermal Imaging camera | NL-N-TS2-002-06-14 | 826000 | 826000 | 0 | 826000 | 0 | 826000 | 826000 | 0 | 826000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826000 | 826000 | 0 | 826000 | 0
463 | ** | Zirconia Oxygen Analyser & Spares | NL-N-TS2-002-06-15 | 8009162.59 | 7342662.6 | 666499.99 | 8009162.59 | 0 | 7342662.6 | 7342662.6 | 0 | 7342662.6 | 0 | 666499.99 | 0 | 666499.99 | 666499.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8009162.59 | 7342662.6 | 666499.99 | 8009162.59 | 0
464 | ** | Flame Scanner (LIGNITE) | NL-N-TS2-002-06-16 | 1801231.28 | 1801231.28 | 0 | 1801231.28 | 0 | 1801231.28 | 1801231.28 | 0 | 1801231.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801231.28 | 1801231.28 | 0 | 1801231.28 | 0
465 | ** | Hydrogen Purity Analyser | NL-N-TS2-002-06-17 | 6226614.43 | 5128574.49 | 1098039.94 | 6226614.43 | 0 | 5128574.49 | 5128574.49 | 0 | 5128574.49 | 0 | 1098039.94 | 0 | 1098039.94 | 1098039.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6226614.43 | 5128574.49 | 1098039.94 | 6226614.43 | 0
466 | ** | Chlorine Leak Detector & Scanner | NL-N-TS2-002-06-18 | 365890 | 0 | 365890 | 365890 | 0 | 0 | 0 | 0 | 0 | 0 | 365890 | 0 | 365890 | 365890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365890 | 0 | 365890 | 365890 | 0
467 | ** | Ultra Sonic Flow Meters | NL-N-TS2-002-06-19 | 1100888.26 | 1100888.26 | 0 | 1100888.26 | 0 | 1100888.26 | 1100888.26 | 0 | 1100888.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100888.26 | 1100888.26 | 0 | 1100888.26 | 0
468 | ** | Secondary & Hot Air Flow Transmitters | NL-N-TS2-002-06-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | ** | Oil Burner Air Flow Transmitter | NL-N-TS2-002-06-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | ** | Coriolis Mass Flow Meters With Tanker Un | NL-N-TS2-002-06-23 | 6646586 | 6646586 | 0 | 6646586 | 0 | 6646586 | 6646586 | 0 | 6646586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6646586 | 6646586 | 0 | 6646586 | 0
471 | ** | Opacity Monitors | NL-N-TS2-002-06-24 | 1258556.98 | 1258556.98 | 0 | 1258556.98 | 0 | 1258556.98 | 1258556.98 | 0 | 1258556.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258556.98 | 1258556.98 | 0 | 1258556.98 | 0
472 | ** | Gas Detectors-Portable | NL-N-TS2-002-06-25 | 139649.99 | 139649.99 | 0 | 139649.99 | 0 | 139649.99 | 139649.99 | 0 | 139649.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139649.99 | 139649.99 | 0 | 139649.99 | 0
473 | ** | Coriolis Flow Meters for Boiler HFO line | NL-N-TS2-002-06-26 | 6153700 | 6153700 | 0 | 6153700 | 0 | 6153700 | 6153700 | 0 | 6153700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6153700 | 6153700 | 0 | 6153700 | 0
474 | ** | Hydrogen Dew Point Meters | NL-N-TS2-002-06-27 | 1138700 | 1138700 | 0 | 1138700 | 0 | 1138700 | 1138700 | 0 | 1138700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1138700 | 1138700 | 0 | 1138700 | 0
475 | ** | CPU with LAN & LCM Power Controller | NL-N-TS2-002-06-28 | 9027000 | 9027000 | 0 | 9027000 | 0 | 9027000 | 9027000 | 0 | 9027000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9027000 | 9027000 | 0 | 9027000 | 0
476 | ** | Hydrogen Gas Density Analyser | NL-N-TS2-002-06-30 | 952850 | 952850 | 0 | 952850 | 0 | 952850 | 952850 | 0 | 952850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952850 | 952850 | 0 | 952850 | 0
477 | ** | Control System and HMI for Water Lancer | NL-N-TS2-002-06-31 | 29500 | 0 | 29500 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 29500 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 29500 | 29500 | 0
478 | ** | Electronic DLI for Boiler Drum | NL-N-TS2-002-06-32 | 295000 | 0 | 295000 | 295000 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 0 | 295000 | 295000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 0 | 295000 | 295000 | 0
479 | ** | Common Monitoring Controller for WCTP | NL-N-TS2-002-06-33 | 3929400 | 0 | 3929400 | 3929400 | 0 | 0 | 0 | 0 | 0 | 0 | 3929400 | 0 | 3929400 | 3929400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3929400 | 0 | 3929400 | 3929400 | 0
480 | ** | Steam & Water Analysis System-Stage-I | NL-N-TS2-002-06-34 | 2050722 | 2050722 | 0 | 2050722 | 0 | 2050722 | 2050722 | 0 | 2050722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050722 | 2050722 | 0 | 2050722 | 0
481 | ** | Single Compartment Temp Transmitter | NL-N-TS2-002-06-35 | 2248815 | 0 | 2248815 | 2248815 | 0 | 0 | 0 | 0 | 0 | 0 | 2248815 | 0 | 2248815 | 2248815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2248815 | 0 | 2248815 | 2248815 | 0
482 | ** | Positioner Cylinder for BFP Scoop | NL-N-TS2-002-06-36 | 1973640.02 | 1973640.02 | 0 | 1973640.02 | 0 | 1973640.02 | 1973640.02 | 0 | 1973640.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1973640.02 | 1973640.02 | 0 | 1973640.02 | 0
483 | ** | Erection of Venturi&Impules Line/U-4,6,7 | NL-N-TS2-002-06-37 | 3159450 | 2933775 | 225675 | 3159450 | 0 | 2933775 | 2933775 | 0 | 2933775 | 0 | 225675 | 0 | 225675 | 225675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3159450 | 2933775 | 225675 | 3159450 | 0
484 | ** | Erection of Venturi&Impules Line/Unit-1 | NL-N-TS2-002-06-38 | 1215282 | 1173694.08 | 41587.92 | 1215282 | 0 | 1173694.08 | 1173694.08 | 0 | 1173694.08 | 0 | 41587.92 | 0 | 41587.92 | 41587.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215282 | 1173694.08 | 41587.92 | 1215282 | 0
485 | ** | Effluent Outlet Flow measurement System | NL-N-TS2-002-06-39 | 681450.11 | 616549.89 | 32450.11 | 649000 | 32450.11 | 649000 | 616549.89 | 0 | 616549.89 | 32450.11 | 32450.11 | 0 | 32450.11 | 32450.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 681450.11 | 616549.89 | 32450.11 | 649000 | 32450.11
486 | ** | Stage-I DCS upgradation | NL-N-TS2-002-06-42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | ** | DP Level Transmitter | NL-N-TS2-002-06-48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | ** | Turbo Supervisory Instruments Spares | NL-N-TS2-002-06-49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | ** | HP & LP Bypass instruments | NL-N-TS2-002-06-50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | ** | ID/FD PCD & Instruments | NL-N-TS2-002-06-51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | ** | EWLI for Hotwell & Deaerator | NL-N-TS2-002-06-52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | ** | STAGE-I DCS Spares &OWS | NL-N-TS2-002-06-54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | ** | Controls System for Water Lancer | NL-N-TS2-002-06-55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | ** | water lanceblowing valve GSR | NL-N-TS2-002-06-56 | 1390512 | 1390512 | 0 | 1390512 | 0 | 1390512 | 1390512 | 0 | 1390512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1390512 | 1390512 | 0 | 1390512 | 0
495 | ** | Turbo Supervisory instrument modules 12 | NL-N-TS2-002-06-57 | 7543538.8 | 0 | 7543538.8 | 7543538.8 | 0 | 0 | 0 | 0 | 0 | 0 | 7543538.8 | 0 | 7543538.8 | 7543538.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7543538.8 | 0 | 7543538.8 | 7543538.8 | 0
496 | ** | Keltron Make Pneu Actuators for ID&FD | NL-N-TS2-002-06-58 | 2226355.49 | 0 | 2226355.49 | 2226355.49 | 0 | 0 | 0 | 0 | 0 | 0 | 2226355.49 | 0 | 2226355.49 | 2226355.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2226355.49 | 0 | 2226355.49 | 2226355.49 | 0
497 | ** | Purchase of pfb transmitter for HP bp | NL-N-TS2-002-06-59 | 2421774.57 | 0 | 2421774.57 | 2421774.57 | 0 | 0 | 0 | 0 | 0 | 0 | 2421774.57 | 0 | 2421774.57 | 2421774.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2421774.57 | 0 | 2421774.57 | 2421774.57 | 0
498 | ** | Purchase of DCS Spares for SIEMENS St-I | NL-N-TS2-002-06-60 | 2404956.69 | 2404956.69 | 0 | 2404956.69 | 0 | 2404956.69 | 2404956.69 | 0 | 2404956.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2404956.69 | 2404956.69 | 0 | 2404956.69 | 0
499 | ** | Purchase of Rockwin Turbine Flowmeter | NL-N-TS2-002-06-61 | 434018.16 | 434018.16 | 0 | 434018.16 | 0 | 434018.16 | 434018.16 | 0 | 434018.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434018.16 | 434018.16 | 0 | 434018.16 | 0
500 | ** | Pur & Comm of radar type level transmitt | NL-N-TS2-002-06-62 | 626095.66 | 521913.38 | 104181.64 | 626095.02 | 0.64 | 521914.02 | 521913.38 | 0 | 521913.38 | 0.64 | 104181.64 | 0 | 104181.64 | 104181.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626095.66 | 521913.38 | 104181.64 | 626095.02 | 0.64
501 | ** | Online weighing system for stacker | NL-N-TS2-002-06-63 | 803186 | 0 | 803186 | 803186 | 0 | 0 | 0 | 0 | 0 | 0 | 803186 | 0 | 803186 | 803186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803186 | 0 | 803186 | 803186 | 0
502 | ** | Flue gas Detector 3Nos | NL-N-TS2-002-06-64 | 2484624 | 0 | 2484624 | 2484624 | 0 | 0 | 0 | 0 | 0 | 0 | 2484624 | 0 | 2484624 | 2484624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2484624 | 0 | 2484624 | 2484624 | 0
503 | ** | Design Engg manufacturing&supply of DCS | NL-N-TS2-002-06-65 | 212681688.45 | 189447683.48 | 23234004.97 | 212681688.45 | 0 | 189447683.48 | 189447683.48 | 0 | 189447683.48 | 0 | 23234004.97 | 0 | 23234004.97 | 23234004.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212681688.45 | 189447683.48 | 23234004.97 | 212681688.45 | 0
504 | ** | Purchase of Metso DNA DCS Controller spa | NL-N-TS2-002-06-66 | 9209900 | 9209900 | 0 | 9209900 | 0 | 0 | 0 | 0 | 0 | 0 | 9209900 | 9209900 | 0 | 9209900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9209900 | 9209900 | 0 | 9209900 | 0
505 | ** | Purchase of Temperature Transmitters | NL-N-TS2-002-06-67 | 2102550.11 | 0 | 2101933.67 | 2101933.67 | 616.44 | 0 | 0 | 0 | 0 | 0 | 2102550.11 | 0 | 2101933.67 | 2101933.67 | 616.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2102550.11 | 0 | 2101933.67 | 2101933.67 | 616.44
506 | ** | Purchase of Metso DNA spares-IPSP &IBC | NL-N-TS2-002-06-68 | 30789788.2 | 0 | 30789788.2 | 30789788.2 | 0 | 0 | 0 | 0 | 0 | 0 | 30789788.2 | 0 | 30789788.2 | 30789788.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30789788.2 | 0 | 30789788.2 | 30789788.2 | 0
507 | ** | Power supply Unit for Siemens DCS | NL-N-TS2-002-06-69 | 8855608.36 | 0 | 8838550 | 8838550 | 17058.36 | 0 | 0 | 0 | 0 | 0 | 8855608.36 | 0 | 8838550 | 8838550 | 17058.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8855608.36 | 0 | 8838550 | 8838550 | 17058.36
508 | ** | RTD Input Module for Stage-I DCS | NL-N-TS2-002-06-70 | 8636560.45 | 0 | 8619924 | 8619924 | 16636.45 | 0 | 0 | 0 | 0 | 0 | 8636560.45 | 0 | 8619924 | 8619924 | 16636.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8636560.45 | 0 | 8619924 | 8619924 | 16636.45
509 | *** | LHS MAINTENANCE | NL-N-TS2-002-07 | 661771344.25 | 621315735.58 | 40455608.67 | 661771344.25 | 0 | 621315735.58 | 621315735.58 | 0 | 621315735.58 | 0 | 40455608.67 | 0 | 40455608.67 | 40455608.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661771344.25 | 621315735.58 | 40455608.67 | 661771344.25 | 0
510 | ** | CONVEYORS AND SYSTEM ASSEMBLY | NL-N-TS2-002-07-01 | 20939218.48 | 20246204.46 | 693014.02 | 20939218.48 | 0 | 20246204.46 | 20246204.46 | 0 | 20246204.46 | 0 | 693014.02 | 0 | 693014.02 | 693014.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20939218.48 | 20246204.46 | 693014.02 | 20939218.48 | 0
511 | ** | LIGNITE YARD RAILS REPLACEMENT | NL-N-TS2-002-07-02 | 27000001.3 | 26848891.29 | 151110.01 | 27000001.3 | 0 | 26848891.29 | 26848891.29 | 0 | 26848891.29 | 0 | 151110.01 | 0 | 151110.01 | 151110.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000001.3 | 26848891.29 | 151110.01 | 27000001.3 | 0
512 | ** | BELT EQUIPMENT SYSTEM | NL-N-TS2-002-07-03 | 705000 | 705000 | 0 | 705000 | 0 | 705000 | 705000 | 0 | 705000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705000 | 705000 | 0 | 705000 | 0
513 | ** | Replacement of Two Reclaimers | NL-N-TS2-002-07-04 | 549498106.49 | 549498102.27 | 4.22 | 549498106.49 | 0 | 549498102.27 | 549498102.27 | 0 | 549498102.27 | 0 | 4.22 | 0 | 4.22 | 4.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549498106.49 | 549498102.27 | 4.22 | 549498106.49 | 0
514 | ** | Vacuum Cleaners for Bunker bay | NL-N-TS2-002-07-05 | 1803473.97 | 1803473.97 | 0 | 1803473.97 | 0 | 1803473.97 | 1803473.97 | 0 | 1803473.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803473.97 | 1803473.97 | 0 | 1803473.97 | 0
515 | ** | Vulcanizing Equipments | NL-N-TS2-002-07-06 | 6071695.81 | 6071695.81 | 0 | 6071695.81 | 0 | 6071695.81 | 6071695.81 | 0 | 6071695.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6071695.81 | 6071695.81 | 0 | 6071695.81 | 0
516 | ** | Various Idlers | NL-N-TS2-002-07-07 | 10289087.89 | 0 | 10289087.89 | 10289087.89 | 0 | 0 | 0 | 0 | 0 | 0 | 10289087.89 | 0 | 10289087.89 | 10289087.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10289087.89 | 0 | 10289087.89 | 10289087.89 | 0
517 | ** | Cam Shafts | NL-N-TS2-002-07-08 | 4196352.41 | 0 | 4196352.41 | 4196352.41 | 0 | 0 | 0 | 0 | 0 | 0 | 4196352.41 | 0 | 4196352.41 | 4196352.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4196352.41 | 0 | 4196352.41 | 4196352.41 | 0
518 | ** | Structural Repair Works | NL-N-TS2-002-07-09 | 12477113.66 | 9221777.39 | 3255336.27 | 12477113.66 | 0 | 9221777.39 | 9221777.39 | 0 | 9221777.39 | 0 | 3255336.27 | 0 | 3255336.27 | 3255336.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12477113.66 | 9221777.39 | 3255336.27 | 12477113.66 | 0
519 | ** | Compressor for DSS system at LHS | NL-N-TS2-002-07-10 | 4496421.39 | 4496421.39 | 0 | 4496421.39 | 0 | 4496421.39 | 4496421.39 | 0 | 4496421.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4496421.39 | 4496421.39 | 0 | 4496421.39 | 0
520 | ** | Rack for Shuttle Conveyors | NL-N-TS2-002-07-11 | 810661.86 | 810661.86 | 0 | 810661.86 | 0 | 810661.86 | 810661.86 | 0 | 810661.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810661.86 | 810661.86 | 0 | 810661.86 | 0
521 | ** | Bunker Grill_size2400x1120x100 | NL-N-TS2-002-07-12 | 1613507.14 | 1613507.14 | 0 | 1613507.14 | 0 | 1613507.14 | 1613507.14 | 0 | 1613507.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1613507.14 | 1613507.14 | 0 | 1613507.14 | 0
522 | ** | Gear Box Spares | NL-N-TS2-002-07-13 | 8185896 | 0 | 8185896 | 8185896 | 0 | 0 | 0 | 0 | 0 | 0 | 8185896 | 0 | 8185896 | 8185896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8185896 | 0 | 8185896 | 8185896 | 0
523 | ** | Hydraulic Cylinders for Conveyors | NL-N-TS2-002-07-14 | 1579649.45 | 0 | 1579649.45 | 1579649.45 | 0 | 0 | 0 | 0 | 0 | 0 | 1579649.45 | 0 | 1579649.45 | 1579649.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579649.45 | 0 | 1579649.45 | 1579649.45 | 0
524 | ** | Gear box spares for Bunker Conveyors | NL-N-TS2-002-07-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
525 | ** | Structural repair Works | NL-N-TS2-002-07-16 | 12105158.4 | 0 | 12105158.4 | 12105158.4 | 0 | 0 | 0 | 0 | 0 | 0 | 12105158.4 | 0 | 12105158.4 | 12105158.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12105158.4 | 0 | 12105158.4 | 12105158.4 | 0
526 | *** | TURBINE MAINTENANCE | NL-N-TS2-002-08 | 1300064047.19 | 139372041.41 | 205246313.79 | 344618355.2 | 955445691.99 | 130378330.08 | 130380508.86 | 1651044.03 | 132031552.89 | -1653222.81 | 1169685717.11 | 8991532.55 | 203595269.76 | 212586802.31 | 957098914.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300064047.19 | 139372041.41 | 205246313.79 | 344618355.2 | 955445691.99
527 | ** | MAIN TURBINE | NL-N-TS2-002-08-01 | 1007595568.66 | 5126154.84 | 68459154.82 | 73585309.66 | 934010259 | 5126154.84 | 5126154.84 | 0 | 5126154.84 | 0 | 1002469413.82 | 0 | 68459154.82 | 68459154.82 | 934010259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007595568.66 | 5126154.84 | 68459154.82 | 73585309.66 | 934010259
528 | * | HP Module Purchase | NL-N-TS2-002-08-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
529 | * | IP Inner casing | NL-N-TS2-002-08-01-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
530 | * | LP Laststage Blade | NL-N-TS2-002-08-01-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
531 | * | Turbine Gov system Internals | NL-N-TS2-002-08-01-04 | 2009824.02 | 2009824.02 | 0 | 2009824.02 | 0 | 2009824.02 | 2009824.02 | 0 | 2009824.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009824.02 | 2009824.02 | 0 | 2009824.02 | 0
532 | * | Turbine fasteners & Coupling Bolts | NL-N-TS2-002-08-01-05 | 1547157.78 | 1547157.78 | 0 | 1547157.78 | 0 | 1547157.78 | 1547157.78 | 0 | 1547157.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547157.78 | 1547157.78 | 0 | 1547157.78 | 0
533 | * | MS Strainer body | NL-N-TS2-002-08-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
534 | * | HRH Stainer Body | NL-N-TS2-002-08-01-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
535 | * | UNIT-2 MAIN TURBINE LEP PURCHASE | NL-N-TS2-002-08-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
536 | * | UNIT-1 LEP SPares Purchase | NL-N-TS2-002-08-01-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
537 | * | Clam pie T lp rotor last stage blades | NL-N-TS2-002-08-01-11 | 5222594.09 | 0 | 5222594.09 | 5222594.09 | 0 | 0 | 0 | 0 | 0 | 0 | 5222594.09 | 0 | 5222594.09 | 5222594.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5222594.09 | 0 | 5222594.09 | 5222594.09 | 0
538 | * | Jet Gage and System | NL-N-TS2-002-08-01-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
539 | * | EOT Crane Spares | NL-N-TS2-002-08-01-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540 | * | Centrifuge Spares | NL-N-TS2-002-08-01-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
541 | * | Machining items | NL-N-TS2-002-08-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
542 | * | Governing valves spares | NL-N-TS2-002-08-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
543 | * | Turbine Gl seal segment BHELmake 12items | NL-N-TS2-002-08-01-17 | 9337634 | 0 | 9337634 | 9337634 | 0 | 0 | 0 | 0 | 0 | 0 | 9337634 | 0 | 9337634 | 9337634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9337634 | 0 | 9337634 | 9337634 | 0
544 | * | Helical com spring for T G Sealing 2ite | NL-N-TS2-002-08-01-18 | 1232753 | 1232753 | 0 | 1232753 | 0 | 1232753 | 1232753 | 0 | 1232753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232753 | 1232753 | 0 | 1232753 | 0
545 | * | IP Plane fastener GS spares ST-2 | NL-N-TS2-002-08-01-19 | 16250553.12 | 0 | 16250553.12 | 16250553.12 | 0 | 0 | 0 | 0 | 0 | 0 | 16250553.12 | 0 | 16250553.12 | 16250553.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16250553.12 | 0 | 16250553.12 | 16250553.12 | 0
546 | * | Spares for main Turbine Sealing Strip | NL-N-TS2-002-08-01-20 | 5448111.75 | 315606.04 | 5132505.71 | 5448111.75 | 0 | 315606.04 | 315606.04 | 0 | 315606.04 | 0 | 5132505.71 | 0 | 5132505.71 | 5132505.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5448111.75 | 315606.04 | 5132505.71 | 5448111.75 | 0
547 | * | Condenser Manhole Cover assembly | NL-N-TS2-002-08-01-21 | 1975320 | 0 | 1975320 | 1975320 | 0 | 0 | 0 | 0 | 0 | 0 | 1975320 | 0 | 1975320 | 1975320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1975320 | 0 | 1975320 | 1975320 | 0
548 | * | Planetary unit sub assembly for Main hoi | NL-N-TS2-002-08-01-22 | 726500 | 0 | 726500 | 726500 | 0 | 0 | 0 | 0 | 0 | 0 | 726500 | 0 | 726500 | 726500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726500 | 0 | 726500 | 726500 | 0
549 | * | Portable single phase welding machine | NL-N-TS2-002-08-01-23 | 20814 | 20814 | 0 | 20814 | 0 | 20814 | 20814 | 0 | 20814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20814 | 20814 | 0 | 20814 | 0
550 | * | MOP Spares,HP stop valves spares&HP casi | NL-N-TS2-002-08-01-24 | 13004945 | 0 | 13004945 | 13004945 | 0 | 0 | 0 | 0 | 0 | 0 | 13004945 | 0 | 13004945 | 13004945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13004945 | 0 | 13004945 | 13004945 | 0
551 | * | Main Oil pump impeller for St-II Turbine | NL-N-TS2-002-08-01-25 | 10775099.9 | 0 | 10775099.9 | 10775099.9 | 0 | 0 | 0 | 0 | 0 | 0 | 10775099.9 | 0 | 10775099.9 | 10775099.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10775099.9 | 0 | 10775099.9 | 10775099.9 | 0
552 | * | Boll &Kirch Filter Element for Duplex | NL-N-TS2-002-08-01-26 | 3469068 | 0 | 3469068 | 3469068 | 0 | 0 | 0 | 0 | 0 | 0 | 3469068 | 0 | 3469068 | 3469068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3469068 | 0 | 3469068 | 3469068 | 0
553 | * | Over speed trip release unit | NL-N-TS2-002-08-01-27 | 2564935 | 0 | 2564935 | 2564935 | 0 | 0 | 0 | 0 | 0 | 0 | 2564935 | 0 | 2564935 | 2564935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2564935 | 0 | 2564935 | 2564935 | 0
554 | * | purchase of Turbine spares unit 1 LEP | NL-N-TS2-002-08-01-28 | 924013865 | 0 | 0 | 0 | 924013865 | 0 | 0 | 0 | 0 | 0 | 924013865 | 0 | 0 | 0 | 924013865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 924013865 | 0 | 0 | 0 | 924013865
555 | * | DUROMAR COATING ON SHEETS & WATER BOX | NL-N-TS2-002-08-01-29 | 9996394 | 0 | 0 | 0 | 9996394 | 0 | 0 | 0 | 0 | 0 | 9996394 | 0 | 0 | 0 | 9996394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9996394 | 0 | 0 | 0 | 9996394
556 | ** | BOILER FEED PUMP | NL-N-TS2-002-08-02 | 84478023.56 | 21120593.94 | 57653423.87 | 78774017.81 | 5704005.75 | 13934006.71 | 13935098.59 | 0 | 13935098.59 | -1091.88 | 70544016.85 | 7185495.35 | 57653423.87 | 64838919.22 | 5705097.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84478023.56 | 21120593.94 | 57653423.87 | 78774017.81 | 5704005.75
557 | * | catridge with barrel | NL-N-TS2-002-08-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
558 | * | CWP impellers & brg | NL-N-TS2-002-08-02-02 | 3442521.36 | 3442521.36 | 0 | 3442521.36 | 0 | 3442521.36 | 3442521.36 | 0 | 3442521.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3442521.36 | 3442521.36 | 0 | 3442521.36 | 0
559 | * | CEP replacement | NL-N-TS2-002-08-02-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
560 | * | Mechanical seal cart | NL-N-TS2-002-08-02-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
561 | * | Mechanical seal coolers kit | NL-N-TS2-002-08-02-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
562 | * | Booster pump brgs & housings | NL-N-TS2-002-08-02-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
563 | * | BFP WOC & LOC tubes stack | NL-N-TS2-002-08-02-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
564 | * | BFP WOC chamber fabrication | NL-N-TS2-002-08-02-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
565 | * | CWP impellers & bearings | NL-N-TS2-002-08-02-09 | 3280819.79 | 3280819.79 | 0 | 3280819.79 | 0 | 3280819.79 | 3280819.79 | 0 | 3280819.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3280819.79 | 3280819.79 | 0 | 3280819.79 | 0
566 | * | CWP REJ | NL-N-TS2-002-08-02-10 | 1979568 | 0 | 1979568 | 1979568 | 0 | 0 | 0 | 0 | 0 | 0 | 1979568 | 0 | 1979568 | 1979568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1979568 | 0 | 1979568 | 1979568 | 0
567 | * | CWP VALVES | NL-N-TS2-002-08-02-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
568 | * | CWP EOT crane replacement | NL-N-TS2-002-08-02-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
569 | * | Chlorination plant valves replacement | NL-N-TS2-002-08-02-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
570 | * | CWP suction filters replacement | NL-N-TS2-002-08-02-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
571 | * | BFP coupling assembly | NL-N-TS2-002-08-02-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
572 | * | BFP & Booster Pumps Spares | NL-N-TS2-002-08-02-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
573 | * | Hydrocoupling replacement | NL-N-TS2-002-08-02-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
574 | * | BRP bed replacement & assembly | NL-N-TS2-002-08-02-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
575 | * | Chlorination Plant Spares | NL-N-TS2-002-08-02-20 | 817691.02 | 817691.02 | 0 | 817691.02 | 0 | 817691.02 | 817691.02 | 0 | 817691.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 817691.02 | 817691.02 | 0 | 817691.02 | 0
576 | * | BFP Wear rings for stage-1&2 | NL-N-TS2-002-08-02-21 | 1123452.6 | 0 | 1123452.6 | 1123452.6 | 0 | 0 | 0 | 0 | 0 | 0 | 1123452.6 | 0 | 1123452.6 | 1123452.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123452.6 | 0 | 1123452.6 | 1123452.6 | 0
577 | * | Boiler Feed Pump Wear Rings Stage-I | NL-N-TS2-002-08-02-23 | 602615.77 | 353248.38 | 249367.39 | 602615.77 | 0 | 353248.38 | 353248.38 | 0 | 353248.38 | 0 | 249367.39 | 0 | 249367.39 | 249367.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602615.77 | 353248.38 | 249367.39 | 602615.77 | 0
578 | * | Condensate Extraction Pump Spares | NL-N-TS2-002-08-02-24 | 4102538.4 | 0 | 4102538.4 | 4102538.4 | 0 | 0 | 0 | 0 | 0 | 0 | 4102538.4 | 0 | 4102538.4 | 4102538.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4102538.4 | 0 | 4102538.4 | 4102538.4 | 0
579 | * | Spares for BFP 6WC-137/C Mech seal st-I | NL-N-TS2-002-08-02-25 | 2325187.36 | 2325187.36 | 0 | 2325187.36 | 0 | 2325187.36 | 2325187.36 | 0 | 2325187.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2325187.36 | 2325187.36 | 0 | 2325187.36 | 0
580 | * | Spares for BFP FK6D30 Mech Seal Stage-II | NL-N-TS2-002-08-02-26 | 2373599.1 | 2374296.82 | 0 | 2374296.82 | -697.72 | 2373599.1 | 2374296.82 | 0 | 2374296.82 | -697.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2373599.1 | 2374296.82 | 0 | 2374296.82 | -697.72
581 | * | Spares for st-I BFP Shaft Type-6WC 137/C | NL-N-TS2-002-08-02-27 | 2725338.28 | 2726139.34 | 0 | 2726139.34 | -801.06 | 0 | 0 | 0 | 0 | 0 | 2725338.28 | 2726139.34 | 0 | 2726139.34 | -801.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2725338.28 | 2726139.34 | 0 | 2726139.34 | -801.06
582 | * | Spares for BFP Thrust Collar Spring O ri | NL-N-TS2-002-08-02-28 | 2236909.74 | 1341333.86 | 895970.04 | 2237303.9 | -394.16 | 1340939.7 | 1341333.86 | 0 | 1341333.86 | -394.16 | 895970.04 | 0 | 895970.04 | 895970.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2236909.74 | 1341333.86 | 895970.04 | 2237303.9 | -394.16
583 | * | BFP Type 6WC 137/C "C" Ring | NL-N-TS2-002-08-02-29 | 4459356.01 | 4459356.01 | 0 | 4459356.01 | 0 | 0 | 0 | 0 | 0 | 0 | 4459356.01 | 4459356.01 | 0 | 4459356.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4459356.01 | 4459356.01 | 0 | 4459356.01 | 0
584 | * | BFP Mech seals Spares for St-II Eagle ma | NL-N-TS2-002-08-02-30 | 2470008 | 0 | 2423246.95 | 2423246.95 | 46761.05 | 0 | 0 | 0 | 0 | 0 | 2470008 | 0 | 2423246.95 | 2423246.95 | 46761.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2470008 | 0 | 2423246.95 | 2423246.95 | 46761.05
585 | * | Duplex Filter for Stage-2 CWP | NL-N-TS2-002-08-02-31 | 605837.29 | 0 | 605837.29 | 605837.29 | 0 | 0 | 0 | 0 | 0 | 0 | 605837.29 | 0 | 605837.29 | 605837.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605837.29 | 0 | 605837.29 | 605837.29 | 0
586 | * | BFP TYPE FK 6D 30 IMPELLER STG-2 | NL-N-TS2-002-08-02-32 | 1248118.08 | 0 | 1248118.08 | 1248118.08 | 0 | 0 | 0 | 0 | 0 | 0 | 1248118.08 | 0 | 1248118.08 | 1248118.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1248118.08 | 0 | 1248118.08 | 1248118.08 | 0
587 | * | BFP type FK 6D 30 Diffusers and Diapharm | NL-N-TS2-002-08-02-33 | 1272173.35 | 0 | 1272173.35 | 1272173.35 | 0 | 0 | 0 | 0 | 0 | 0 | 1272173.35 | 0 | 1272173.35 | 1272173.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1272173.35 | 0 | 1272173.35 | 1272173.35 | 0
588 | * | BRG Bracket/Lantern ring-Booster pump | NL-N-TS2-002-08-02-34 | 2385597.52 | 0 | 2385597.52 | 2385597.52 | 0 | 0 | 0 | 0 | 0 | 0 | 2385597.52 | 0 | 2385597.52 | 2385597.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2385597.52 | 0 | 2385597.52 | 2385597.52 | 0
589 | * | WOC/LOC stack assembly | NL-N-TS2-002-08-02-35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
590 | * | Spare for BFP working oil cooler tube | NL-N-TS2-002-08-02-36 | 3874428 | 0 | 3874428 | 3874428 | 0 | 0 | 0 | 0 | 0 | 0 | 3874428 | 0 | 3874428 | 3874428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3874428 | 0 | 3874428 | 3874428 | 0
591 | * | Finostos B Bearing as per Dimension | NL-N-TS2-002-08-02-37 | 1962468 | 0 | 1962468 | 1962468 | 0 | 0 | 0 | 0 | 0 | 0 | 1962468 | 0 | 1962468 | 1962468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1962468 | 0 | 1962468 | 1962468 | 0
592 | * | Providing energy efficient coating CWP | NL-N-TS2-002-08-02-38 | 1374750.01 | 0 | 1374750.01 | 1374750.01 | 0 | 0 | 0 | 0 | 0 | 0 | 1374750.01 | 0 | 1374750.01 | 1374750.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1374750.01 | 0 | 1374750.01 | 1374750.01 | 0
593 | * | Impeller Shaft and Top Shaft for CWP | NL-N-TS2-002-08-02-39 | 5982424.2 | 0 | 5982424.2 | 5982424.2 | 0 | 0 | 0 | 0 | 0 | 0 | 5982424.2 | 0 | 5982424.2 | 5982424.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5982424.2 | 0 | 5982424.2 | 5982424.2 | 0
594 | * | SPARES FOR BFP TYPE FK6D30 | NL-N-TS2-002-08-02-40 | 2487253.56 | 0 | 2487253.56 | 2487253.56 | 0 | 0 | 0 | 0 | 0 | 0 | 2487253.56 | 0 | 2487253.56 | 2487253.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2487253.56 | 0 | 2487253.56 | 2487253.56 | 0
595 | * | Rotor assembly of BFP Booster pump St-I | NL-N-TS2-002-08-02-41 | 6709433 | 0 | 6710525 | 6710525 | -1092 | 0 | 0 | 0 | 0 | 0 | 6709433 | 0 | 6710525 | 6710525 | -1092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6709433 | 0 | 6710525 | 6710525 | -1092
596 | * | Complete set of BFP Booster pump | NL-N-TS2-002-08-02-42 | 10083511.64 | 0 | 10084680 | 10084680 | -1168.36 | 0 | 0 | 0 | 0 | 0 | 10083511.64 | 0 | 10084680 | 10084680 | -1168.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10083511.64 | 0 | 10084680 | 10084680 | -1168.36
597 | * | Feed Pump Recirculation Valve | NL-N-TS2-002-08-02-43 | 8891025.48 | 0 | 8891025.48 | 8891025.48 | 0 | 0 | 0 | 0 | 0 | 0 | 8891025.48 | 0 | 8891025.48 | 8891025.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8891025.48 | 0 | 8891025.48 | 8891025.48 | 0
598 | * | BEARINGS FOR HYDROCOUPLINGS OF BFP | NL-N-TS2-002-08-02-44 | 5661398 | 0 | 0 | 0 | 5661398 | 0 | 0 | 0 | 0 | 0 | 5661398 | 0 | 0 | 0 | 5661398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5661398 | 0 | 0 | 0 | 5661398
599 | ** | PIPING & VALVES | NL-N-TS2-002-08-03 | 26993629.15 | 885454.55 | 25918250.71 | 26803705.26 | 189923.89 | 885454.55 | 885454.55 | 0 | 885454.55 | 0 | 26108174.6 | 0 | 25918250.71 | 25918250.71 | 189923.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26993629.15 | 885454.55 | 25918250.71 | 26803705.26 | 189923.89
600 | * | Hand operated valves | NL-N-TS2-002-08-03-01 | 56050 | 56050 | 0 | 56050 | 0 | 56050 | 56050 | 0 | 56050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56050 | 56050 | 0 | 56050 | 0
601 | * | MOV | NL-N-TS2-002-08-03-02 | 418923.6 | 418923.6 | 0 | 418923.6 | 0 | 418923.6 | 418923.6 | 0 | 418923.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418923.6 | 418923.6 | 0 | 418923.6 | 0
602 | * | PCV | NL-N-TS2-002-08-03-03 | 350861.68 | 350861.68 | 0 | 350861.68 | 0 | 350861.68 | 350861.68 | 0 | 350861.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350861.68 | 350861.68 | 0 | 350861.68 | 0
603 | * | RC valves replacement | NL-N-TS2-002-08-03-04 | 4228518.6 | 0 | 4038594.71 | 4038594.71 | 189923.89 | 0 | 0 | 0 | 0 | 0 | 4228518.6 | 0 | 4038594.71 | 4038594.71 | 189923.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4228518.6 | 0 | 4038594.71 | 4038594.71 | 189923.89
604 | * | NRV | NL-N-TS2-002-08-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
605 | * | Pipes | NL-N-TS2-002-08-03-06 | 1586164.27 | 59619.27 | 1526545 | 1586164.27 | 0 | 59619.27 | 59619.27 | 0 | 59619.27 | 0 | 1526545 | 0 | 1526545 | 1526545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1586164.27 | 59619.27 | 1526545 | 1586164.27 | 0
606 | * | SV replacement | NL-N-TS2-002-08-03-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
607 | * | Bore Well Pipes Replacement | NL-N-TS2-002-08-03-08 | 10400460 | 0 | 10400460 | 10400460 | 0 | 0 | 0 | 0 | 0 | 0 | 10400460 | 0 | 10400460 | 10400460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10400460 | 0 | 10400460 | 10400460 | 0
608 | * | Purchase of pressure seal gaskets for HP | NL-N-TS2-002-08-03-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
609 | * | MAL Valves | NL-N-TS2-002-08-03-10 | 4353531 | 0 | 4353531 | 4353531 | 0 | 0 | 0 | 0 | 0 | 0 | 4353531 | 0 | 4353531 | 4353531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4353531 | 0 | 4353531 | 4353531 | 0
610 | * | LP by pass Limiting regulator | NL-N-TS2-002-08-03-11 | 5599120 | 0 | 5599120 | 5599120 | 0 | 0 | 0 | 0 | 0 | 0 | 5599120 | 0 | 5599120 | 5599120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5599120 | 0 | 5599120 | 5599120 | 0
611 | * | LP by pass Governing system spare parts | NL-N-TS2-002-08-03-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
612 | ** | AC PLANT | NL-N-TS2-002-08-04 | 15707981.09 | 7675957.54 | 6149923.33 | 13825880.87 | 1882100.22 | 7674870.64 | 7675957.54 | 1651044 | 9327001.54 | -1652130.9 | 8033110.45 | 0 | 4498879.33 | 4498879.33 | 3534231.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15707981.09 | 7675957.54 | 6149923.33 | 13825880.87 | 1882100.22
613 | * | KC6 compressor replacement | NL-N-TS2-002-08-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
614 | * | AC Plant Pumps Spares | NL-N-TS2-002-08-04-02 | 4684911.55 | 3698448.94 | 987549.51 | 4685998.45 | -1086.9 | 3697362.04 | 3698448.94 | 0 | 3698448.94 | -1086.9 | 987549.51 | 0 | 987549.51 | 987549.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4684911.55 | 3698448.94 | 987549.51 | 4685998.45 | -1086.9
615 | * | Air washer replacement | NL-N-TS2-002-08-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
616 | * | Accel 4-100 compressor replacement | NL-N-TS2-002-08-04-04 | 1669586.52 | 0 | 1651044 | 1651044 | 18542.52 | 0 | 0 | 1651044 | 1651044 | -1651044 | 1669586.52 | 0 | 0 | 0 | 1669586.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669586.52 | 0 | 1651044 | 1651044 | 18542.52
617 | * | Accel 6-100 compressor replacement | NL-N-TS2-002-08-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
618 | * | Beacon weir pump replacement | NL-N-TS2-002-08-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
619 | * | Air washer unit replacement | NL-N-TS2-002-08-04-07 | 2980261.13 | 2980261.1 | 0.03 | 2980261.13 | 0 | 2980261.1 | 2980261.1 | 0 | 2980261.1 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2980261.13 | 2980261.1 | 0.03 | 2980261.13 | 0
620 | * | Kirloskar make KC6 Compressor spares | NL-N-TS2-002-08-04-08 | 666847.5 | 666847.5 | 0 | 666847.5 | 0 | 666847.5 | 666847.5 | 0 | 666847.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 666847.5 | 666847.5 | 0 | 666847.5 | 0
621 | * | Rep of Unit-2 Air washer Pre Suc Filter | NL-N-TS2-002-08-04-09 | 370400 | 330400 | 40000 | 370400 | 0 | 330400 | 330400 | 0 | 330400 | 0 | 40000 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370400 | 330400 | 40000 | 370400 | 0
622 | * | AC plant St-II Beacon weir pump spares | NL-N-TS2-002-08-04-10 | 3471329.79 | 0 | 3471329.79 | 3471329.79 | 0 | 0 | 0 | 0 | 0 | 0 | 3471329.79 | 0 | 3471329.79 | 3471329.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3471329.79 | 0 | 3471329.79 | 3471329.79 | 0
623 | * | AC Plant Vee Groove Pulley | NL-N-TS2-002-08-04-11 | 1864644.6 | 0 | 0 | 0 | 1864644.6 | 0 | 0 | 0 | 0 | 0 | 1864644.6 | 0 | 0 | 0 | 1864644.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864644.6 | 0 | 0 | 0 | 1864644.6
624 | ** | MAIN TURBINE CONTRACTS | NL-N-TS2-002-08-05 | 146627607.73 | 104563880.54 | 41797224.42 | 146361104.96 | 266502.77 | 102757843.34 | 102757843.34 | 0.03 | 102757843.37 | -0.03 | 43869764.39 | 1806037.2 | 41797224.39 | 43603261.59 | 266502.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146627607.73 | 104563880.54 | 41797224.42 | 146361104.96 | 266502.77
625 | * | LEP Works : U-4 | NL-N-TS2-002-08-05-01 | 21122000 | 19059360 | 2062640 | 21122000 | 0 | 19059360 | 19059360 | 0 | 19059360 | 0 | 2062640 | 0 | 2062640 | 2062640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21122000 | 19059360 | 2062640 | 21122000 | 0
626 | * | U-4 CONDITION ASSESSMENT | NL-N-TS2-002-08-05-02 | 2891000 | 2891000 | 0 | 2891000 | 0 | 2891000 | 2891000 | 0 | 2891000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2891000 | 2891000 | 0 | 2891000 | 0
627 | * | U-2 WORKS CONTRACTS | NL-N-TS2-002-08-05-03 | 83622309.67 | 76702121.77 | 6920187.9 | 83622309.67 | 0 | 76702121.77 | 76702121.77 | 0 | 76702121.77 | 0 | 6920187.9 | 0 | 6920187.9 | 6920187.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83622309.67 | 76702121.77 | 6920187.9 | 83622309.67 | 0
628 | * | U-2 CONDITION ASSESSMENT | NL-N-TS2-002-08-05-04 | 1412460.02 | 1355961.6 | 56498.42 | 1412460.02 | 0 | 1355961.6 | 1355961.6 | 0 | 1355961.6 | 0 | 56498.42 | 0 | 56498.42 | 56498.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1412460.02 | 1355961.6 | 56498.42 | 1412460.02 | 0
629 | * | U-2 INSULATION CONTRACT | NL-N-TS2-002-08-05-05 | 1274400.03 | 1274400 | 0.03 | 1274400.03 | 0 | 1274400 | 1274400 | 0 | 1274400 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1274400.03 | 1274400 | 0.03 | 1274400.03 | 0
630 | * | ESP cooling tower supply & erection | NL-N-TS2-002-08-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
631 | * | Unit-4 Insulation Work | NL-N-TS2-002-08-05-07 | 1474999.98 | 1474999.97 | 0.01 | 1474999.98 | 0 | 1474999.97 | 1474999.97 | 0 | 1474999.97 | 0 | 0.01 | 0 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1474999.98 | 1474999.97 | 0.01 | 1474999.98 | 0
632 | * | LEP works Unit-6 | NL-N-TS2-002-08-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
633 | * | Unit-6 Condition assesment | NL-N-TS2-002-08-05-09 | 2699900.01 | 0 | 2699900.01 | 2699900.01 | 0 | 0 | 0 | 0 | 0 | 0 | 2699900.01 | 0 | 2699900.01 | 2699900.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2699900.01 | 0 | 2699900.01 | 2699900.01 | 0
634 | * | Unit-6 Insulation contract | NL-N-TS2-002-08-05-10 | 1728700.01 | 0 | 1465000.01 | 1465000.01 | 263700 | 0 | 0 | 0 | 0 | 0 | 1728700.01 | 0 | 1465000.01 | 1465000.01 | 263700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1728700.01 | 0 | 1465000.01 | 1465000.01 | 263700
635 | * | Unit-1 Works Contract | NL-N-TS2-002-08-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
636 | * | Unit-1 condition assesment | NL-N-TS2-002-08-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
637 | * | Unit-1 Insulation contract | NL-N-TS2-002-08-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
638 | * | Stage-II ducts replacement | NL-N-TS2-002-08-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
639 | * | HP By pass spares-reconditioning contrac | NL-N-TS2-002-08-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
640 | * | CWP Suction filters replacement | NL-N-TS2-002-08-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
641 | * | Hydrocoupling replacement | NL-N-TS2-002-08-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
642 | * | U-6 Turbine Capital Overhaul | NL-N-TS2-002-08-05-18 | 28577538.01 | 0 | 28577538.01 | 28577538.01 | 0 | 0 | 0 | 0 | 0 | 0 | 28577538.01 | 0 | 28577538.01 | 28577538.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28577538.01 | 0 | 28577538.01 | 28577538.01 | 0
643 | * | Duromar coating on condenser Tube sheet | NL-N-TS2-002-08-05-19 | 1824300 | 1806037.2 | 15460.03 | 1821497.23 | 2802.77 | 0 | 0 | 0.03 | 0.03 | -0.03 | 1824300 | 1806037.2 | 15460 | 1821497.2 | 2802.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1824300 | 1806037.2 | 15460.03 | 1821497.23 | 2802.77
644 | ** | Turbine Miscelaneous | NL-N-TS2-002-08-07 | 1559880 | 0 | 1556433.64 | 1556433.64 | 3446.36 | 0 | 0 | 0 | 0 | 0 | 1559880 | 0 | 1556433.64 | 1556433.64 | 3446.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559880 | 0 | 1556433.64 | 1556433.64 | 3446.36
645 | * | Purchase of Mukund Crane Spares | NL-N-TS2-002-08-07-01 | 1559880 | 0 | 1556433.64 | 1556433.64 | 3446.36 | 0 | 0 | 0 | 0 | 0 | 1559880 | 0 | 1556433.64 | 1556433.64 | 3446.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559880 | 0 | 1556433.64 | 1556433.64 | 3446.36
646 | ** | Ciculating Water Pump | NL-N-TS2-002-08-08 | 17101357 | 0 | 3711903 | 3711903 | 13389454 | 0 | 0 | 0 | 0 | 0 | 17101357 | 0 | 3711903 | 3711903 | 13389454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17101357 | 0 | 3711903 | 3711903 | 13389454
647 | * | Impeller for Mather &Plate Make CWP | NL-N-TS2-002-08-08-01 | 3711903 | 0 | 3711903 | 3711903 | 0 | 0 | 0 | 0 | 0 | 0 | 3711903 | 0 | 3711903 | 3711903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3711903 | 0 | 3711903 | 3711903 | 0
648 | * | Line shaft and Intermediat shaft for CWP | NL-N-TS2-002-08-08-02 | 13389454 | 0 | 0 | 0 | 13389454 | 0 | 0 | 0 | 0 | 0 | 13389454 | 0 | 0 | 0 | 13389454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13389454 | 0 | 0 | 0 | 13389454
649 | *** | WCTP | NL-N-TS2-002-09 | 153379089.13 | 140672714.41 | 12706374.72 | 153379089.13 | 0 | 140672714.41 | 140672714.41 | 0 | 140672714.41 | 0 | 12706374.72 | 0 | 12706374.72 | 12706374.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153379089.13 | 140672714.41 | 12706374.72 | 153379089.13 | 0
650 | ** | UV Spectrophotometer | NL-N-TS2-002-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
651 | ** | Portable Dissolved Oxygen Analyser | NL-N-TS2-002-09-02 | 612017.6 | 612017.6 | 0 | 612017.6 | 0 | 612017.6 | 612017.6 | 0 | 612017.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612017.6 | 612017.6 | 0 | 612017.6 | 0
652 | ** | CW Treatment System for Higher COC | NL-N-TS2-002-09-03 | 151508431.53 | 140060696.81 | 11447734.72 | 151508431.53 | 0 | 140060696.81 | 140060696.81 | 0 | 140060696.81 | 0 | 11447734.72 | 0 | 11447734.72 | 11447734.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151508431.53 | 140060696.81 | 11447734.72 | 151508431.53 | 0
653 | ** | UV-VISIBLE SPECTROMETER | NL-N-TS2-002-09-04 | 1258640 | 0 | 1258640 | 1258640 | 0 | 0 | 0 | 0 | 0 | 0 | 1258640 | 0 | 1258640 | 1258640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258640 | 0 | 1258640 | 1258640 | 0
654 | *** | COMPUTER | NL-N-TS2-002-10 | 10708536.92 | 10683536.92 | 25000 | 10708536.92 | 0 | 10683536.92 | 10683536.92 | 0 | 10683536.92 | 0 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10708536.92 | 10683536.92 | 25000 | 10708536.92 | 0
655 | ** | Simulator for PSTC | NL-N-TS2-002-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
656 | ** | CCTV & Network for Watch Tower | NL-N-TS2-002-10-02 | 2527725.2 | 2527725.2 | 0 | 2527725.2 | 0 | 2527725.2 | 2527725.2 | 0 | 2527725.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2527725.2 | 2527725.2 | 0 | 2527725.2 | 0
657 | ** | CCTV Network System for Peripheral area | NL-N-TS2-002-10-03 | 8180811.72 | 8155811.72 | 25000 | 8180811.72 | 0 | 8155811.72 | 8155811.72 | 0 | 8155811.72 | 0 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8180811.72 | 8155811.72 | 25000 | 8180811.72 | 0
658 | ** | CCTV Network in Plant Area | NL-N-TS2-002-10-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
659 | ** | Phase-III -Proposal for the STWC OF CCTV | NL-N-TS2-002-10-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
660 | *** | PLANNING & TECHNICAL | NL-N-TS2-002-11 | 15418517.79 | 2575734.34 | 10982783.45 | 13558517.79 | 1860000 | 2575734.34 | 2575734.34 | 0 | 2575734.34 | 0 | 12842783.45 | 0 | 10982783.45 | 10982783.45 | 1860000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15418517.79 | 2575734.34 | 10982783.45 | 13558517.79 | 1860000
661 | ** | Study of MoEF Norms for FGD & WC Project | NL-N-TS2-002-11-01 | 3467810.79 | 2575734.34 | 892076.45 | 3467810.79 | 0 | 2575734.34 | 2575734.34 | 0 | 2575734.34 | 0 | 892076.45 | 0 | 892076.45 | 892076.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3467810.79 | 2575734.34 | 892076.45 | 3467810.79 | 0
662 | ** | Special Purpose Vehicle Mounted De-silt | NL-N-TS2-002-11-02 | 11950707 | 0 | 10090707 | 10090707 | 1860000 | 0 | 0 | 0 | 0 | 0 | 11950707 | 0 | 10090707 | 10090707 | 1860000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11950707 | 0 | 10090707 | 10090707 | 1860000
663 | *** | BOILER AUXILLARY MAINTENANCE | NL-N-TS2-002-12 | 9273996.56 | 3395568.19 | 5877752.64 | 9273320.83 | 675.73 | 2472329.76 | 2472329.76 | 0 | 2472329.76 | 0 | 6801666.8 | 923238.43 | 5877752.64 | 6800991.07 | 675.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9273996.56 | 3395568.19 | 5877752.64 | 9273320.83 | 675.73
664 | ** | FIRE PROTECTION SYSTEM | NL-N-TS2-002-12-01 | 4225353.36 | 1082677.2 | 3142000.43 | 4224677.63 | 675.73 | 1082677.2 | 1082677.2 | 0 | 1082677.2 | 0 | 3142676.16 | 0 | 3142000.43 | 3142000.43 | 675.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4225353.36 | 1082677.2 | 3142000.43 | 4224677.63 | 675.73
665 | * | AMVWSS for bunker conveyor system | NL-N-TS2-002-12-01-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
666 | * | Clean agent FSS fire suppresion system | NL-N-TS2-002-12-01-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
667 | * | 9 Ltr Mechanical Foam fire extingushers | NL-N-TS2-002-12-01-06 | 376998.2 | 376998.2 | 0 | 376998.2 | 0 | 376998.2 | 376998.2 | 0 | 376998.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376998.2 | 376998.2 | 0 | 376998.2 | 0
668 | * | 4 Ton capacity Battery Platform trolley | NL-N-TS2-002-12-01-07 | 705679 | 705679 | 0 | 705679 | 0 | 705679 | 705679 | 0 | 705679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705679 | 705679 | 0 | 705679 | 0
669 | * | Procurement of Dry Chemical Powder fire | NL-N-TS2-002-12-01-08 | 185000.4 | 0 | 185000.4 | 185000.4 | 0 | 0 | 0 | 0 | 0 | 0 | 185000.4 | 0 | 185000.4 | 185000.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000.4 | 0 | 185000.4 | 185000.4 | 0
670 | * | Procurement of Fire water Booster pump | NL-N-TS2-002-12-01-09 | 891555.06 | 0 | 891000.01 | 891000.01 | 555.05 | 0 | 0 | 0 | 0 | 0 | 891555.06 | 0 | 891000.01 | 891000.01 | 555.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 891555.06 | 0 | 891000.01 | 891000.01 | 555.05
671 | * | Procure of Pump/Motor Coupling for FWP | NL-N-TS2-002-12-01-10 | 20120.7 | 0 | 20000.02 | 20000.02 | 120.68 | 0 | 0 | 0 | 0 | 0 | 20120.7 | 0 | 20000.02 | 20000.02 | 120.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20120.7 | 0 | 20000.02 | 20000.02 | 120.68
672 | * | Procure of 22 Tons of 150 NB ERW Pipe | NL-N-TS2-002-12-01-11 | 2046000 | 0 | 2046000 | 2046000 | 0 | 0 | 0 | 0 | 0 | 0 | 2046000 | 0 | 2046000 | 2046000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2046000 | 0 | 2046000 | 2046000 | 0
673 | ** | MECHANICAL MAINTENANCE | NL-N-TS2-002-12-02 | 5048643.2 | 2312890.99 | 2735752.21 | 5048643.2 | 0 | 1389652.56 | 1389652.56 | 0 | 1389652.56 | 0 | 3658990.64 | 923238.43 | 2735752.21 | 3658990.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5048643.2 | 2312890.99 | 2735752.21 | 5048643.2 | 0
674 | * | Replace the ST-II DG set Cooling Towers | NL-N-TS2-002-12-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
675 | * | Pipe for Borewell-G to CWPH Stage-I | NL-N-TS2-002-12-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
676 | * | N2H4 Dozing Pump for Stage-II | NL-N-TS2-002-12-02-03 | 357999.97 | 357999.97 | 0 | 357999.97 | 0 | 357999.97 | 357999.97 | 0 | 357999.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357999.97 | 357999.97 | 0 | 357999.97 | 0
677 | * | MSRL Pipes and Fittings | NL-N-TS2-002-12-02-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
678 | * | Replace the ST-I DG set Cooling Towers | NL-N-TS2-002-12-02-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
679 | * | ACWBP Replacement in Stage-I/Unit | NL-N-TS2-002-12-02-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
680 | * | Battery Operated Platform Trolley 2 Ton | NL-N-TS2-002-12-02-08 | 1031652.59 | 1031652.59 | 0 | 1031652.59 | 0 | 1031652.59 | 1031652.59 | 0 | 1031652.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1031652.59 | 1031652.59 | 0 | 1031652.59 | 0
681 | * | Phospate dozing Pump &Check valve assemb | NL-N-TS2-002-12-02-09 | 923238.43 | 923238.43 | 0 | 923238.43 | 0 | 0 | 0 | 0 | 0 | 0 | 923238.43 | 923238.43 | 0 | 923238.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 923238.43 | 923238.43 | 0 | 923238.43 | 0
682 | * | dECANTING SUMP BARE PUMP INCLUDING BASE | NL-N-TS2-002-12-02-10 | 258000.01 | 0 | 258000.01 | 258000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 258000.01 | 0 | 258000.01 | 258000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258000.01 | 0 | 258000.01 | 258000.01 | 0
683 | * | Degassed water pump assembly w/o motor | NL-N-TS2-002-12-02-11 | 2477752.2 | 0 | 2477752.2 | 2477752.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2477752.2 | 0 | 2477752.2 | 2477752.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2477752.2 | 0 | 2477752.2 | 2477752.2 | 0
684 | ** | WORKSHOP AND COMPRESSOR MAINTENANCE | NL-N-TS2-002-12-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
685 | * | Supply,Erect&Commission of 2 Compressors | NL-N-TS2-002-12-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
686 | *** | BOILER OPERATION SERVICES | NL-N-TS2-002-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0