## Sheet1
Sl | WBS_Elements_Info. |  |  | Total of years |  |  |  |  | Previous years |  |  |  |  | 2025 |  |  |  |  | 2026 |  |  |  |  | 2027 |  |  |  |  | 2028 and Following |  |  |  |  | Overall values
No. | Level | Description | ID_No | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available | Budget | Actual | Commitment | Assigned | Available
0 | 5* | TPS-II LEP Stage I & II Non Plan CAPEX | NL-N-TS2-002 | 6869461119.73 | 2877803714.97 | 3372380385.67 | 6250194821.63 | 619266298.1 | 2820744957.79 | 2811734033.52 | 0 | 2811744754.51 | 9000203.28 | 4048716161.94 | 66069681.45 | 3354169422.19 | 3420239103.64 | 628477058.3 | 0 | 0 | 18210963.48 | 18210963.48 | -18210963.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6869461119.73 | 2877803714.97 | 3372380385.67 | 6250194821.63 | 619266298.1
1 | 4* | TPS-II LEP Stage I & II Non Plan CAPEX | NL-N-TS2-002 | 6869461119.73 | 2877803714.97 | 3372380385.67 | 6250194821.63 | 619266298.1 | 2820744957.79 | 2811734033.52 | 0 | 2811744754.51 | 9000203.28 | 4048716161.94 | 66069681.45 | 3354169422.19 | 3420239103.64 | 628477058.3 | 0 | 0 | 18210963.48 | 18210963.48 | -18210963.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6869461119.73 | 2877803714.97 | 3372380385.67 | 6250194821.63 | 619266298.1
2 | *** | AHS | NL-N-TS2-002-01 | 225199259.95 | 58360292.44 | 166838967.51 | 225199259.95 | 0 | 57148332.38 | 57148332.38 | 0 | 57148332.38 | 0 | 168050927.57 | 1211960.06 | 166838967.51 | 168050927.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225199259.95 | 58360292.44 | 166838967.51 | 225199259.95 | 0
3 | ** | ESP-UNIT-2 | NL-N-TS2-002-01-01 | 22310264.97 | 22310264.97 | 0 | 22310264.97 | 0 | 22310264.97 | 22310264.97 | 0 | 22310264.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22310264.97 | 22310264.97 | 0 | 22310264.97 | 0
4 | ** | CS Seamless pipe size 8 &10 inch | NL-N-TS2-002-01-03 | 11370400 | 11361324.16 | 9075.84 | 11370400 | 0 | 11361324.16 | 11361324.16 | 0 | 11361324.16 | 0 | 9075.84 | 0 | 9075.84 | 9075.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11370400 | 11361324.16 | 9075.84 | 11370400 | 0
5 | ** | Purchase of ceramic lined fittings&pipes | NL-N-TS2-002-01-04 | 2150544.69 | 2150544.69 | 0 | 2150544.69 | 0 | 2150544.69 | 2150544.69 | 0 | 2150544.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2150544.69 | 2150544.69 | 0 | 2150544.69 | 0
6 | ** | GS Plain Grating for ESP | NL-N-TS2-002-01-05 | 6515074.25 | 0 | 6515074.25 | 6515074.25 | 0 | 0 | 0 | 0 | 0 | 0 | 6515074.25 | 0 | 6515074.25 | 6515074.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6515074.25 | 0 | 6515074.25 | 6515074.25 | 0
7 | ** | Air BLOCK 1ST STAGE COVN AIR COMPRESSOR | NL-N-TS2-002-01-06 | 8979800 | 8979800 | 0 | 8979800 | 0 | 8979800 | 8979800 | 0 | 8979800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8979800 | 8979800 | 0 | 8979800 | 0
8 | ** | Air Block 1st &2nd stage for compressor | NL-N-TS2-002-01-08 | 8920800 | 8920800 | 0 | 8920800 | 0 | 8920800 | 8920800 | 0 | 8920800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8920800 | 8920800 | 0 | 8920800 | 0
9 | ** | Purchase of Ash inlet Cup valves in DAS | NL-N-TS2-002-01-09 | 3425598.56 | 3425598.56 | 0 | 3425598.56 | 0 | 3425598.56 | 3425598.56 | 0 | 3425598.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3425598.56 | 3425598.56 | 0 | 3425598.56 | 0
10 | ** | Purchase of ceramic lined bends & Spool | NL-N-TS2-002-01-10 | 1211960.06 | 1211960.06 | 0 | 1211960.06 | 0 | 0 | 0 | 0 | 0 | 0 | 1211960.06 | 1211960.06 | 0 | 1211960.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1211960.06 | 1211960.06 | 0 | 1211960.06 | 0
11 | ** | CSS Pipe 8/10 Inch ASTM A106 | NL-N-TS2-002-01-12 | 43980500 | 0 | 43980500 | 43980500 | 0 | 0 | 0 | 0 | 0 | 0 | 43980500 | 0 | 43980500 | 43980500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43980500 | 0 | 43980500 | 43980500 | 0
12 | ** | ASH INLET CUPVALVE ASSEMBLY WITH ACTUATO | NL-N-TS2-002-01-14 | 51357384.96 | 0 | 51357384.96 | 51357384.96 | 0 | 0 | 0 | 0 | 0 | 0 | 51357384.96 | 0 | 51357384.96 | 51357384.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51357384.96 | 0 | 51357384.96 | 51357384.96 | 0
13 | ** |  | NL-N-TS2-002-01-15 | 64976932.46 | 0 | 64976932.46 | 64976932.46 | 0 | 0 | 0 | 0 | 0 | 0 | 64976932.46 | 0 | 64976932.46 | 64976932.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64976932.46 | 0 | 64976932.46 | 64976932.46 | 0
14 | *** | CIVIL | NL-N-TS2-002-02 | 348487074.78 | 194950981.41 | 152705548.01 | 347656529.42 | 830545.36 | 201676531.12 | 200652881.13 | 0 | 200652881.13 | 1023649.99 | 146810543.66 | -5701899.72 | 152705548.01 | 147003648.29 | -193104.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348591261.69 | 194950981.41 | 152705548.01 | 347656529.42 | 934732.27
15 | ** | Rehabilitation works to CT-2 inside | NL-N-TS2-002-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | ** | Rehabilitation works to CT-5 outside | NL-N-TS2-002-02-02 | 18780348.93 | 18780348.93 | 0 | 18780348.93 | 0 | 18780348.93 | 18780348.93 | 0 | 18780348.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18780348.93 | 18780348.93 | 0 | 18780348.93 | 0
17 | ** | Water Proofing works to Main Building | NL-N-TS2-002-02-05 | 8872831.53 | 6281602.89 | 2566884.2 | 8848487.09 | 24344.44 | 6305947.33 | 6281602.89 | 0 | 6281602.89 | 24344.44 | 2566884.2 | 0 | 2566884.2 | 2566884.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8872831.53 | 6281602.89 | 2566884.2 | 8848487.09 | 24344.44
18 | ** | Paver block pavement&fencing around CTs | NL-N-TS2-002-02-06 | 6082931.41 | 6082931.41 | 0 | 6082931.41 | 0 | 6082931.41 | 6082931.41 | 0 | 6082931.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6082931.41 | 6082931.41 | 0 | 6082931.41 | 0
19 | ** | Rehabilitation works to CT-1 - Outside | NL-N-TS2-002-02-07 | 20904541.88 | 20680612.08 | 0 | 20680612.08 | 223929.8 | 20904541.88 | 20680612.08 | 0 | 20680612.08 | 223929.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20904541.88 | 20680612.08 | 0 | 20680612.08 | 223929.8
20 | ** | Roof& cladding to JT-1& sloping conveyor | NL-N-TS2-002-02-09 | 3186642.45 | 3186642.45 | 0 | 3186642.45 | 0 | 3186642.45 | 3186642.45 | 0 | 3186642.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3186642.45 | 3186642.45 | 0 | 3186642.45 | 0
21 | ** | Painting of Boiler structures U-5,6 & 7 | NL-N-TS2-002-02-10 | 1838450.46 | 1283419.04 | 0 | 1283419.04 | 555031.42 | 1838450.46 | 1283419.04 | 0 | 1283419.04 | 555031.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1838450.46 | 1283419.04 | 0 | 1283419.04 | 555031.42
22 | ** | Repair& painting of Stage II Boiler Lift | NL-N-TS2-002-02-11 | 3896420.89 | 3896420.89 | 0 | 3896420.89 | 0 | 3896420.89 | 3896420.89 | 0 | 3896420.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3896420.89 | 3896420.89 | 0 | 3896420.89 | 0
23 | ** | Coat over existing bituminous roads | NL-N-TS2-002-02-12 | 1813726.51 | 1813726.51 | 0 | 1813726.51 | 0 | 1813726.51 | 1813726.51 | 0 | 1813726.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813726.51 | 1813726.51 | 0 | 1813726.51 | 0
24 | ** | Providing golvelume sheet of Lift-6&7 | NL-N-TS2-002-02-13 | 1517070.85 | 1517070.85 | 0 | 1517070.85 | 0 | 1517070.85 | 1517070.85 | 0 | 1517070.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517070.85 | 1517070.85 | 0 | 1517070.85 | 0
25 | ** | Restoration sheets Boiler ST-II/Phase-I | NL-N-TS2-002-02-17 | 13027194.37 | 12373433.2 | 653761.17 | 13027194.37 | 0 | 12449036.98 | 12373433.2 | 0 | 12373433.2 | 75603.78 | 578157.39 | 0 | 653761.17 | 653761.17 | -75603.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13027194.37 | 12373433.2 | 653761.17 | 13027194.37 | 0
26 | ** | Restoration sheet Boiler ST-II/Phase-II | NL-N-TS2-002-02-18 | 12685552.22 | 12685552.16 | 0.06 | 12685552.22 | 0 | 12685552.16 | 12685552.16 | 0 | 12685552.16 | 0 | 0.06 | 0 | 0.06 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12685552.22 | 12685552.16 | 0.06 | 12685552.22 | 0
27 | ** | Installation&Commissioning of STP | NL-N-TS2-002-02-21 | 14181240.06 | 7944114 | 6237126.06 | 14181240.06 | 0 | 7944114 | 7944114 | 0 | 7944114 | 0 | 6237126.06 | 0 | 6237126.06 | 6237126.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14181240.06 | 7944114 | 6237126.06 | 14181240.06 | 0
28 | ** | Upgraditaion of Weighbridge to 100 T | NL-N-TS2-002-02-22 | 443809.82 | 430495.86 | 13313.96 | 443809.82 | 0 | 443809.8 | 430495.86 | 0 | 430495.86 | 13313.94 | 0.02 | 0 | 13313.96 | 13313.96 | -13313.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443809.82 | 430495.86 | 13313.96 | 443809.82 | 0
29 | ** | Retrofit outside platform of Stage-I CTs | NL-N-TS2-002-02-24 | 19026910.03 | 18928675 | 98235.03 | 19026910.03 | 0 | 18928675 | 18928675 | 0 | 18928675 | 0 | 98235.03 | 0 | 98235.03 | 98235.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19026910.03 | 18928675 | 98235.03 | 19026910.03 | 0
30 | ** | Laterite Platform for Reclaimer erection | NL-N-TS2-002-02-25 | 8065282.96 | 8065282.96 | 0 | 8065282.96 | 0 | 8065282.96 | 8065282.96 | 0 | 8065282.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8065282.96 | 8065282.96 | 0 | 8065282.96 | 0
31 | ** | Civil & Structural works for VIP Lift | NL-N-TS2-002-02-26 | 1619421.75 | 1619421.75 | 0 | 1619421.75 | 0 | 1619421.75 | 1619421.75 | 0 | 1619421.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1619421.75 | 1619421.75 | 0 | 1619421.75 | 0
32 | ** | Cover Shed for ESP Transformer -Stage-II | NL-N-TS2-002-02-27 | 1719385.54 | 1692145.84 | 0 | 1692145.84 | 27239.7 | 1719385.54 | 1692145.84 | 0 | 1692145.84 | 27239.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1719385.54 | 1692145.84 | 0 | 1692145.84 | 27239.7
33 | ** | Unit-5 Lift enclose with MS,Galva Sheet | NL-N-TS2-002-02-28 | 2921029.03 | 2520119.44 | 400909.59 | 2921029.03 | 0 | 2520119.44 | 2520119.44 | 0 | 2520119.44 | 0 | 400909.59 | 0 | 400909.59 | 400909.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2921029.03 | 2520119.44 | 400909.59 | 2921029.03 | 0
34 | ** | Repair of J-Row Walls in Stage-II | NL-N-TS2-002-02-30 | 1446652.07 | 840520.82 | 606131.25 | 1446652.07 | 0 | 944707.73 | 840520.82 | 0 | 840520.82 | 104186.91 | 501944.34 | 0 | 606131.25 | 606131.25 | -104186.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550838.98 | 840520.82 | 606131.25 | 1446652.07 | 104186.91
35 | ** | Modification of Power Monitoring centre | NL-N-TS2-002-02-33 | 383179.44 | 383179.44 | 0 | 383179.44 | 0 | 383179.44 | 383179.44 | 0 | 383179.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383179.44 | 383179.44 | 0 | 383179.44 | 0
36 | ** | REPAIR OF LHS TRACKS STOCKYARD | NL-N-TS2-002-02-34 | 37419688.03 | 5076264.42 | 32343423.61 | 37419688.03 | 0 | 10778164.14 | 10778164.14 | 0 | 10778164.14 | 0 | 26641523.89 | -5701899.72 | 32343423.61 | 26641523.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37419688.03 | 5076264.42 | 32343423.61 | 37419688.03 | 0
37 | ** | Manu.&supply of sleepers & REpair in LHS | NL-N-TS2-002-02-35 | 8902303.07 | 7107621.2 | 1794681.87 | 8902303.07 | 0 | 7107621.2 | 7107621.2 | 0 | 7107621.2 | 0 | 1794681.87 | 0 | 1794681.87 | 1794681.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8902303.07 | 7107621.2 | 1794681.87 | 8902303.07 | 0
38 | ** | Formation of new WBM road over embakment | NL-N-TS2-002-02-38 | 42691526.33 | 11577802.24 | 31113724.09 | 42691526.33 | 0 | 11577802.24 | 11577802.24 | 0 | 11577802.24 | 0 | 31113724.09 | 0 | 31113724.09 | 31113724.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42691526.33 | 11577802.24 | 31113724.09 | 42691526.33 | 0
39 | ** | IMPROVE BT ROAD TO MAKE UP WATER LAKE | NL-N-TS2-002-02-39 | 40854174.71 | 37674704.3 | 3179470.41 | 40854174.71 | 0 | 37674704.3 | 37674704.3 | 0 | 37674704.3 | 0 | 3179470.41 | 0 | 3179470.41 | 3179470.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40854174.71 | 37674704.3 | 3179470.41 | 40854174.71 | 0
40 | ** | WIDEN EXISTING OUTER ROAD-RCC WALL-2EXPN | NL-N-TS2-002-02-40 | 13436174.11 | 2508873.73 | 10927300.38 | 13436174.11 | 0 | 2508873.73 | 2508873.73 | 0 | 2508873.73 | 0 | 10927300.38 | 0 | 10927300.38 | 10927300.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13436174.11 | 2508873.73 | 10927300.38 | 13436174.11 | 0
41 | ** | galvaume sheets- transformer-esp fields | NL-N-TS2-002-02-41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | ** | galvaume sheets-LHS COVER SHED TT1 TT2 | NL-N-TS2-002-02-42 | 7878655.42 | 0 | 7878655.42 | 7878655.42 | 0 | 0 | 0 | 0 | 0 | 0 | 7878655.42 | 0 | 7878655.42 | 7878655.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7878655.42 | 0 | 7878655.42 | 7878655.42 | 0
43 | ** | galvaume sheets-7AB & 14AB CONVEYOR GALL | NL-N-TS2-002-02-43 | 10621883.48 | 0 | 10621883.48 | 10621883.48 | 0 | 0 | 0 | 0 | 0 | 0 | 10621883.48 | 0 | 10621883.48 | 10621883.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10621883.48 | 0 | 10621883.48 | 10621883.48 | 0
44 | ** | LIFT CONSTRUCTION- AO BUILDING | NL-N-TS2-002-02-44 | 1653112.51 | 0 | 1653112.51 | 1653112.51 | 0 | 0 | 0 | 0 | 0 | 0 | 1653112.51 | 0 | 1653112.51 | 1653112.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1653112.51 | 0 | 1653112.51 | 1653112.51 | 0
45 | ** |  | NL-N-TS2-002-02-45 | 8620822.04 | 0 | 8620822.04 | 8620822.04 | 0 | 0 | 0 | 0 | 0 | 0 | 8620822.04 | 0 | 8620822.04 | 8620822.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8620822.04 | 0 | 8620822.04 | 8620822.04 | 0
46 | ** |  | NL-N-TS2-002-02-46 | 5964987.14 | 0 | 5964987.14 | 5964987.14 | 0 | 0 | 0 | 0 | 0 | 0 | 5964987.14 | 0 | 5964987.14 | 5964987.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5964987.14 | 0 | 5964987.14 | 5964987.14 | 0
47 | ** |  | NL-N-TS2-002-02-47 | 16938507.7 | 0 | 16938507.7 | 16938507.7 | 0 | 0 | 0 | 0 | 0 | 0 | 16938507.7 | 0 | 16938507.7 | 16938507.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16938507.7 | 0 | 16938507.7 | 16938507.7 | 0
48 | ** |  | NL-N-TS2-002-02-48 | 11092618.04 | 0 | 11092618.04 | 11092618.04 | 0 | 0 | 0 | 0 | 0 | 0 | 11092618.04 | 0 | 11092618.04 | 11092618.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11092618.04 | 0 | 11092618.04 | 11092618.04 | 0
49 | *** | ELECTRICAL O & S | NL-N-TS2-002-03 | 67038344.33 | 31970221.42 | 35068122.91 | 67038344.33 | 0 | 31970221.42 | 31970221.42 | 0 | 31970221.42 | 0 | 35068122.91 | 0 | 35068122.91 | 35068122.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68450788.37 | 31970221.42 | 35068122.91 | 67038344.33 | 1412444.04
50 | ** | Retrofit of relay for 6.6KV incomers,Tie | NL-N-TS2-002-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | ** | Battery charger 220V 300A sets | NL-N-TS2-002-03-02 | 4476239.99 | 4476239.99 | 0 | 4476239.99 | 0 | 4476239.99 | 4476239.99 | 0 | 4476239.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4476239.99 | 4476239.99 | 0 | 4476239.99 | 0
52 | ** | Replace 1180AH cap battery bank Stage-I | NL-N-TS2-002-03-03 | 18489989.03 | 18489989.03 | 0 | 18489989.03 | 0 | 18489989.03 | 18489989.03 | 0 | 18489989.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18489989.03 | 18489989.03 | 0 | 18489989.03 | 0
53 | ** | Replace 1285AH cap battery bank Stage-II | NL-N-TS2-002-03-04 | 6552405.79 | 6552405.79 | 0 | 6552405.79 | 0 | 6552405.79 | 6552405.79 | 0 | 6552405.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6552405.79 | 6552405.79 | 0 | 6552405.79 | 0
54 | ** | Swyrd PLCC 48V/ 300A Battery charger | NL-N-TS2-002-03-10 | 2543985.6 | 0 | 2543985.6 | 2543985.6 | 0 | 0 | 0 | 0 | 0 | 0 | 2543985.6 | 0 | 2543985.6 | 2543985.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2543985.6 | 0 | 2543985.6 | 2543985.6 | 0
55 | ** | Swyrd Source 220V/ 150A Battery charger | NL-N-TS2-002-03-11 | 2932252.8 | 0 | 2932252.8 | 2932252.8 | 0 | 0 | 0 | 0 | 0 | 0 | 2932252.8 | 0 | 2932252.8 | 2932252.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2932252.8 | 0 | 2932252.8 | 2932252.8 | 0
56 | ** | 48V Thyrister based FCBC Battery Charger | NL-N-TS2-002-03-14 | 324999.99 | 324999.99 | 0 | 324999.99 | 0 | 324999.99 | 324999.99 | 0 | 324999.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324999.99 | 324999.99 | 0 | 324999.99 | 0
57 | ** | Control cable 4 core & 2 core-1.1KV | NL-N-TS2-002-03-21 | 730707.73 | 730707.73 | 0 | 730707.73 | 0 | 730707.73 | 730707.73 | 0 | 730707.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730707.73 | 730707.73 | 0 | 730707.73 | 0
58 | ** | Battery Operated platform trolley 4000kg | NL-N-TS2-002-03-22 | 719080 | 719080 | 0 | 719080 | 0 | 719080 | 719080 | 0 | 719080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719080 | 719080 | 0 | 719080 | 0
59 | ** | 1.1kV FRLS-Cu cable 7CX1.5 sqmm | NL-N-TS2-002-03-23 | 561080.86 | 561080.86 | 0 | 561080.86 | 0 | 561080.86 | 561080.86 | 0 | 561080.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561080.86 | 561080.86 | 0 | 561080.86 | 0
60 | ** | 1.1 KV FRLS Cu Cables | NL-N-TS2-002-03-24 | 1066183.59 | 0 | 1066183.59 | 1066183.59 | 0 | 0 | 0 | 0 | 0 | 0 | 1066183.59 | 0 | 1066183.59 | 1066183.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066183.59 | 0 | 1066183.59 | 1066183.59 | 0
61 | ** | Instrument Air Compressor Dryer Panel | NL-N-TS2-002-03-25 | 823199.96 | 0 | 823199.96 | 823199.96 | 0 | 0 | 0 | 0 | 0 | 0 | 823199.96 | 0 | 823199.96 | 823199.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2235644 | 0 | 823199.96 | 823199.96 | 1412444.04
62 | ** | GT Cooler Control Panel for Stage-2 | NL-N-TS2-002-03-26 | 3300837.6 | 0 | 3300837.6 | 3300837.6 | 0 | 0 | 0 | 0 | 0 | 0 | 3300837.6 | 0 | 3300837.6 | 3300837.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300837.6 | 0 | 3300837.6 | 3300837.6 | 0
63 | ** | Clamp Meter | NL-N-TS2-002-03-27 | 115718.03 | 115718.03 | 0 | 115718.03 | 0 | 115718.03 | 115718.03 | 0 | 115718.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115718.03 | 115718.03 | 0 | 115718.03 | 0
64 | ** | 2X20KVA UPS FOR DRY FLY ASH SYSTEM | NL-N-TS2-002-03-28 | 5600330 | 0 | 5600330 | 5600330 | 0 | 0 | 0 | 0 | 0 | 0 | 5600330 | 0 | 5600330 | 5600330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600330 | 0 | 5600330 | 5600330 | 0
65 | ** | Centrifuge Control panels- Stage-II | NL-N-TS2-002-03-30 | 2281333.36 | 0 | 2281333.36 | 2281333.36 | 0 | 0 | 0 | 0 | 0 | 0 | 2281333.36 | 0 | 2281333.36 | 2281333.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2281333.36 | 0 | 2281333.36 | 2281333.36 | 0
66 | ** |  | NL-N-TS2-002-03-31 | 16520000 | 0 | 16520000 | 16520000 | 0 | 0 | 0 | 0 | 0 | 0 | 16520000 | 0 | 16520000 | 16520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16520000 | 0 | 16520000 | 16520000 | 0
67 | *** | ELECTRICAL MAINTENANCE | NL-N-TS2-002-04 | 2091800556.26 | 688260333.81 | 1403540222.45 | 2091800556.26 | 0 | 683654596.82 | 683541906.82 | 0 | 683541906.82 | 112690 | 1408145959.44 | 4718426.99 | 1392133459.73 | 1396851886.72 | 11294072.72 | 0 | 0 | 11406762.72 | 11406762.72 | -11406762.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2104363033.32 | 688260333.81 | 1403540222.45 | 2091800556.26 | 12562477.06
68 | ** | LHS CONTROLS | NL-N-TS2-002-04-01 | 18041806.08 | 15941739.48 | 2100066.6 | 18041806.08 | 0 | 15941739.48 | 15941739.48 | 0 | 15941739.48 | 0 | 2100066.6 | 0 | 2100066.6 | 2100066.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18041806.08 | 15941739.48 | 2100066.6 | 18041806.08 | 0
69 | * | Bunker Level Transmitter stage-II | NL-N-TS2-002-04-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | * | TPS-II Emerson PLC Upgradation for DAS | NL-N-TS2-002-04-01-02 | 5130640 | 5130640 | 0 | 5130640 | 0 | 5130640 | 5130640 | 0 | 5130640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5130640 | 5130640 | 0 | 5130640 | 0
71 | * | HMI Hardware Workstation | NL-N-TS2-002-04-01-04 | 700500.02 | 700500.02 | 0 | 700500.02 | 0 | 700500.02 | 700500.02 | 0 | 700500.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700500.02 | 700500.02 | 0 | 700500.02 | 0
72 | * | Procurement of Magnetic Separators | NL-N-TS2-002-04-01-13 | 9192000 | 9192000 | 0 | 9192000 | 0 | 9192000 | 9192000 | 0 | 9192000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9192000 | 9192000 | 0 | 9192000 | 0
73 | * | 2T capacity Battery Operated platform Tr | NL-N-TS2-002-04-01-14 | 690950 | 0 | 690950 | 690950 | 0 | 0 | 0 | 0 | 0 | 0 | 690950 | 0 | 690950 | 690950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 690950 | 0 | 690950 | 690950 | 0
74 | * | Linear Heat Sensing (LHS) Cable | NL-N-TS2-002-04-01-15 | 851239.74 | 851239.74 | 0 | 851239.74 | 0 | 851239.74 | 851239.74 | 0 | 851239.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851239.74 | 851239.74 | 0 | 851239.74 | 0
75 | * | Rotex 2/2 Direct Acting Solenoid Valve | NL-N-TS2-002-04-01-16 | 67359.72 | 67359.72 | 0 | 67359.72 | 0 | 67359.72 | 67359.72 | 0 | 67359.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67359.72 | 67359.72 | 0 | 67359.72 | 0
76 | * | Procurement of Infra red Detector (IRD) | NL-N-TS2-002-04-01-17 | 1409116.6 | 0 | 1409116.6 | 1409116.6 | 0 | 0 | 0 | 0 | 0 | 0 | 1409116.6 | 0 | 1409116.6 | 1409116.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409116.6 | 0 | 1409116.6 | 1409116.6 | 0
77 | ** | ESP CONTROLS | NL-N-TS2-002-04-02 | 21325198.59 | 20276248.57 | 1048950.02 | 21325198.59 | 0 | 20276248.57 | 20276248.57 | 0 | 20276248.57 | 0 | 1048950.02 | 0 | 1048950.02 | 1048950.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21325198.59 | 20276248.57 | 1048950.02 | 21325198.59 | 0
78 | * | Boiler Lift-5 & 6 | NL-N-TS2-002-04-02-01 | 15340000 | 14572999.99 | 767000.01 | 15340000 | 0 | 14572999.99 | 14572999.99 | 0 | 14572999.99 | 0 | 767000.01 | 0 | 767000.01 | 767000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15340000 | 14572999.99 | 767000.01 | 15340000 | 0
79 | * | Boiler lift- 2,4 & 7 | NL-N-TS2-002-04-02-04 | 2060704.8 | 2060704.8 | 0 | 2060704.8 | 0 | 2060704.8 | 2060704.8 | 0 | 2060704.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060704.8 | 2060704.8 | 0 | 2060704.8 | 0
80 | * | Supply,Erection&Commisioning of New Lift | NL-N-TS2-002-04-02-07 | 1400000.38 | 1400000.38 | 0 | 1400000.38 | 0 | 1400000.38 | 1400000.38 | 0 | 1400000.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000.38 | 1400000.38 | 0 | 1400000.38 | 0
81 | * | Retrofitting of Unit-3 ACP | NL-N-TS2-002-04-02-08 | 1112566.73 | 1112566.73 | 0 | 1112566.73 | 0 | 1112566.73 | 1112566.73 | 0 | 1112566.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1112566.73 | 1112566.73 | 0 | 1112566.73 | 0
82 | * | Procurement and inst of 6 passenger lift | NL-N-TS2-002-04-02-09 | 1411926.68 | 1129976.67 | 281950.01 | 1411926.68 | 0 | 1129976.67 | 1129976.67 | 0 | 1129976.67 | 0 | 281950.01 | 0 | 281950.01 | 281950.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411926.68 | 1129976.67 | 281950.01 | 1411926.68 | 0
83 | ** | ELECTRICAL MAINTENANCE-I | NL-N-TS2-002-04-03 | 356671594.87 | 319609564.91 | 37062029.96 | 356671594.87 | 0 | 319301977.92 | 319198137.92 | 0 | 319198137.92 | 103840 | 37369616.95 | 411426.99 | 37062029.96 | 37473456.95 | -103840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356671594.87 | 319609564.91 | 37062029.96 | 356671594.87 | 0
84 | * | ESP Hoist for stage I Units | NL-N-TS2-002-04-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | * | Retrofitting of 6.6KV Breaker-Stage-II | NL-N-TS2-002-04-03-09 | 11581426.18 | 11581426.18 | 0 | 11581426.18 | 0 | 11581426.18 | 11581426.18 | 0 | 11581426.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11581426.18 | 11581426.18 | 0 | 11581426.18 | 0
86 | * | GENERATOR STATOR END WINDING SPARES | NL-N-TS2-002-04-03-11 | 6826717.25 | 6826717.25 | 0 | 6826717.25 | 0 | 6826717.25 | 6826717.25 | 0 | 6826717.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6826717.25 | 6826717.25 | 0 | 6826717.25 | 0
87 | * | OIP 400 KV Bushing - Stage-2 GT | NL-N-TS2-002-04-03-12 | 4311174.55 | 4311174.55 | 0 | 4311174.55 | 0 | 4311174.55 | 4311174.55 | 0 | 4311174.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4311174.55 | 4311174.55 | 0 | 4311174.55 | 0
88 | * | LVBushing for Stage-1 GT with metal part | NL-N-TS2-002-04-03-13 | 1947000 | 1947000 | 0 | 1947000 | 0 | 1947000 | 1947000 | 0 | 1947000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1947000 | 1947000 | 0 | 1947000 | 0
89 | * | LV Bushing for Stage-1 GT porcelien only | NL-N-TS2-002-04-03-14 | 251233.8 | 251233.8 | 0 | 251233.8 | 0 | 251233.8 | 251233.8 | 0 | 251233.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251233.8 | 251233.8 | 0 | 251233.8 | 0
90 | * | LV Bushing for Stage-2 GT metal part | NL-N-TS2-002-04-03-15 | 2920500 | 2920500 | 0 | 2920500 | 0 | 2920500 | 2920500 | 0 | 2920500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2920500 | 2920500 | 0 | 2920500 | 0
91 | * | LV Bushing for Stage-2 GT porcelien only | NL-N-TS2-002-04-03-16 | 502467.6 | 502467.6 | 0 | 502467.6 | 0 | 502467.6 | 502467.6 | 0 | 502467.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502467.6 | 502467.6 | 0 | 502467.6 | 0
92 | * | Oil Pump for stage-1 GT | NL-N-TS2-002-04-03-17 | 389400 | 389400 | 0 | 389400 | 0 | 389400 | 389400 | 0 | 389400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389400 | 389400 | 0 | 389400 | 0
93 | * | Oil Pump for stage-2 GT | NL-N-TS2-002-04-03-18 | 389400 | 389400 | 0 | 389400 | 0 | 389400 | 389400 | 0 | 389400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389400 | 389400 | 0 | 389400 | 0
94 | * | 160 KVA LDB Transformer | NL-N-TS2-002-04-03-19 | 1402289.81 | 1402289.81 | 0 | 1402289.81 | 0 | 1402289.81 | 1402289.81 | 0 | 1402289.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1402289.81 | 1402289.81 | 0 | 1402289.81 | 0
95 | * | Retrofitting of Tadiran Exchange TPS-2 | NL-N-TS2-002-04-03-21 | 2400000 | 2400000 | 0 | 2400000 | 0 | 2400000 | 2400000 | 0 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 2400000 | 0 | 2400000 | 0
96 | * | Purchase of 12 KV,2500A VCBs | NL-N-TS2-002-04-03-22 | 3841472.82 | 3841472.82 | 0 | 3841472.82 | 0 | 3841472.82 | 3841472.82 | 0 | 3841472.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3841472.82 | 3841472.82 | 0 | 3841472.82 | 0
97 | * | Generator Seal Rings Turbine&Exiter Ends | NL-N-TS2-002-04-03-23 | 1517272 | 1517272 | 0 | 1517272 | 0 | 1517272 | 1517272 | 0 | 1517272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517272 | 1517272 | 0 | 1517272 | 0
98 | * | 100KVA LTG Transformer R&R Work | NL-N-TS2-002-04-03-24 | 446040.03 | 423738 | 22302.03 | 446040.03 | 0 | 423738 | 423738 | 0 | 423738 | 0 | 22302.03 | 0 | 22302.03 | 22302.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446040.03 | 423738 | 22302.03 | 446040.03 | 0
99 | * | 400KVA Bore Well Transformer R&R Work | NL-N-TS2-002-04-03-25 | 472000.03 | 472000 | 0.03 | 472000.03 | 0 | 472000 | 472000 | 0 | 472000 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472000.03 | 472000 | 0.03 | 472000.03 | 0
100 | * | Field over voltage circuit assembly DSES | NL-N-TS2-002-04-03-26 | 325385 | 325385 | 0 | 325385 | 0 | 325385 | 325385 | 0 | 325385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325385 | 325385 | 0 | 325385 | 0
101 | * | Differential Pressure Regulator A & B | NL-N-TS2-002-04-03-27 | 3581659.62 | 3581659.62 | 0 | 3581659.62 | 0 | 3581659.62 | 3581659.62 | 0 | 3581659.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3581659.62 | 3581659.62 | 0 | 3581659.62 | 0
102 | * | Radio Remote Control for TG EOT Crane | NL-N-TS2-002-04-03-28 | 304463.6 | 304463.6 | 0 | 304463.6 | 0 | 304463.6 | 304463.6 | 0 | 304463.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304463.6 | 304463.6 | 0 | 304463.6 | 0
103 | * | Dielectric Coating at 6.6 KV SWGR Panel | NL-N-TS2-002-04-03-29 | 1688344 | 1688344 | 0 | 1688344 | 0 | 1688344 | 1688344 | 0 | 1688344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1688344 | 1688344 | 0 | 1688344 | 0
104 | * | Carbon brush holder & Coil spring | NL-N-TS2-002-04-03-30 | 2041926.68 | 2041926.68 | 0 | 2041926.68 | 0 | 2041926.68 | 2041926.68 | 0 | 2041926.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2041926.68 | 2041926.68 | 0 | 2041926.68 | 0
105 | * | AC Drive suitable for 4 & 5.5KW Motors | NL-N-TS2-002-04-03-32 | 1716500.1 | 1716500.1 | 0 | 1716500.1 | 0 | 1716500.1 | 1716500.1 | 0 | 1716500.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1716500.1 | 1716500.1 | 0 | 1716500.1 | 0
106 | * | Erection & Commissioning of UAT-4B | NL-N-TS2-002-04-03-33 | 525100 | 525100 | 0 | 525100 | 0 | 525100 | 525100 | 0 | 525100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525100 | 525100 | 0 | 525100 | 0
107 | * | Complete Overhauling of UAT | NL-N-TS2-002-04-03-34 | 222548 | 222548 | 0 | 222548 | 0 | 222548 | 222548 | 0 | 222548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222548 | 222548 | 0 | 222548 | 0
108 | * | Rectification of NGR of ST-1&2 | NL-N-TS2-002-04-03-36 | 283200 | 283200 | 0 | 283200 | 0 | 283200 | 283200 | 0 | 283200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283200 | 283200 | 0 | 283200 | 0
109 | * | Generator Spares | NL-N-TS2-002-04-03-45 | 550980 | 550980 | 0 | 550980 | 0 | 550980 | 550980 | 0 | 550980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550980 | 550980 | 0 | 550980 | 0
110 |  |  | work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | * | Dry Type Indoor Excitation Transformer | NL-N-TS2-002-04-03-51 | 8341426.72 | 8341426.72 | 0 | 8341426.72 | 0 | 8341426.72 | 8341426.72 | 0 | 8341426.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8341426.72 | 8341426.72 | 0 | 8341426.72 | 0
112 | * | Inter Connecting Transformer | NL-N-TS2-002-04-03-52 | 2322594.03 | 2322594 | 0.03 | 2322594.03 | 0 | 2322594 | 2322594 | 0 | 2322594 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2322594.03 | 2322594 | 0.03 | 2322594.03 | 0
113 | * | Main & Stuffing Bellows for DPRV | NL-N-TS2-002-04-03-56 | 631717.39 | 631717.39 | 0 | 631717.39 | 0 | 631717.39 | 631717.39 | 0 | 631717.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631717.39 | 631717.39 | 0 | 631717.39 | 0
114 | * | Split AC 2 Ton Capacity 5 Star rating | NL-N-TS2-002-04-03-57 | 1024960 | 1024960 | 0 | 1024960 | 0 | 1024960 | 1024960 | 0 | 1024960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024960 | 1024960 | 0 | 1024960 | 0
115 | * | Rejuvenation of ESP STr Earth Pits | NL-N-TS2-002-04-03-58 | 552239.98 | 552239.68 | 0.3 | 552239.98 | 0 | 552239.68 | 552239.68 | 0 | 552239.68 | 0 | 0.3 | 0 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552239.98 | 552239.68 | 0.3 | 552239.98 | 0
116 | * | Refregirant H2 Gas Dryer-ST II Generator | NL-N-TS2-002-04-03-59 | 2468559.99 | 2468559.99 | 0 | 2468559.99 | 0 | 2057133 | 2057133 | 0 | 2057133 | 0 | 411426.99 | 411426.99 | 0 | 411426.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2468559.99 | 2468559.99 | 0 | 2468559.99 | 0
117 | * | Vacuum Cleaner for HT Panel | NL-N-TS2-002-04-03-60 | 18336.1 | 18336.1 | 0 | 18336.1 | 0 | 18336.1 | 18336.1 | 0 | 18336.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18336.1 | 18336.1 | 0 | 18336.1 | 0
118 | * | REFREGIRANT TYPE H2GAS DRIYER FOR GENER | NL-N-TS2-002-04-03-61 | 2095500 | 2095500 | 0 | 2095500 | 0 | 2095500 | 2095500 | 0 | 2095500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2095500 | 2095500 | 0 | 2095500 | 0
119 | * | refurishment of Rotor of Unit -3 ,Gen | NL-N-TS2-002-04-03-62 | 113312609.33 | 110070559.3 | 3242050.03 | 113312609.33 | 0 | 110070559.3 | 110070559.3 | 0 | 110070559.3 | 0 | 3242050.03 | 0 | 3242050.03 | 3242050.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113312609.33 | 110070559.3 | 3242050.03 | 113312609.33 | 0
120 | * | Rectification of Unit-5 Generator | NL-N-TS2-002-04-03-63 | 25075000 | 25075000 | 0 | 25075000 | 0 | 25075000 | 25075000 | 0 | 25075000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25075000 | 25075000 | 0 | 25075000 | 0
121 | * | digital Tachometer for speed mes C&PBF M | NL-N-TS2-002-04-03-64 | 51174.01 | 51174.01 | 0 | 51174.01 | 0 | 51174.01 | 51174.01 | 0 | 51174.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51174.01 | 51174.01 | 0 | 51174.01 | 0
122 | * | Top panel mount cooler for VFD | NL-N-TS2-002-04-03-65 | 2200500 | 2200500 | 0 | 2200500 | 0 | 2200500 | 2200500 | 0 | 2200500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200500 | 2200500 | 0 | 2200500 | 0
123 | * | 11/0.433kv transformer rep rectification | NL-N-TS2-002-04-03-66 | 584640.03 | 501500 | 83140.03 | 584640.03 | 0 | 501500 | 501500 | 0 | 501500 | 0 | 83140.03 | 0 | 83140.03 | 83140.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584640.03 | 501500 | 83140.03 | 584640.03 | 0
124 | * | Seal oil pump for stage-2 Generator | NL-N-TS2-002-04-03-67 | 1337576.56 | 1337576.56 | 0 | 1337576.56 | 0 | 1337576.56 | 1337576.56 | 0 | 1337576.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1337576.56 | 1337576.56 | 0 | 1337576.56 | 0
125 | * | tranformer movement rail support | NL-N-TS2-002-04-03-68 | 3223763.56 | 2379429.56 | 844334 | 3223763.56 | 0 | 2379429.56 | 2379429.56 | 0 | 2379429.56 | 0 | 844334 | 0 | 844334 | 844334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3223763.56 | 2379429.56 | 844334 | 3223763.56 | 0
126 | * | Arresting oil leaks in LV bushings GT-2 | NL-N-TS2-002-04-03-69 | 323480.03 | 231280 | 92200.03 | 323480.03 | 0 | 231280 | 231280 | 0 | 231280 | 0 | 92200.03 | 0 | 92200.03 | 92200.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323480.03 | 231280 | 92200.03 | 323480.03 | 0
127 | * | 3X240 sqmm XLPE cable | NL-N-TS2-002-04-03-70 | 6101753.79 | 6101753.79 | 0 | 6101753.79 | 0 | 6101753.79 | 6101753.79 | 0 | 6101753.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6101753.79 | 6101753.79 | 0 | 6101753.79 | 0
128 | * | Purchase of 420 KV OIP bushing for ICT | NL-N-TS2-002-04-03-71 | 5748960 | 0 | 5748960 | 5748960 | 0 | 0 | 0 | 0 | 0 | 0 | 5748960 | 0 | 5748960 | 5748960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5748960 | 0 | 5748960 | 5748960 | 0
129 | * | Overhauling work of 6.6 kv Motor in TP2 | NL-N-TS2-002-04-03-72 | 4029700.01 | 3109300 | 920400.01 | 4029700.01 | 0 | 3109300 | 3109300 | 0 | 3109300 | 0 | 920400.01 | 0 | 920400.01 | 920400.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4029700.01 | 3109300 | 920400.01 | 4029700.01 | 0
130 | * | DCS 800 converter FOR U-2 DSES | NL-N-TS2-002-04-03-73 | 1911600 | 1911600 | 0 | 1911600 | 0 | 1911600 | 1911600 | 0 | 1911600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1911600 | 1911600 | 0 | 1911600 | 0
131 | * | Purchase of 2 T battery platform truck | NL-N-TS2-002-04-03-74 | 505000 | 505000 | 0 | 505000 | 0 | 505000 | 505000 | 0 | 505000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 505000 | 505000 | 0 | 505000 | 0
132 | * | Replacement of 2650 KVA Transformer | NL-N-TS2-002-04-03-75 | 1633545.02 | 1563795 | 69750.02 | 1633545.02 | 0 | 1563795 | 1563795 | 0 | 1563795 | 0 | 69750.02 | 0 | 69750.02 | 69750.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1633545.02 | 1563795 | 69750.02 | 1633545.02 | 0
133 | * | Transformer Oil IS335/1993 | NL-N-TS2-002-04-03-76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | * | Stator water centrifugal pump-Gen Mtce | NL-N-TS2-002-04-03-77 | 586090 | 0 | 586090 | 586090 | 0 | 0 | 0 | 0 | 0 | 0 | 586090 | 0 | 586090 | 586090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586090 | 0 | 586090 | 586090 | 0
135 | * | ST-Repair & RC of 3.3/6.6 KV HT motors | NL-N-TS2-002-04-03-78 | 6941940.03 | 6941940 | 0.03 | 6941940.03 | 0 | 6941940 | 6941940 | 0 | 6941940 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6941940.03 | 6941940 | 0.03 | 6941940.03 | 0
136 | * | Purchase of St-I Digital Exitation Spare | NL-N-TS2-002-04-03-79 | 1803653.6 | 1803653.6 | 0 | 1803653.6 | 0 | 1803653.6 | 1803653.6 | 0 | 1803653.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803653.6 | 1803653.6 | 0 | 1803653.6 | 0
137 | * | Seal rings Tubine&Exiter end 210 MW | NL-N-TS2-002-04-03-80 | 6194187.78 | 6194187.78 | 0 | 6194187.78 | 0 | 6194187.78 | 6194187.78 | 0 | 6194187.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6194187.78 | 6194187.78 | 0 | 6194187.78 | 0
138 | * | Megger make Coulometric Karl Fisher Titr | NL-N-TS2-002-04-03-81 | 1714950.5 | 1714950.5 | 0 | 1714950.5 | 0 | 1714950.5 | 1714950.5 | 0 | 1714950.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1714950.5 | 1714950.5 | 0 | 1714950.5 | 0
139 | * | MURR make power supply unit for stage-I | NL-N-TS2-002-04-03-83 | 307941.06 | 307941.06 | 0 | 307941.06 | 0 | 307941.06 | 307941.06 | 0 | 307941.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307941.06 | 307941.06 | 0 | 307941.06 | 0
140 | * | Generator Stator Winding Bar of BHEL mak | NL-N-TS2-002-04-03-84 | 17006868 | 17006868 | 0 | 17006868 | 0 | 17006868 | 17006868 | 0 | 17006868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17006868 | 17006868 | 0 | 17006868 | 0
141 | * | Rotor Fan blades for 210 MW Turbo Genera | NL-N-TS2-002-04-03-85 | 29557734.47 | 29557734.47 | 0 | 29557734.47 | 0 | 29557734.47 | 29557734.47 | 0 | 29557734.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29557734.47 | 29557734.47 | 0 | 29557734.47 | 0
142 | * | Proc of Submersible pump | NL-N-TS2-002-04-03-86 | 204299.99 | 204299.99 | 0 | 204299.99 | 0 | 204299.99 | 204299.99 | 0 | 204299.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204299.99 | 204299.99 | 0 | 204299.99 | 0
143 | * | Purchase of Mill Motors for stage-I & II | NL-N-TS2-002-04-03-87 | 22978497 | 0 | 22978497 | 22978497 | 0 | 0 | 0 | 0 | 0 | 0 | 22978497 | 0 | 22978497 | 22978497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22978497 | 0 | 22978497 | 22978497 | 0
144 | * | Retrofitting of Public Address System | NL-N-TS2-002-04-03-88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | * | Refurbishment of seal oil coolers | NL-N-TS2-002-04-03-90 | 1056000.01 | 0 | 1056000.01 | 1056000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000.01 | 0 | 1056000.01 | 1056000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056000.01 | 0 | 1056000.01 | 1056000.01 | 0
146 | * | SCISSOR LIFT | NL-N-TS2-002-04-03-91 | 910000 | 0 | 910000 | 910000 | 0 | 0 | 0 | 0 | 0 | 0 | 910000 | 0 | 910000 | 910000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910000 | 0 | 910000 | 910000 | 0
147 | * | ST work repair and rect of welding M/C | NL-N-TS2-002-04-03-92 | 1108280.03 | 687940 | 420340.03 | 1108280.03 | 0 | 791780 | 687940 | 0 | 687940 | 103840 | 316500.03 | 0 | 420340.03 | 420340.03 | -103840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108280.03 | 687940 | 420340.03 | 1108280.03 | 0
148 | * | Electrolytic Cells in Stage- 2 Hyd plant | NL-N-TS2-002-04-03-93 | 3630510.04 | 3590720.53 | 39789.51 | 3630510.04 | 0 | 3590720.53 | 3590720.53 | 0 | 3590720.53 | 0 | 39789.51 | 0 | 39789.51 | 39789.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3630510.04 | 3590720.53 | 39789.51 | 3630510.04 | 0
149 | * | Hydraulic Torque wrench | NL-N-TS2-002-04-03-94 | 1534639.15 | 1534639.15 | 0 | 1534639.15 | 0 | 1534639.15 | 1534639.15 | 0 | 1534639.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534639.15 | 1534639.15 | 0 | 1534639.15 | 0
150 | * | 10 KV Insulation Tester | NL-N-TS2-002-04-03-95 | 802164 | 802164 | 0 | 802164 | 0 | 802164 | 802164 | 0 | 802164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802164 | 802164 | 0 | 802164 | 0
151 | * | Retrofit & Upgrade the existing GPS syst | NL-N-TS2-002-04-03-96 | 2408843.82 | 2360666.95 | 48176.87 | 2408843.82 | 0 | 2360666.95 | 2360666.95 | 0 | 2360666.95 | 0 | 48176.87 | 0 | 48176.87 | 48176.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2408843.82 | 2360666.95 | 48176.87 | 2408843.82 | 0
152 | * | Hydogen gas Compressor 25 NM3/Hr | NL-N-TS2-002-04-03-97 | 18488300.74 | 18488300.74 | 0 | 18488300.74 | 0 | 18488300.74 | 18488300.74 | 0 | 18488300.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18488300.74 | 18488300.74 | 0 | 18488300.74 | 0
153 | * | Supply,insta and comm of Digital Wireles | NL-N-TS2-002-04-03-98 | 2477528 | 2477528 | 0 | 2477528 | 0 | 2477528 | 2477528 | 0 | 2477528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2477528 | 2477528 | 0 | 2477528 | 0
154 | * | 1cX1000 Sq mm Al XLPE insulated cable | NL-N-TS2-002-04-03-99 | 3026029.03 | 3026029.03 | 0 | 3026029.03 | 0 | 3026029.03 | 3026029.03 | 0 | 3026029.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3026029.03 | 3026029.03 | 0 | 3026029.03 | 0
155 | ** | ELECTRICAL MAINTENANCE-II | NL-N-TS2-002-04-04 | 70428613.15 | 36621646.09 | 33806967.06 | 70428613.15 | 0 | 36621646.09 | 36621646.09 | 0 | 36621646.09 | 0 | 33806967.06 | 0 | 27147957.05 | 27147957.05 | 6659010.01 | 0 | 0 | 6659010.01 | 6659010.01 | -6659010.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71020976.26 | 36621646.09 | 33806967.06 | 70428613.15 | 592363.11
156 | * | Retrofitting of Stage-1 WTP MCC panel | NL-N-TS2-002-04-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | * | Purchase of Switchgear Components-U2/U3 | NL-N-TS2-002-04-04-09 | 5707638.41 | 5707638.41 | 0 | 5707638.41 | 0 | 5707638.41 | 5707638.41 | 0 | 5707638.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5707638.41 | 5707638.41 | 0 | 5707638.41 | 0
158 | * | Retrofit of Switchgear Components-U2/U3 | NL-N-TS2-002-04-04-10 | 2259373.83 | 2239533.8 | 19840.03 | 2259373.83 | 0 | 2239533.8 | 2239533.8 | 0 | 2239533.8 | 0 | 19840.03 | 0 | 19840.03 | 19840.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2259373.83 | 2239533.8 | 19840.03 | 2259373.83 | 0
159 | * | PMCC panel for Stage-I AC plant | NL-N-TS2-002-04-04-11 | 12824240 | 0 | 12824240 | 12824240 | 0 | 0 | 0 | 0 | 0 | 0 | 12824240 | 0 | 12824240 | 12824240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12824240 | 0 | 12824240 | 12824240 | 0
160 | * | Supply & Retrofit of ACBs in Unit-4 & 5 | NL-N-TS2-002-04-04-12 | 23782132.57 | 17123122.56 | 6659010.01 | 23782132.57 | 0 | 17123122.56 | 17123122.56 | 0 | 17123122.56 | 0 | 6659010.01 | 0 | 0 | 0 | 6659010.01 | 0 | 0 | 6659010.01 | 6659010.01 | -6659010.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23782132.57 | 17123122.56 | 6659010.01 | 23782132.57 | 0
161 | * | Supply of spares&Replacement in ACBs/TS2 | NL-N-TS2-002-04-04-13 | 1873579.53 | 1873456.5 | 123.03 | 1873579.53 | 0 | 1873456.5 | 1873456.5 | 0 | 1873456.5 | 0 | 123.03 | 0 | 123.03 | 123.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1873579.53 | 1873456.5 | 123.03 | 1873579.53 | 0
162 | * | Refurbish of Festooning-ST2 Bunker Hoist | NL-N-TS2-002-04-04-14 | 1430560.05 | 1429791.84 | 768.21 | 1430560.05 | 0 | 1429791.84 | 1429791.84 | 0 | 1429791.84 | 0 | 768.21 | 0 | 768.21 | 768.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430560.05 | 1429791.84 | 768.21 | 1430560.05 | 0
163 | * | 2 ton Battery powered I P Truck | NL-N-TS2-002-04-04-26 | 514985 | 514985 | 0 | 514985 | 0 | 514985 | 514985 | 0 | 514985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514985 | 514985 | 0 | 514985 | 0
164 | * | 2 Ton Battery powered I P Truck | NL-N-TS2-002-04-04-27 | 516669.62 | 516669.62 | 0 | 516669.62 | 0 | 516669.62 | 516669.62 | 0 | 516669.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516669.62 | 516669.62 | 0 | 516669.62 | 0
165 | * | Refurbish of 3.5cX300 Sq.mm Al cable | NL-N-TS2-002-04-04-28 | 526018.88 | 526018.88 | 0 | 526018.88 | 0 | 526018.88 | 526018.88 | 0 | 526018.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526018.88 | 526018.88 | 0 | 526018.88 | 0
166 | * | Procurement of Dewatering Pump | NL-N-TS2-002-04-04-29 | 136731.95 | 136731.95 | 0 | 136731.95 | 0 | 136731.95 | 136731.95 | 0 | 136731.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136731.95 | 136731.95 | 0 | 136731.95 | 0
167 | * | Procurement of MCM Measuring instrument | NL-N-TS2-002-04-04-30 | 190000.06 | 190000.06 | 0 | 190000.06 | 0 | 190000.06 | 190000.06 | 0 | 190000.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000.06 | 190000.06 | 0 | 190000.06 | 0
168 | * | Rotork make actuators spares Forty items | NL-N-TS2-002-04-04-31 | 1635297.63 | 1635297.63 | 0 | 1635297.63 | 0 | 1635297.63 | 1635297.63 | 0 | 1635297.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635297.63 | 1635297.63 | 0 | 1635297.63 | 0
169 | * | Procurement of Stage-I & II motors | NL-N-TS2-002-04-04-32 | 1905927.4 | 1905927.4 | 0 | 1905927.4 | 0 | 1905927.4 | 1905927.4 | 0 | 1905927.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1905927.4 | 1905927.4 | 0 | 1905927.4 | 0
170 | * | Procurement of motors (LEP)for stg1&2 | NL-N-TS2-002-04-04-33 | 2087897.66 | 1408934.21 | 678963.45 | 2087897.66 | 0 | 1408934.21 | 1408934.21 | 0 | 1408934.21 | 0 | 678963.45 | 0 | 678963.45 | 678963.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2278347.54 | 1408934.21 | 678963.45 | 2087897.66 | 190449.88
171 | * | 1100 V greade 3Cx2.5 sq mm copper cable | NL-N-TS2-002-04-04-34 | 1878086.77 | 0 | 1878086.77 | 1878086.77 | 0 | 0 | 0 | 0 | 0 | 0 | 1878086.77 | 0 | 1878086.77 | 1878086.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2280000 | 0 | 1878086.77 | 1878086.77 | 401913.23
172 | * | Purchase of 12"/15"/18"/24" Exhaust fan | NL-N-TS2-002-04-04-35 | 1317735.69 | 281100.21 | 1036635.48 | 1317735.69 | 0 | 281100.21 | 281100.21 | 0 | 281100.21 | 0 | 1036635.48 | 0 | 1036635.48 | 1036635.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317735.69 | 281100.21 | 1036635.48 | 1317735.69 | 0
173 | * | 1100V grade,3.5C*35 Sqmm Aluminium, XLPE | NL-N-TS2-002-04-04-36 | 741735 | 741735 | 0 | 741735 | 0 | 741735 | 741735 | 0 | 741735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 741735 | 741735 | 0 | 741735 | 0
174 | * | 1100V grade , 3.5 C X 70 Sqmm Al cable | NL-N-TS2-002-04-04-39 | 2264000 | 0 | 2264000 | 2264000 | 0 | 0 | 0 | 0 | 0 | 0 | 2264000 | 0 | 2264000 | 2264000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2264000 | 0 | 2264000 | 2264000 | 0
175 | * | 1100V grade 3CX4sqmm Cu XLPE Cable | NL-N-TS2-002-04-04-40 | 384000 | 0 | 384000 | 384000 | 0 | 0 | 0 | 0 | 0 | 0 | 384000 | 0 | 384000 | 384000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384000 | 0 | 384000 | 384000 | 0
176 | * | WBS-Budget-Repair& Restore of CT pump br | NL-N-TS2-002-04-04-41 | 394398.78 | 390703.02 | 3695.76 | 394398.78 | 0 | 390703.02 | 390703.02 | 0 | 390703.02 | 0 | 3695.76 | 0 | 3695.76 | 3695.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394398.78 | 390703.02 | 3695.76 | 394398.78 | 0
177 | * | FIRE SURVIVAL CABLES | NL-N-TS2-002-04-04-42 | 2022738.49 | 0 | 2022738.49 | 2022738.49 | 0 | 0 | 0 | 0 | 0 | 0 | 2022738.49 | 0 | 2022738.49 | 2022738.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022738.49 | 0 | 2022738.49 | 2022738.49 | 0
178 | * | 1100v grade 3.5C X 240 POWER CABLE | NL-N-TS2-002-04-04-43 | 1998000 | 0 | 1998000 | 1998000 | 0 | 0 | 0 | 0 | 0 | 0 | 1998000 | 0 | 1998000 | 1998000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1998000 | 0 | 1998000 | 1998000 | 0
179 | * | Proc-SIRENS ALONG WITH NECESSARY SPARES | NL-N-TS2-002-04-04-44 | 409265.83 | 0 | 409265.83 | 409265.83 | 0 | 0 | 0 | 0 | 0 | 0 | 409265.83 | 0 | 409265.83 | 409265.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 409265.83 | 0 | 409265.83 | 409265.83 | 0
180 | * |  | NL-N-TS2-002-04-04-45 | 1480000 | 0 | 1480000 | 1480000 | 0 | 0 | 0 | 0 | 0 | 0 | 1480000 | 0 | 1480000 | 1480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1480000 | 0 | 1480000 | 1480000 | 0
181 | * |  | NL-N-TS2-002-04-04-46 | 2147600 | 0 | 2147600 | 2147600 | 0 | 0 | 0 | 0 | 0 | 0 | 2147600 | 0 | 2147600 | 2147600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2147600 | 0 | 2147600 | 2147600 | 0
182 | ** | SWITCH YARD | NL-N-TS2-002-04-05 | 246360137.58 | 87719206.5 | 158640931.08 | 246360137.58 | 0 | 87719206.5 | 87719206.5 | 0 | 87719206.5 | 0 | 158640931.08 | 0 | 158640931.08 | 158640931.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247092742.58 | 87719206.5 | 158640931.08 | 246360137.58 | 732605
183 | * | Secondphase 400kV Isolator rejuvenation | NL-N-TS2-002-04-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | * | Thermal Imaging Camera | NL-N-TS2-002-04-05-03 | 3657174 | 3657174 | 0 | 3657174 | 0 | 3657174 | 3657174 | 0 | 3657174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3657174 | 3657174 | 0 | 3657174 | 0
185 | * | Self propelled Scissor Lift | NL-N-TS2-002-04-05-04 | 465000 | 465000 | 0 | 465000 | 0 | 465000 | 465000 | 0 | 465000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465000 | 465000 | 0 | 465000 | 0
186 | * | 360KV 20KA DISCHARGE CLASS IV GAPLESS ZN | NL-N-TS2-002-04-05-11 | 1505225.72 | 1505225.72 | 0 | 1505225.72 | 0 | 1505225.72 | 1505225.72 | 0 | 1505225.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1505225.72 | 1505225.72 | 0 | 1505225.72 | 0
187 | * | 245KV CTs Type-I & II | NL-N-TS2-002-04-05-12 | 8544755.11 | 8544755.11 | 0 | 8544755.11 | 0 | 8544755.11 | 8544755.11 | 0 | 8544755.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8544755.11 | 8544755.11 | 0 | 8544755.11 | 0
188 | * | Clamps for HTLS Conductors | NL-N-TS2-002-04-05-13 | 873047.05 | 873047.05 | 0 | 873047.05 | 0 | 873047.05 | 873047.05 | 0 | 873047.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 873047.05 | 873047.05 | 0 | 873047.05 | 0
189 | * | Self propelled Articulating Boom Lift | NL-N-TS2-002-04-05-14 | 11867364 | 0 | 11867364 | 11867364 | 0 | 0 | 0 | 0 | 0 | 0 | 11867364 | 0 | 11867364 | 11867364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11867364 | 0 | 11867364 | 11867364 | 0
190 | * | 245KV SPRING OPERATEDSF6 CIRCUIT BREAKER | NL-N-TS2-002-04-05-15 | 1659478.89 | 1659478.89 | 0 | 1659478.89 | 0 | 1659478.89 | 1659478.89 | 0 | 1659478.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659478.89 | 1659478.89 | 0 | 1659478.89 | 0
191 | * | Retrofit of 245KV Isolators | NL-N-TS2-002-04-05-16 | 8254704 | 0 | 8254704 | 8254704 | 0 | 0 | 0 | 0 | 0 | 0 | 8254704 | 0 | 8254704 | 8254704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8254704 | 0 | 8254704 | 8254704 | 0
192 | * | 245KV SF6 Gas Current Transformer | NL-N-TS2-002-04-05-17 | 8989240 | 0 | 8989240 | 8989240 | 0 | 0 | 0 | 0 | 0 | 0 | 8989240 | 0 | 8989240 | 8989240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8989240 | 0 | 8989240 | 8989240 | 0
193 | * | 400KV Capacitance Voltage Transformer | NL-N-TS2-002-04-05-18 | 2458379.79 | 2458379.79 | 0 | 2458379.79 | 0 | 2458379.79 | 2458379.79 | 0 | 2458379.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2458379.79 | 2458379.79 | 0 | 2458379.79 | 0
194 | * | Replacement of faulty cables in SWYD | NL-N-TS2-002-04-05-19 | 634910 | 618910 | 16000 | 634910 | 0 | 618910 | 618910 | 0 | 618910 | 0 | 16000 | 0 | 16000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634910 | 618910 | 16000 | 634910 | 0
195 | * |  | 40036023 | 687595.24 | 687595.24 | 0 | 687595.24 | 0 | 687595.24 | 687595.24 | 0 | 687595.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687595.24 | 687595.24 | 0 | 687595.24 | 0
196 | * | Extension of ABT EMS large screen to UCB | NL-N-TS2-002-04-05-21 | 1592946.6 | 1592946.6 | 0 | 1592946.6 | 0 | 1592946.6 | 1592946.6 | 0 | 1592946.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1592946.6 | 1592946.6 | 0 | 1592946.6 | 0
197 | * | 400kV SF6 gas Current Transformers | NL-N-TS2-002-04-05-23 | 3781897.12 | 3781897.12 | 0 | 3781897.12 | 0 | 3781897.12 | 3781897.12 | 0 | 3781897.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3781897.12 | 3781897.12 | 0 | 3781897.12 | 0
198 | * | Retrofitting of 400KV Bus Bar Protection | NL-N-TS2-002-04-05-24 | 21776116.6 | 21776116.6 | 0 | 21776116.6 | 0 | 21776116.6 | 21776116.6 | 0 | 21776116.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21776116.6 | 21776116.6 | 0 | 21776116.6 | 0
199 | * | Replacement of 420 KV CT | NL-N-TS2-002-04-05-25 | 191160 | 191160 | 0 | 191160 | 0 | 191160 | 191160 | 0 | 191160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191160 | 191160 | 0 | 191160 | 0
200 | * | 400KV Spring OperatedSF6 Circuit Breaker | NL-N-TS2-002-04-05-26 | 19846903.4 | 19846903.4 | 0 | 19846903.4 | 0 | 19846903.4 | 19846903.4 | 0 | 19846903.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19846903.4 | 19846903.4 | 0 | 19846903.4 | 0
201 | * | ABT Based Energy Meters | NL-N-TS2-002-04-05-27 | 10469303.28 | 8724273.78 | 1745029.5 | 10469303.28 | 0 | 8724273.78 | 8724273.78 | 0 | 8724273.78 | 0 | 1745029.5 | 0 | 1745029.5 | 1745029.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10469303.28 | 8724273.78 | 1745029.5 | 10469303.28 | 0
202 | * | ST work for Repl of 400KV CB and SF6 gas | NL-N-TS2-002-04-05-31 | 818520.03 | 547520 | 271000.03 | 818520.03 | 0 | 547520 | 547520 | 0 | 547520 | 0 | 271000.03 | 0 | 271000.03 | 271000.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 818520.03 | 547520 | 271000.03 | 818520.03 | 0
203 | * | Reconductoring Existing ACSR with HTLS | NL-N-TS2-002-04-05-32 | 2147600.03 | 1342250 | 805350.03 | 2147600.03 | 0 | 1342250 | 1342250 | 0 | 1342250 | 0 | 805350.03 | 0 | 805350.03 | 805350.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2147600.03 | 1342250 | 805350.03 | 2147600.03 | 0
204 | * | Supply & Servicing of Opera Boxes 245 KV | NL-N-TS2-002-04-05-33 | 9446573.21 | 9446573.2 | 0.01 | 9446573.21 | 0 | 9446573.2 | 9446573.2 | 0 | 9446573.2 | 0 | 0.01 | 0 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9446573.21 | 9446573.2 | 0.01 | 9446573.21 | 0
205 | * | Supply and installation of Earth pits | NL-N-TS2-002-04-05-34 | 9956000 | 0 | 9956000 | 9956000 | 0 | 0 | 0 | 0 | 0 | 0 | 9956000 | 0 | 9956000 | 9956000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9956000 | 0 | 9956000 | 9956000 | 0
206 | * | Comm of 230 kv 1200 Sqmm XLPE copper cab | NL-N-TS2-002-04-05-35 | 82604759 | 0 | 82604759 | 82604759 | 0 | 0 | 0 | 0 | 0 | 0 | 82604759 | 0 | 82604759 | 82604759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82604759 | 0 | 82604759 | 82604759 | 0
207 | * | PUR OF 360KV 20KA LIGHTINING ARRESTOR | NL-N-TS2-002-04-05-36 | 3073251 | 0 | 3073251 | 3073251 | 0 | 0 | 0 | 0 | 0 | 0 | 3073251 | 0 | 3073251 | 3073251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3805856 | 0 | 3073251 | 3073251 | 732605
208 | * | Purchase of 230 KV SF6 Current Transform | NL-N-TS2-002-04-05-37 | 13246674.01 | 0 | 13246674.01 | 13246674.01 | 0 | 0 | 0 | 0 | 0 | 0 | 13246674.01 | 0 | 13246674.01 | 13246674.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13246674.01 | 0 | 13246674.01 | 13246674.01 | 0
209 | * | 4T BATTERY OPERATED PLATFROM TROLLEY | NL-N-TS2-002-04-05-39 | 13110000 | 0 | 13110000 | 13110000 | 0 | 0 | 0 | 0 | 0 | 0 | 13110000 | 0 | 13110000 | 13110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13110000 | 0 | 13110000 | 13110000 | 0
210 | * | SF6 GAS ANALYZER | NL-N-TS2-002-04-05-40 | 2168249 | 0 | 2168249 | 2168249 | 0 | 0 | 0 | 0 | 0 | 0 | 2168249 | 0 | 2168249 | 2168249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2168249 | 0 | 2168249 | 2168249 | 0
211 | * |  | NL-N-TS2-002-04-05-42 | 596047.5 | 0 | 596047.5 | 596047.5 | 0 | 0 | 0 | 0 | 0 | 0 | 596047.5 | 0 | 596047.5 | 596047.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596047.5 | 0 | 596047.5 | 596047.5 | 0
212 | * |  | NL-N-TS2-002-04-05-43 | 1937263 | 0 | 1937263 | 1937263 | 0 | 0 | 0 | 0 | 0 | 0 | 1937263 | 0 | 1937263 | 1937263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937263 | 0 | 1937263 | 1937263 | 0
213 | ** | MRT | NL-N-TS2-002-04-06 | 21171846.94 | 8966160.91 | 12205686.03 | 21171846.94 | 0 | 8966160.91 | 8966160.91 | 0 | 8966160.91 | 0 | 12205686.03 | 0 | 12205686.03 | 12205686.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21171846.94 | 8966160.91 | 12205686.03 | 21171846.94 | 0
214 | * | Multi Testing Kit-Transformer,SWYD&UCB | NL-N-TS2-002-04-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | * | Numerical Motor Protec Relay & Display | NL-N-TS2-002-04-06-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | * | Insulation Resistance Tester-Megger | NL-N-TS2-002-04-06-03 | 1148068.01 | 1148068.01 | 0 | 1148068.01 | 0 | 1148068.01 | 1148068.01 | 0 | 1148068.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148068.01 | 1148068.01 | 0 | 1148068.01 | 0
217 | * | Procurement of Breaker Contact Multiplie | NL-N-TS2-002-04-06-04 | 106500.03 | 0 | 106500.03 | 106500.03 | 0 | 0 | 0 | 0 | 0 | 0 | 106500.03 | 0 | 106500.03 | 106500.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106500.03 | 0 | 106500.03 | 106500.03 | 0
218 | * | DELTA 4110 Megger make Tan Delta test | NL-N-TS2-002-04-06-05 | 5861591.1 | 5861591.1 | 0 | 5861591.1 | 0 | 5861591.1 | 5861591.1 | 0 | 5861591.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5861591.1 | 5861591.1 | 0 | 5861591.1 | 0
219 | * | Over current/Neutral Voltage Relay | NL-N-TS2-002-04-06-06 | 785560.02 | 785560.02 | 0 | 785560.02 | 0 | 785560.02 | 785560.02 | 0 | 785560.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785560.02 | 785560.02 | 0 | 785560.02 | 0
220 | * | Procurement of new ICT protection System | NL-N-TS2-002-04-06-07 | 8283726 | 0 | 8283726 | 8283726 | 0 | 0 | 0 | 0 | 0 | 0 | 8283726 | 0 | 8283726 | 8283726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8283726 | 0 | 8283726 | 8283726 | 0
221 | * | purchase of 3 phase Combined Relay | NL-N-TS2-002-04-06-08 | 1170941.78 | 1170941.78 | 0 | 1170941.78 | 0 | 1170941.78 | 1170941.78 | 0 | 1170941.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170941.78 | 1170941.78 | 0 | 1170941.78 | 0
222 | * | NUMERICAL MOTOR PROTECTION RELAY | NL-N-TS2-002-04-06-09 | 1476582 | 0 | 1476582 | 1476582 | 0 | 0 | 0 | 0 | 0 | 0 | 1476582 | 0 | 1476582 | 1476582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1476582 | 0 | 1476582 | 1476582 | 0
223 | * |  | NL-N-TS2-002-04-06-10 | 2338878 | 0 | 2338878 | 2338878 | 0 | 0 | 0 | 0 | 0 | 0 | 2338878 | 0 | 2338878 | 2338878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2338878 | 0 | 2338878 | 2338878 | 0
224 | ** | ELECTRICAL MAINTENANCE -I-CONTINUATION | NL-N-TS2-002-04-07 | 1357801359.05 | 199125767.35 | 1158675591.7 | 1357801359.05 | 0 | 194827617.35 | 194818767.35 | 0 | 194818767.35 | 8850 | 1162973741.7 | 4307000 | 1153927838.99 | 1158234838.99 | 4738902.71 | 0 | 0 | 4747752.71 | 4747752.71 | -4747752.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369038868 | 199125767.35 | 1158675591.7 | 1357801359.05 | 11237508.95
225 | * | DSES-Field discharge resistor for STG-I | NL-N-TS2-002-04-07-01 | 1852052.04 | 1852052.04 | 0 | 1852052.04 | 0 | 1852052.04 | 1852052.04 | 0 | 1852052.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1852052.04 | 1852052.04 | 0 | 1852052.04 | 0
226 | * | BHEL HVR T/F ESP STG-2 | NL-N-TS2-002-04-07-02 | 18074656.9 | 18074656.9 | 0 | 18074656.9 | 0 | 18074656.9 | 18074656.9 | 0 | 18074656.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18074656.9 | 18074656.9 | 0 | 18074656.9 | 0
227 | * | Upgradation of DSES STG1 | NL-N-TS2-002-04-07-03 | 55022588.64 | 52131545.98 | 2891042.66 | 55022588.64 | 0 | 52131545.98 | 52131545.98 | 0 | 52131545.98 | 0 | 2891042.66 | 0 | 2891042.66 | 2891042.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55022588.64 | 52131545.98 | 2891042.66 | 55022588.64 | 0
228 | * | Monorail of stage 1 Millmotor | NL-N-TS2-002-04-07-04 | 1119128.03 | 1108728 | 10400.03 | 1119128.03 | 0 | 1108728 | 1108728 | 0 | 1108728 | 0 | 10400.03 | 0 | 10400.03 | 10400.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1119128.03 | 1108728 | 10400.03 | 1119128.03 | 0
229 | * | Purchase of Motorola Walkie Talkie Set | NL-N-TS2-002-04-07-05 | 2297460 | 0 | 2297460 | 2297460 | 0 | 0 | 0 | 0 | 0 | 0 | 2297460 | 0 | 2297460 | 2297460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2297460 | 0 | 2297460 | 2297460 | 0
230 | * | Tranformer oil BDV test Kit | NL-N-TS2-002-04-07-06 | 997510.01 | 997510.01 | 0 | 997510.01 | 0 | 997510.01 | 997510.01 | 0 | 997510.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997510.01 | 997510.01 | 0 | 997510.01 | 0
231 | * | SES and VFD | NL-N-TS2-002-04-07-07 | 27373050 | 0 | 27373050 | 27373050 | 0 | 0 | 0 | 0 | 0 | 0 | 27373050 | 0 | 27373050 | 27373050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27373050 | 0 | 27373050 | 27373050 | 0
232 | * | Rectifier Spares of Hydrogen plant | NL-N-TS2-002-04-07-08 | 255262 | 0 | 255262 | 255262 | 0 | 0 | 0 | 0 | 0 | 0 | 255262 | 0 | 255262 | 255262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255262 | 0 | 255262 | 255262 | 0
233 | * | ST contract work for repair 6,6 KV motor | NL-N-TS2-002-04-07-09 | 6360200.08 | 6042190 | 318010.08 | 6360200.08 | 0 | 6042190 | 6042190 | 0 | 6042190 | 0 | 318010.08 | 0 | 318010.08 | 318010.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6360200.08 | 6042190 | 318010.08 | 6360200.08 | 0
234 | * | Pur of self propelled Atricul boom lift | NL-N-TS2-002-04-07-10 | 4307000 | 4307000 | 0 | 4307000 | 0 | 0 | 0 | 0 | 0 | 0 | 4307000 | 4307000 | 0 | 4307000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4307000 | 4307000 | 0 | 4307000 | 0
235 | * | ST work for Overhauling of 6.6 kv motors | NL-N-TS2-002-04-07-11 | 4570749.57 | 4118999.7 | 451749.87 | 4570749.57 | 0 | 4118999.7 | 4118999.7 | 0 | 4118999.7 | 0 | 451749.87 | 0 | 451749.87 | 451749.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4570749.57 | 4118999.7 | 451749.87 | 4570749.57 | 0
236 | * | Purchase of Thermal Imaging Camera | NL-N-TS2-002-04-07-12 | 835208.83 | 835208.83 | 0 | 835208.83 | 0 | 835208.83 | 835208.83 | 0 | 835208.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 835208.83 | 835208.83 | 0 | 835208.83 | 0
237 | * | Retrofitting of stage-I mill motor hoist | NL-N-TS2-002-04-07-13 | 2559483.79 | 0 | 2559483.79 | 2559483.79 | 0 | 0 | 0 | 0 | 0 | 0 | 2559483.79 | 0 | 2559483.79 | 2559483.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6985743.9 | 0 | 2559483.79 | 2559483.79 | 4426260.11
238 | * | HT Motor and cable maintenance | NL-N-TS2-002-04-07-14 | 4387999.97 | 3545305.76 | 842694.21 | 4387999.97 | 0 | 3545305.76 | 3545305.76 | 0 | 3545305.76 | 0 | 842694.21 | 0 | 842694.21 | 842694.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5470800.01 | 3545305.76 | 842694.21 | 4387999.97 | 1082800.04
239 | * | 11000V grade 1C X630 Sq mm Al cable | NL-N-TS2-002-04-07-15 | 4623213.75 | 0 | 4623213.75 | 4623213.75 | 0 | 0 | 0 | 0 | 0 | 0 | 4623213.75 | 0 | 4623213.75 | 4623213.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10349955 | 0 | 4623213.75 | 4623213.75 | 5726741.25
240 | * | Megger make Micro ohm meter | NL-N-TS2-002-04-07-16 | 1382663.44 | 1382663.44 | 0 | 1382663.44 | 0 | 1382663.44 | 1382663.44 | 0 | 1382663.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1382663.44 | 1382663.44 | 0 | 1382663.44 | 0
241 | * | Online partial discharge scanner | NL-N-TS2-002-04-07-17 | 1806179.01 | 1806179.01 | 0 | 1806179.01 | 0 | 1806179.01 | 1806179.01 | 0 | 1806179.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1806179.01 | 1806179.01 | 0 | 1806179.01 | 0
242 | * | Retrofitting of 6.6 KV 1250 A MOCB's | NL-N-TS2-002-04-07-18 | 24464160.35 | 24464160.35 | 0 | 24464160.35 | 0 | 24464160.35 | 24464160.35 | 0 | 24464160.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24464160.35 | 24464160.35 | 0 | 24464160.35 | 0
243 | * | CEP Motor for St-I 6600Volts 515 KW | NL-N-TS2-002-04-07-19 | 5809486.45 | 0 | 5809486.45 | 5809486.45 | 0 | 0 | 0 | 0 | 0 | 0 | 5809486.45 | 0 | 5809486.45 | 5809486.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5811194 | 0 | 5809486.45 | 5809486.45 | 1707.55
244 | * | CAC Motor for DRY ash 6600 Volts 250 KW | NL-N-TS2-002-04-07-20 | 13024868.6 | 0 | 13024868.6 | 13024868.6 | 0 | 0 | 0 | 0 | 0 | 0 | 13024868.6 | 0 | 13024868.6 | 13024868.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13024868.6 | 0 | 13024868.6 | 13024868.6 | 0
245 | * | Condition assesment of HT cable & HT mot | NL-N-TS2-002-04-07-21 | 1386240.03 | 1015390 | 370850.03 | 1386240.03 | 0 | 1024240 | 1015390 | 0 | 1015390 | 8850 | 362000.03 | 0 | 370850.03 | 370850.03 | -8850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1386240.03 | 1015390 | 370850.03 | 1386240.03 | 0
246 | * | AC drive for 3 phase induction motor | NL-N-TS2-002-04-07-22 | 5876000.22 | 5876000.22 | 0 | 5876000.22 | 0 | 5876000.22 | 5876000.22 | 0 | 5876000.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5876000.22 | 5876000.22 | 0 | 5876000.22 | 0
247 | * | Single Core XLPE cable X1000 Sq mm | NL-N-TS2-002-04-07-23 | 22554870 | 0 | 22554870 | 22554870 | 0 | 0 | 0 | 0 | 0 | 0 | 22554870 | 0 | 22554870 | 22554870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22554870 | 0 | 22554870 | 22554870 | 0
248 | * | Rectifi,OH and Testing of Generator- U-I | NL-N-TS2-002-04-07-25 | 50220293.05 | 49520293 | 700000.05 | 50220293.05 | 0 | 49520293 | 49520293 | 0 | 49520293 | 0 | 700000.05 | 0 | 700000.05 | 700000.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50220293.05 | 49520293 | 700000.05 | 50220293.05 | 0
249 | * | Servicing of Siemens make 11 KV Ring | NL-N-TS2-002-04-07-26 | 1442055.9 | 1442055.89 | 0.01 | 1442055.9 | 0 | 1442055.89 | 1442055.89 | 0 | 1442055.89 | 0 | 0.01 | 0 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442055.9 | 1442055.89 | 0.01 | 1442055.9 | 0
250 | * | Supply insta &comm of hydrogen gas leak | NL-N-TS2-002-04-07-27 | 2036971.96 | 0 | 2036971.96 | 2036971.96 | 0 | 0 | 0 | 0 | 0 | 0 | 2036971.96 | 0 | 2036971.96 | 2036971.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036971.96 | 0 | 2036971.96 | 2036971.96 | 0
251 | * | Procure and commissioning of 01 no ICT | NL-N-TS2-002-04-07-28 | 286747270 | 0 | 286747270 | 286747270 | 0 | 0 | 0 | 0 | 0 | 0 | 286747270 | 0 | 286747270 | 286747270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286747270 | 0 | 286747270 | 286747270 | 0
252 | * | Refurb & rewinding of St-2 UAT LTE basis | NL-N-TS2-002-04-07-29 | 18227285.39 | 8266608 | 9960677.39 | 18227285.39 | 0 | 8266608 | 8266608 | 0 | 8266608 | 0 | 9960677.39 | 0 | 9960677.39 | 9960677.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18227285.39 | 8266608 | 9960677.39 | 18227285.39 | 0
253 | * | Purchase of 3 cX240 Sq mm 6.35 KV/11 KV | NL-N-TS2-002-04-07-30 | 12180000 | 0 | 12180000 | 12180000 | 0 | 0 | 0 | 0 | 0 | 0 | 12180000 | 0 | 12180000 | 12180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12180000 | 0 | 12180000 | 12180000 | 0
254 | * | Purchase of Circuit Breaker T I Meter | NL-N-TS2-002-04-07-31 | 112100 | 112100 | 0 | 112100 | 0 | 112100 | 112100 | 0 | 112100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112100 | 112100 | 0 | 112100 | 0
255 | * | Retrofitting and Upgradation of DSES | NL-N-TS2-002-04-07-32 | 44096000.06 | 0 | 44096000.06 | 44096000.06 | 0 | 0 | 0 | 0 | 0 | 0 | 44096000.06 | 0 | 44096000.06 | 44096000.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44096000.06 | 0 | 44096000.06 | 44096000.06 | 0
256 | * | DCS 800 Converter unit for stage-I | NL-N-TS2-002-04-07-33 | 1970600 | 1970600 | 0 | 1970600 | 0 | 1970600 | 1970600 | 0 | 1970600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1970600 | 1970600 | 0 | 1970600 | 0
257 | * | Repair and Rectification of Mill Motors | NL-N-TS2-002-04-07-34 | 7170897.15 | 6166189.12 | 1004708.03 | 7170897.15 | 0 | 6166189.12 | 6166189.12 | 0 | 6166189.12 | 0 | 1004708.03 | 0 | 1004708.03 | 1004708.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7170897.15 | 6166189.12 | 1004708.03 | 7170897.15 | 0
258 | * | RETROFITTING OF VCs FOR LHS HT CONVEYORS | NL-N-TS2-002-04-07-35 | 3915210.84 | 3660330.84 | 254880 | 3915210.84 | 0 | 3660330.84 | 3660330.84 | 0 | 3660330.84 | 0 | 254880 | 0 | 254880 | 254880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3915210.84 | 3660330.84 | 254880 | 3915210.84 | 0
259 | * | 6 NOS OF MOTORIZED HOIST WITH MANUAL MOV | NL-N-TS2-002-04-07-36 | 5141666.11 | 0 | 5141666.11 | 5141666.11 | 0 | 0 | 0 | 0 | 0 | 0 | 5141666.11 | 0 | 5141666.11 | 5141666.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5141666.11 | 0 | 5141666.11 | 5141666.11 | 0
260 | * | REPAIR-RECTIFICATION-6.6KV 420KW CONVEYO | NL-N-TS2-002-04-07-37 | 430000.29 | 430000.26 | 0.03 | 430000.29 | 0 | 430000.26 | 430000.26 | 0 | 430000.26 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430000.29 | 430000.26 | 0.03 | 430000.29 | 0
261 | * | PURCHASE OF NEUTRAL GROUNDING RESISTOR | NL-N-TS2-002-04-07-38 | 1627938.3 | 0 | 1627938.3 | 1627938.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1627938.3 | 0 | 1627938.3 | 1627938.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1627938.3 | 0 | 1627938.3 | 1627938.3 | 0
262 | * | TG HALL EOT CRANE ELECTRICAL SPARES | NL-N-TS2-002-04-07-39 | 1936710.49 | 0 | 1936710.49 | 1936710.49 | 0 | 0 | 0 | 0 | 0 | 0 | 1936710.49 | 0 | 1936710.49 | 1936710.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1936710.49 | 0 | 1936710.49 | 1936710.49 | 0
263 | * | MILL MOTOR-STAGE1-6.6KV-710KW | NL-N-TS2-002-04-07-40 | 78906288 | 0 | 78906288 | 78906288 | 0 | 0 | 0 | 0 | 0 | 0 | 78906288 | 0 | 78906288 | 78906288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78906288 | 0 | 78906288 | 78906288 | 0
264 | * | MILL MOTOR-STAGE2-6.6KV-600KW | NL-N-TS2-002-04-07-41 | 54344665.98 | 0 | 54344665.98 | 54344665.98 | 0 | 0 | 0 | 0 | 0 | 0 | 54344665.98 | 0 | 54344665.98 | 54344665.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54344665.98 | 0 | 54344665.98 | 54344665.98 | 0
265 | * | PURS-LT CONTROL CABLE-3RD ICT 315MVA T/F | NL-N-TS2-002-04-07-42 | 997017.05 | 0 | 997017.05 | 997017.05 | 0 | 0 | 0 | 0 | 0 | 0 | 997017.05 | 0 | 997017.05 | 997017.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997017.05 | 0 | 997017.05 | 997017.05 | 0
266 | * | PURS-LT CABLES-3RD ICT 315MVA T/F-PROTEC | NL-N-TS2-002-04-07-43 | 2432500 | 0 | 2432500 | 2432500 | 0 | 0 | 0 | 0 | 0 | 0 | 2432500 | 0 | 2432500 | 2432500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2432500 | 0 | 2432500 | 2432500 | 0
267 | * | 30 NOS OF VACUUM CIRCUIT BREAKERS-STAGE2 | NL-N-TS2-002-04-07-44 | 15497972.25 | 0 | 15497972.25 | 15497972.25 | 0 | 0 | 0 | 0 | 0 | 0 | 15497972.25 | 0 | 15497972.25 | 15497972.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15497972.25 | 0 | 15497972.25 | 15497972.25 | 0
268 | * | STATOR WINDING REPAIR -STAGE1 TURBO GEN | NL-N-TS2-002-04-07-45 | 26640658 | 0 | 26640658 | 26640658 | 0 | 0 | 0 | 0 | 0 | 0 | 26640658 | 0 | 26640658 | 26640658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26640658 | 0 | 26640658 | 26640658 | 0
269 | * | TRANSFORMER MTCE-RLA STUDY | NL-N-TS2-002-04-07-46 | 2664000.01 | 0 | 2664000.01 | 2664000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 2664000.01 | 0 | 2664000.01 | 2664000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2664000.01 | 0 | 2664000.01 | 2664000.01 | 0
270 | * | REPAIR AND RECTIFICATION OF ONE ID FAN | NL-N-TS2-002-04-07-47 | 4032250.01 | 0 | 4032250.01 | 4032250.01 | 0 | 0 | 0 | 0 | 0 | 0 | 4032250.01 | 0 | 4032250.01 | 4032250.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4032250.01 | 0 | 4032250.01 | 4032250.01 | 0
271 | * | PURC 3 NO OIP TYPE HV BUSHING FOR GT S2 | NL-N-TS2-002-04-07-48 | 4747752.71 | 0 | 4747752.71 | 4747752.71 | 0 | 0 | 0 | 0 | 0 | 0 | 4747752.71 | 0 | 0 | 0 | 4747752.71 | 0 | 0 | 4747752.71 | 4747752.71 | -4747752.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4747752.71 | 0 | 4747752.71 | 4747752.71 | 0
272 | * | REPAIR & RECT/ 6.6 KV motors stage1 mill | NL-N-TS2-002-04-07-49 | 6735000.01 | 0 | 6735000.01 | 6735000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 6735000.01 | 0 | 6735000.01 | 6735000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6735000.01 | 0 | 6735000.01 | 6735000.01 | 0
273 | * | TRANSFORMER OIL-100KL | NL-N-TS2-002-04-07-50 | 17950000 | 0 | 17950000 | 17950000 | 0 | 0 | 0 | 0 | 0 | 0 | 17950000 | 0 | 17950000 | 17950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17950000 | 0 | 17950000 | 17950000 | 0
274 | * | STATOR WINDING BARS FOR STAGE 1 TURBOGEN | NL-N-TS2-002-04-07-51 | 387608760 | 0 | 387608760 | 387608760 | 0 | 0 | 0 | 0 | 0 | 0 | 387608760 | 0 | 387608760 | 387608760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387608760 | 0 | 387608760 | 387608760 | 0
275 | * | overhauling 6.6 kv motors in TPS2 | NL-N-TS2-002-04-07-52 | 7942500.01 | 0 | 7942500.01 | 7942500.01 | 0 | 0 | 0 | 0 | 0 | 0 | 7942500.01 | 0 | 7942500.01 | 7942500.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7942500.01 | 0 | 7942500.01 | 7942500.01 | 0
276 | * |  | NL-N-TS2-002-04-07-53 | 1819610.3 | 0 | 1819610.3 | 1819610.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1819610.3 | 0 | 1819610.3 | 1819610.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1819610.3 | 0 | 1819610.3 | 1819610.3 | 0
277 | * |  | NL-N-TS2-002-04-07-54 | 24794750 | 0 | 24794750 | 24794750 | 0 | 0 | 0 | 0 | 0 | 0 | 24794750 | 0 | 24794750 | 24794750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24794750 | 0 | 24794750 | 24794750 | 0
278 | * |  | NL-N-TS2-002-04-07-55 | 67420985 | 0 | 67420985 | 67420985 | 0 | 0 | 0 | 0 | 0 | 0 | 67420985 | 0 | 67420985 | 67420985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67420985 | 0 | 67420985 | 67420985 | 0
279 | * |  | NL-N-TS2-002-04-07-56 | 1612818.99 | 0 | 1612818.99 | 1612818.99 | 0 | 0 | 0 | 0 | 0 | 0 | 1612818.99 | 0 | 1612818.99 | 1612818.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612818.99 | 0 | 1612818.99 | 1612818.99 | 0
280 | * |  | NL-N-TS2-002-04-07-57 | 3458799.48 | 0 | 3458799.48 | 3458799.48 | 0 | 0 | 0 | 0 | 0 | 0 | 3458799.48 | 0 | 3458799.48 | 3458799.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3458799.48 | 0 | 3458799.48 | 3458799.48 | 0
281 | *** | BOILER MAINTENANCE | NL-N-TS2-002-05 | 1271346914.11 | 530972435.28 | 732532344.66 | 1263515500.93 | 7831413.18 | 495142453.38 | 487300319.21 | 0 | 487311040.2 | 7831413.18 | 776204460.73 | 43672116.07 | 732532344.66 | 776204460.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1274674965.5 | 530972435.28 | 732532344.66 | 1263515500.93 | 11159464.57
282 | ** | SLAG CONVEYOR,ABG & FEEDER | NL-N-TS2-002-05-01 | 202062346.37 | 167545154.97 | 34517191.4 | 202062346.37 | 0 | 123873038.9 | 123873038.9 | 0 | 123873038.9 | 0 | 78189307.47 | 43672116.07 | 34517191.4 | 78189307.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202062346.37 | 167545154.97 | 34517191.4 | 202062346.37 | 0
283 | * | SLAG CONVEYOR CHAIN,PIV CHAIN AND ABG | NL-N-TS2-002-05-01-01 | 17118894.93 | 10762694.93 | 6356200 | 17118894.93 | 0 | 10762694.93 | 10762694.93 | 0 | 10762694.93 | 0 | 6356200 | 0 | 6356200 | 6356200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17118894.93 | 10762694.93 | 6356200 | 17118894.93 | 0
284 | * | Replace Str & Chequered plates-Boilers | NL-N-TS2-002-05-01-02 | 3132330 | 3132330 | 0 | 3132330 | 0 | 3132330 | 3132330 | 0 | 3132330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3132330 | 3132330 | 0 | 3132330 | 0
285 | * | Procurement of PB Elements Part - I | NL-N-TS2-002-05-01-03 | 2436741.11 | 2436741.11 | 0 | 2436741.11 | 0 | 2436741.11 | 2436741.11 | 0 | 2436741.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2436741.11 | 2436741.11 | 0 | 2436741.11 | 0
286 | * | Rectification of Unit-5 Boiler Girder | NL-N-TS2-002-05-01-04 | 4598035.2 | 4598035.2 | 0 | 4598035.2 | 0 | 4598035.2 | 4598035.2 | 0 | 4598035.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4598035.2 | 4598035.2 | 0 | 4598035.2 | 0
287 | * | Replacement of liner plates in B Bunker | NL-N-TS2-002-05-01-05 | 2419000 | 0 | 2419000 | 2419000 | 0 | 0 | 0 | 0 | 0 | 0 | 2419000 | 0 | 2419000 | 2419000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2419000 | 0 | 2419000 | 2419000 | 0
288 | * | procurement of ABG link chain | NL-N-TS2-002-05-01-06 | 1995944.86 | 0 | 1995944.86 | 1995944.86 | 0 | 0 | 0 | 0 | 0 | 0 | 1995944.86 | 0 | 1995944.86 | 1995944.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995944.86 | 0 | 1995944.86 | 1995944.86 | 0
289 | * | link chain size 22*86 having 59links SC | NL-N-TS2-002-05-01-07 | 33254760 | 33254760 | 0 | 33254760 | 0 | 33254760 | 33254760 | 0 | 33254760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33254760 | 33254760 | 0 | 33254760 | 0
290 | * | Round link Chain-14X64 For SPBF | NL-N-TS2-002-05-01-08 | 993504.14 | 993504.14 | 0 | 993504.14 | 0 | 993504.14 | 993504.14 | 0 | 993504.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 993504.14 | 993504.14 | 0 | 993504.14 | 0
291 | * | Side/Intermediate Grate bar supp for ABG | NL-N-TS2-002-05-01-09 | 4160393.6 | 4160393.6 | 0 | 4160393.6 | 0 | 4160393.6 | 4160393.6 | 0 | 4160393.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4160393.6 | 4160393.6 | 0 | 4160393.6 | 0
292 | * | Roller for ABG 355mm long as per drawing | NL-N-TS2-002-05-01-10 | 1509025.32 | 1509025.32 | 0 | 1509025.32 | 0 | 1509025.32 | 1509025.32 | 0 | 1509025.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509025.32 | 1509025.32 | 0 | 1509025.32 | 0
293 | * | Connecting pin for ABG Supports | NL-N-TS2-002-05-01-11 | 411500.01 | 411500.01 | 0 | 411500.01 | 0 | 411500.01 | 411500.01 | 0 | 411500.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 411500.01 | 411500.01 | 0 | 411500.01 | 0
294 | * | Louver Type Grate Bar Having Length397mm | NL-N-TS2-002-05-01-12 | 6763015.55 | 6763015.55 | 0 | 6763015.55 | 0 | 6763015.55 | 6763015.55 | 0 | 6763015.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6763015.55 | 6763015.55 | 0 | 6763015.55 | 0
295 | * | ABG CAP BEARING A180 | NL-N-TS2-002-05-01-13 | 929790.96 | 929790.96 | 0 | 929790.96 | 0 | 929790.96 | 929790.96 | 0 | 929790.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929790.96 | 929790.96 | 0 | 929790.96 | 0
296 | * | ABG plate link chain complete set | NL-N-TS2-002-05-01-14 | 3051478.28 | 3051478.28 | 0 | 3051478.28 | 0 | 3051478.28 | 3051478.28 | 0 | 3051478.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3051478.28 | 3051478.28 | 0 | 3051478.28 | 0
297 | * | Repl & Recti of Supporting Struct & Cheq | NL-N-TS2-002-05-01-15 | 5908583.89 | 4429696.01 | 1478887.88 | 5908583.89 | 0 | 4429696.01 | 4429696.01 | 0 | 4429696.01 | 0 | 1478887.88 | 0 | 1478887.88 | 1478887.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5908583.89 | 4429696.01 | 1478887.88 | 5908583.89 | 0
298 | * | Belt Conveyor Idler 108X300,108X310 | NL-N-TS2-002-05-01-16 | 428599.22 | 428599.22 | 0 | 428599.22 | 0 | 428599.22 | 428599.22 | 0 | 428599.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428599.22 | 428599.22 | 0 | 428599.22 | 0
299 | * | Replacement of damaged Chequred plate | NL-N-TS2-002-05-01-17 | 123408.32 | 123408.32 | 0 | 123408.32 | 0 | 123408.32 | 123408.32 | 0 | 123408.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123408.32 | 123408.32 | 0 | 123408.32 | 0
300 | * | ABG Drive Shaft Chain Wheel | NL-N-TS2-002-05-01-18 | 1230871.05 | 1230871.05 | 0 | 1230871.05 | 0 | 1230871.05 | 1230871.05 | 0 | 1230871.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230871.05 | 1230871.05 | 0 | 1230871.05 | 0
301 | * | Complete set of Spacer Bar and Tube Asse | NL-N-TS2-002-05-01-19 | 1064049.66 | 1064049.66 | 0 | 1064049.66 | 0 | 1064049.66 | 1064049.66 | 0 | 1064049.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1064049.66 | 1064049.66 | 0 | 1064049.66 | 0
302 | * | ST contract 5 nos ABG overhaul in TPS-II | NL-N-TS2-002-05-01-20 | 7418993.02 | 6383728.02 | 1035265 | 7418993.02 | 0 | 6383728.02 | 6383728.02 | 0 | 6383728.02 | 0 | 1035265 | 0 | 1035265 | 1035265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7418993.02 | 6383728.02 | 1035265 | 7418993.02 | 0
303 | * | RUD Chain coupling connector size 22X86 | NL-N-TS2-002-05-01-21 | 2660000.02 | 2660000.02 | 0 | 2660000.02 | 0 | 2660000.02 | 2660000.02 | 0 | 2660000.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2660000.02 | 2660000.02 | 0 | 2660000.02 | 0
304 | * | ST work for fabrication,erection in ABG | NL-N-TS2-002-05-01-22 | 6355880 | 6078180 | 277700 | 6355880 | 0 | 6095880 | 6095880 | 0 | 6095880 | 0 | 260000 | -17700 | 277700 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6355880 | 6078180 | 277700 | 6355880 | 0
305 | * | Louvre Type Grate bar Having Length 347 | NL-N-TS2-002-05-01-23 | 10508223.41 | 10508223.41 | 0 | 10508223.41 | 0 | 10508223.41 | 10508223.41 | 0 | 10508223.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10508223.41 | 10508223.41 | 0 | 10508223.41 | 0
306 | * | Changing /Rectifi of Damaged Chequ plate | NL-N-TS2-002-05-01-24 | 11635876.26 | 5013766.16 | 6622110.1 | 11635876.26 | 0 | 5013766.16 | 5013766.16 | 0 | 5013766.16 | 0 | 6622110.1 | 0 | 6622110.1 | 6622110.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11635876.26 | 5013766.16 | 6622110.1 | 11635876.26 | 0
307 | * | Side/Intermediate Grate bar support | NL-N-TS2-002-05-01-25 | 6621457.85 | 6621457.85 | 0 | 6621457.85 | 0 | 6621457.85 | 6621457.85 | 0 | 6621457.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6621457.85 | 6621457.85 | 0 | 6621457.85 | 0
308 | * | ABG Plate Link Chain | NL-N-TS2-002-05-01-26 | 3934566.89 | 3934566.89 | 0 | 3934566.89 | 0 | 3934566.89 | 3934566.89 | 0 | 3934566.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3934566.89 | 3934566.89 | 0 | 3934566.89 | 0
309 | * | ABG- COMPLETE SET OF SPACER BAR AND TUBE | NL-N-TS2-002-05-01-27 | 2551836.65 | 2551836.65 | 0 | 2551836.65 | 0 | 238058.57 | 238058.57 | 0 | 238058.57 | 0 | 2313778.08 | 2313778.08 | 0 | 2313778.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551836.65 | 2551836.65 | 0 | 2551836.65 | 0
310 | * | ABG-ROLLER-305MM | NL-N-TS2-002-05-01-28 | 1114269.57 | 1114269.57 | 0 | 1114269.57 | 0 | 1114269.57 | 1114269.57 | 0 | 1114269.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114269.57 | 1114269.57 | 0 | 1114269.57 | 0
311 | * | ABG-ROLLER-355MM | NL-N-TS2-002-05-01-29 | 2659232.95 | 2659232.95 | 0 | 2659232.95 | 0 | 2023195.05 | 2023195.05 | 0 | 2023195.05 | 0 | 636037.9 | 636037.9 | 0 | 636037.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2659232.95 | 2659232.95 | 0 | 2659232.95 | 0
312 | * | IMPORTED ROUND LINK CHAINS 22MMX86MM | NL-N-TS2-002-05-01-30 | 40740000.09 | 40740000.09 | 0 | 40740000.09 | 0 | 0 | 0 | 0 | 0 | 0 | 40740000.09 | 40740000.09 | 0 | 40740000.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40740000.09 | 40740000.09 | 0 | 40740000.09 | 0
313 | * | SEVEN NO OF ABG OVERHAUL | NL-N-TS2-002-05-01-31 | 5152119 | 0 | 5152119 | 5152119 | 0 | 0 | 0 | 0 | 0 | 0 | 5152119 | 0 | 5152119 | 5152119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5152119 | 0 | 5152119 | 5152119 | 0
314 | * |  | NL-N-TS2-002-05-01-32 | 5641146.56 | 0 | 5641146.56 | 5641146.56 | 0 | 0 | 0 | 0 | 0 | 0 | 5641146.56 | 0 | 5641146.56 | 5641146.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5641146.56 | 0 | 5641146.56 | 5641146.56 | 0
315 | * |  | NL-N-TS2-002-05-01-33 | 3538818 | 0 | 3538818 | 3538818 | 0 | 0 | 0 | 0 | 0 | 0 | 3538818 | 0 | 3538818 | 3538818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3538818 | 0 | 3538818 | 3538818 | 0
316 | ** | MILL MAINTENANCE | NL-N-TS2-002-05-02 | 91230053.87 | 78941528.56 | 12288525.31 | 91230053.87 | 0 | 78941528.56 | 78941528.56 | 0 | 78941528.56 | 0 | 12288525.31 | 0 | 12288525.31 | 12288525.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93282053.88 | 78941528.56 | 12288525.31 | 91230053.87 | 2052000.01
317 | * | MILLS AND PF DUCTS | NL-N-TS2-002-05-02-01 | 21074260.09 | 20507859.74 | 566400.35 | 21074260.09 | 0 | 20507859.74 | 20507859.74 | 0 | 20507859.74 | 0 | 566400.35 | 0 | 566400.35 | 566400.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23126260.1 | 20507859.74 | 566400.35 | 21074260.09 | 2052000.01
318 | * | Helical Spring &Visco DamperUnit | NL-N-TS2-002-05-02-02 | 8138236.21 | 8138236.21 | 0 | 8138236.21 | 0 | 8138236.21 | 8138236.21 | 0 | 8138236.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8138236.21 | 8138236.21 | 0 | 8138236.21 | 0
319 | * | Mill double bearing bed frame | NL-N-TS2-002-05-02-03 | 890100 | 890100 | 0 | 890100 | 0 | 890100 | 890100 | 0 | 890100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890100 | 890100 | 0 | 890100 | 0
320 | * | PF Duct lifting & Aligning work sup Ibm | NL-N-TS2-002-05-02-04 | 2320200.03 | 1486800 | 833400.03 | 2320200.03 | 0 | 1486800 | 1486800 | 0 | 1486800 | 0 | 833400.03 | 0 | 833400.03 | 833400.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2320200.03 | 1486800 | 833400.03 | 2320200.03 | 0
321 | * | replace of spring units & visco dampers | NL-N-TS2-002-05-02-05 | 2534640.02 | 2534640 | 0.02 | 2534640.02 | 0 | 2534640 | 2534640 | 0 | 2534640 | 0 | 0.02 | 0 | 0.02 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2534640.02 | 2534640 | 0.02 | 2534640.02 | 0
322 | * | Replace recti classifier platform,Gratin | NL-N-TS2-002-05-02-06 | 4697547.15 | 2936420.22 | 1761126.93 | 4697547.15 | 0 | 2936420.22 | 2936420.22 | 0 | 2936420.22 | 0 | 1761126.93 | 0 | 1761126.93 | 1761126.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4697547.15 | 2936420.22 | 1761126.93 | 4697547.15 | 0
323 | * | Spring unit/visco damper | NL-N-TS2-002-05-02-07 | 8299186.73 | 8299186.73 | 0 | 8299186.73 | 0 | 8299186.73 | 8299186.73 | 0 | 8299186.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8299186.73 | 8299186.73 | 0 | 8299186.73 | 0
324 | * | Replace of Spring Visco dampers st-II | NL-N-TS2-002-05-02-08 | 2534640.02 | 2534640 | 0.02 | 2534640.02 | 0 | 2534640 | 2534640 | 0 | 2534640 | 0 | 0.02 | 0 | 0.02 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2534640.02 | 2534640 | 0.02 | 2534640.02 | 0
325 | * | Mill Door seal collar assemblyfor N110.6 | NL-N-TS2-002-05-02-09 | 11446000 | 11446000 | 0 | 11446000 | 0 | 11446000 | 11446000 | 0 | 11446000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11446000 | 11446000 | 0 | 11446000 | 0
326 | * | Voith Turbo/EPK Connecting Coupling | NL-N-TS2-002-05-02-10 | 9612273.02 | 9612273.02 | 0 | 9612273.02 | 0 | 9612273.02 | 9612273.02 | 0 | 9612273.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9612273.02 | 9612273.02 | 0 | 9612273.02 | 0
327 | * | MILL DOUBLE BEARING SHAFT | NL-N-TS2-002-05-02-11 | 10555372.64 | 10555372.64 | 0 | 10555372.64 | 0 | 10555372.64 | 10555372.64 | 0 | 10555372.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10555372.64 | 10555372.64 | 0 | 10555372.64 | 0
328 | * | REVAMPING-MILL DOOR SEAL COLLAR ASSEMBLY | NL-N-TS2-002-05-02-12 | 4965000.01 | 0 | 4965000.01 | 4965000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 4965000.01 | 0 | 4965000.01 | 4965000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4965000.01 | 0 | 4965000.01 | 4965000.01 | 0
329 | * | PROC-MILL DOUBLE BEARING BED FRAME | NL-N-TS2-002-05-02-13 | 4162597.95 | 0 | 4162597.95 | 4162597.95 | 0 | 0 | 0 | 0 | 0 | 0 | 4162597.95 | 0 | 4162597.95 | 4162597.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4162597.95 | 0 | 4162597.95 | 4162597.95 | 0
330 | ** | PRESSURE PARTS | NL-N-TS2-002-05-03 | 679830459.66 | 121153822.41 | 558661814.11 | 679815636.52 | 14823.14 | 121168645.55 | 121153822.41 | 0 | 121153822.41 | 14823.14 | 558661814.11 | 0 | 558661814.11 | 558661814.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679830459.66 | 121153822.41 | 558661814.11 | 679815636.52 | 14823.14
331 | * | SH3 Outlet Header (Stage-1) | NL-N-TS2-002-05-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | * | Drum Safety Valves (Stage-2) | NL-N-TS2-002-05-03-04 | 7404920.03 | 7404919.99 | 0.04 | 7404920.03 | 0 | 7404919.99 | 7404919.99 | 0 | 7404919.99 | 0 | 0.04 | 0 | 0.04 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7404920.03 | 7404919.99 | 0.04 | 7404920.03 | 0
333 | * | Temperature Control Valves (Stage-2) | NL-N-TS2-002-05-03-06 | 2257641 | 0 | 2257641 | 2257641 | 0 | 0 | 0 | 0 | 0 | 0 | 2257641 | 0 | 2257641 | 2257641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2257641 | 0 | 2257641 | 2257641 | 0
334 | * | Water Lance Pump | NL-N-TS2-002-05-03-09 | 1813850.98 | 1813850.98 | 0 | 1813850.98 | 0 | 1813850.98 | 1813850.98 | 0 | 1813850.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813850.98 | 1813850.98 | 0 | 1813850.98 | 0
335 | * | Automatic Stress Relieving Machine | NL-N-TS2-002-05-03-12 | 372880 | 372880 | 0 | 372880 | 0 | 372880 | 372880 | 0 | 372880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372880 | 372880 | 0 | 372880 | 0
336 | * | Portable Rebound Hardness tester | NL-N-TS2-002-05-03-13 | 198240 | 198240 | 0 | 198240 | 0 | 198240 | 198240 | 0 | 198240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198240 | 198240 | 0 | 198240 | 0
337 | * | Water Wall Tube & Panel Replacement U-4 | NL-N-TS2-002-05-03-14 | 595145.97 | 595145.97 | 0 | 595145.97 | 0 | 595145.97 | 595145.97 | 0 | 595145.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595145.97 | 595145.97 | 0 | 595145.97 | 0
338 | * | Boiler-5 Hanger Inspection&Rectification | NL-N-TS2-002-05-03-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | * | Water Wall Tube,Panel Replacement U-6&2 | NL-N-TS2-002-05-03-16 | 1651570.5 | 1651570.5 | 0 | 1651570.5 | 0 | 1651570.5 | 1651570.5 | 0 | 1651570.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1651570.5 | 1651570.5 | 0 | 1651570.5 | 0
340 | * | Replace of Drain,Vent,Impulse Line&Valve | NL-N-TS2-002-05-03-17 | 3803065.67 | 998841.12 | 2789401.41 | 3788242.53 | 14823.14 | 1013664.26 | 998841.12 | 0 | 998841.12 | 14823.14 | 2789401.41 | 0 | 2789401.41 | 2789401.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3803065.67 | 998841.12 | 2789401.41 | 3788242.53 | 14823.14
341 | * | Replacement of WW Panels in Stage-1&2 | NL-N-TS2-002-05-03-18 | 2204377.3 | 2204377.3 | 0 | 2204377.3 | 0 | 2204377.3 | 2204377.3 | 0 | 2204377.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2204377.3 | 2204377.3 | 0 | 2204377.3 | 0
342 | * | HRH Safety Valve Tap-Off Line Bend Pipe | NL-N-TS2-002-05-03-19 | 1828205.99 | 1828205.99 | 0 | 1828205.99 | 0 | 1828205.99 | 1828205.99 | 0 | 1828205.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1828205.99 | 1828205.99 | 0 | 1828205.99 | 0
343 | * | Safety Valve Spares | NL-N-TS2-002-05-03-24 | 2088271.46 | 2088271.46 | 0 | 2088271.46 | 0 | 2088271.46 | 2088271.46 | 0 | 2088271.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2088271.46 | 2088271.46 | 0 | 2088271.46 | 0
344 | * | Thickness Survey -Boiler pressure Parts | NL-N-TS2-002-05-03-25 | 1258352.83 | 1258352.83 | 0 | 1258352.83 | 0 | 1258352.83 | 1258352.83 | 0 | 1258352.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258352.83 | 1258352.83 | 0 | 1258352.83 | 0
345 | * | Replacement of WW Panels/ST-1&2(2022-23) | NL-N-TS2-002-05-03-26 | 13658204.49 | 13658204.49 | 0 | 13658204.49 | 0 | 13658204.49 | 13658204.49 | 0 | 13658204.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13658204.49 | 13658204.49 | 0 | 13658204.49 | 0
346 | * | Refractory Work inside RSD for 7 Boilers | NL-N-TS2-002-05-03-27 | 1387542.48 | 1387542.48 | 0 | 1387542.48 | 0 | 1387542.48 | 1387542.48 | 0 | 1387542.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1387542.48 | 1387542.48 | 0 | 1387542.48 | 0
347 | * | Procurement of fuel oil line pipes | NL-N-TS2-002-05-03-29 | 6590010.92 | 6584693.82 | 5317.1 | 6590010.92 | 0 | 6584693.82 | 6584693.82 | 0 | 6584693.82 | 0 | 5317.1 | 0 | 5317.1 | 5317.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6590010.92 | 6584693.82 | 5317.1 | 6590010.92 | 0
348 | * | Replacement of Insulation and Cladding | NL-N-TS2-002-05-03-30 | 74278330.69 | 30300223.08 | 43978107.61 | 74278330.69 | 0 | 30300223.08 | 30300223.08 | 0 | 30300223.08 | 0 | 43978107.61 | 0 | 43978107.61 | 43978107.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74278330.69 | 30300223.08 | 43978107.61 | 74278330.69 | 0
349 | * | Procurement of FCS MOVs for replacement | NL-N-TS2-002-05-03-31 | 2485080 | 2485080 | 0 | 2485080 | 0 | 2485080 | 2485080 | 0 | 2485080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2485080 | 2485080 | 0 | 2485080 | 0
350 | * | Hopper S type &Corner WW Panels for St-I | NL-N-TS2-002-05-03-32 | 7375592.01 | 7375592.01 | 0 | 7375592.01 | 0 | 7375592.01 | 7375592.01 | 0 | 7375592.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7375592.01 | 7375592.01 | 0 | 7375592.01 | 0
351 | * | Replacement of ECO outer bend St-I | NL-N-TS2-002-05-03-33 | 7523680.03 | 5168282 | 2355398.03 | 7523680.03 | 0 | 5168282 | 5168282 | 0 | 5168282 | 0 | 2355398.03 | 0 | 2355398.03 | 2355398.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7523680.03 | 5168282 | 2355398.03 | 7523680.03 | 0
352 | * | Water lance casing Top/bottom/Vertical | NL-N-TS2-002-05-03-34 | 547053.92 | 547053.92 | 0 | 547053.92 | 0 | 547053.92 | 547053.92 | 0 | 547053.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 547053.92 | 547053.92 | 0 | 547053.92 | 0
353 | * | Procurement of FAS MOVs for stage I&II | NL-N-TS2-002-05-03-35 | 2450860 | 2450860 | 0 | 2450860 | 0 | 2450860 | 2450860 | 0 | 2450860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450860 | 2450860 | 0 | 2450860 | 0
354 | * | Replacement of HRH SV Tap off bend U-3 | NL-N-TS2-002-05-03-37 | 1568696.03 | 1105896 | 462800.03 | 1568696.03 | 0 | 1105896 | 1105896 | 0 | 1105896 | 0 | 462800.03 | 0 | 462800.03 | 462800.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568696.03 | 1105896 | 462800.03 | 1568696.03 | 0
355 | * | Replacement of HRH SV Tap off bend U-1 | NL-N-TS2-002-05-03-38 | 552948.03 | 552948 | 0.03 | 552948.03 | 0 | 552948 | 552948 | 0 | 552948 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552948.03 | 552948 | 0.03 | 552948.03 | 0
356 | * | Procurement of SSB Chains | NL-N-TS2-002-05-03-39 | 1894449.8 | 1894449.8 | 0 | 1894449.8 | 0 | 1894449.8 | 1894449.8 | 0 | 1894449.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1894449.8 | 1894449.8 | 0 | 1894449.8 | 0
357 | * | Procu of St-II SSB Puppet valve lever | NL-N-TS2-002-05-03-40 | 4773265.2 | 4773265.2 | 0 | 4773265.2 | 0 | 4773265.2 | 4773265.2 | 0 | 4773265.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4773265.2 | 4773265.2 | 0 | 4773265.2 | 0
358 | * | Procure of fuel oil line pipe fittings | NL-N-TS2-002-05-03-41 | 747223.4 | 0 | 747223.4 | 747223.4 | 0 | 0 | 0 | 0 | 0 | 0 | 747223.4 | 0 | 747223.4 | 747223.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 747223.4 | 0 | 747223.4 | 747223.4 | 0
359 | * | Purchase of pipes and tubes for drains | NL-N-TS2-002-05-03-42 | 2571249.51 | 1396118.34 | 1175131.17 | 2571249.51 | 0 | 1396118.34 | 1396118.34 | 0 | 1396118.34 | 0 | 1175131.17 | 0 | 1175131.17 | 1175131.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571249.51 | 1396118.34 | 1175131.17 | 2571249.51 | 0
360 | * | Conducting Thickness survey and oxide | NL-N-TS2-002-05-03-43 | 1412370.88 | 1331752.74 | 80618.14 | 1412370.88 | 0 | 1331752.74 | 1331752.74 | 0 | 1331752.74 | 0 | 80618.14 | 0 | 80618.14 | 80618.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1412370.88 | 1331752.74 | 80618.14 | 1412370.88 | 0
361 | * | Replacement of W/w Tubes and panels | NL-N-TS2-002-05-03-44 | 9976875.02 | 0 | 9976875.02 | 9976875.02 | 0 | 0 | 0 | 0 | 0 | 0 | 9976875.02 | 0 | 9976875.02 | 9976875.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9976875.02 | 0 | 9976875.02 | 9976875.02 | 0
362 | * | Procurement of water lancefunnel,Dogplat | NL-N-TS2-002-05-03-45 | 1486463.38 | 1486463.38 | 0 | 1486463.38 | 0 | 1486463.38 | 1486463.38 | 0 | 1486463.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1486463.38 | 1486463.38 | 0 | 1486463.38 | 0
363 | * | RLA Study in TPS-II Boiler of Unit-5 | NL-N-TS2-002-05-03-46 | 824937.8 | 792938.94 | 31998.86 | 824937.8 | 0 | 792938.94 | 792938.94 | 0 | 792938.94 | 0 | 31998.86 | 0 | 31998.86 | 31998.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824937.8 | 792938.94 | 31998.86 | 824937.8 | 0
364 | * | Replacement of Eco coil outer loop bend | NL-N-TS2-002-05-03-47 | 12415800.01 | 0 | 12415800.01 | 12415800.01 | 0 | 0 | 0 | 0 | 0 | 0 | 12415800.01 | 0 | 12415800.01 | 12415800.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12415800.01 | 0 | 12415800.01 | 12415800.01 | 0
365 | * | Replacement of Boiler drain,Vent& Impuls | NL-N-TS2-002-05-03-48 | 8744700.01 | 0 | 8744700.01 | 8744700.01 | 0 | 0 | 0 | 0 | 0 | 0 | 8744700.01 | 0 | 8744700.01 | 8744700.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8744700.01 | 0 | 8744700.01 | 8744700.01 | 0
366 | * | Procurement of economiser Outer Bend | NL-N-TS2-002-05-03-49 | 4674003.6 | 0 | 4674003.6 | 4674003.6 | 0 | 0 | 0 | 0 | 0 | 0 | 4674003.6 | 0 | 4674003.6 | 4674003.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4674003.6 | 0 | 4674003.6 | 4674003.6 | 0
367 | * | Procurement of economiser long Bends | NL-N-TS2-002-05-03-50 | 3791966.45 | 0 | 3791966.45 | 3791966.45 | 0 | 0 | 0 | 0 | 0 | 0 | 3791966.45 | 0 | 3791966.45 | 3791966.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3791966.45 | 0 | 3791966.45 | 3791966.45 | 0
368 | * | Procurement of High Pressure HOV for PRP | NL-N-TS2-002-05-03-51 | 24179843.3 | 0 | 24179843.3 | 24179843.3 | 0 | 0 | 0 | 0 | 0 | 0 | 24179843.3 | 0 | 24179843.3 | 24179843.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24179843.3 | 0 | 24179843.3 | 24179843.3 | 0
369 | * | Water Lance 8 stage centrifugal pump | NL-N-TS2-002-05-03-52 | 2955348 | 2955348 | 0 | 2955348 | 0 | 2955348 | 2955348 | 0 | 2955348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2955348 | 2955348 | 0 | 2955348 | 0
370 | * | Boiler J row pipe supporting Structure | NL-N-TS2-002-05-03-53 | 6205500.01 | 0 | 6205500.01 | 6205500.01 | 0 | 0 | 0 | 0 | 0 | 0 | 6205500.01 | 0 | 6205500.01 | 6205500.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6205500.01 | 0 | 6205500.01 | 6205500.01 | 0
371 | * | Damaged Boiler Auxiliary Structures Rect | NL-N-TS2-002-05-03-54 | 868101.03 | 838440.03 | 29661 | 868101.03 | 0 | 838440.03 | 838440.03 | 0 | 838440.03 | 0 | 29661 | 0 | 29661 | 29661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 868101.03 | 838440.03 | 29661 | 868101.03 | 0
372 | * | Purchase of Seamless Carbon Steel pipes | NL-N-TS2-002-05-03-55 | 31581166 | 0 | 31581166 | 31581166 | 0 | 0 | 0 | 0 | 0 | 0 | 31581166 | 0 | 31581166 | 31581166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31581166 | 0 | 31581166 | 31581166 | 0
373 | * | Procurement of Water wall S panel St-I | NL-N-TS2-002-05-03-56 | 24101976.47 | 0 | 24101976.47 | 24101976.47 | 0 | 0 | 0 | 0 | 0 | 0 | 24101976.47 | 0 | 24101976.47 | 24101976.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24101976.47 | 0 | 24101976.47 | 24101976.47 | 0
374 | * | Replacement of Economiser Coil Bend-St-I | NL-N-TS2-002-05-03-57 | 9532439.57 | 2193620.35 | 7338819.22 | 9532439.57 | 0 | 2193620.35 | 2193620.35 | 0 | 2193620.35 | 0 | 7338819.22 | 0 | 7338819.22 | 7338819.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9532439.57 | 2193620.35 | 7338819.22 | 9532439.57 | 0
375 | * | Rep of damaged water wall tubes&Panels | NL-N-TS2-002-05-03-58 | 13286999.26 | 10913265.94 | 2373733.32 | 13286999.26 | 0 | 10913265.94 | 10913265.94 | 0 | 10913265.94 | 0 | 2373733.32 | 0 | 2373733.32 | 2373733.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13286999.26 | 10913265.94 | 2373733.32 | 13286999.26 | 0
376 | * | SSB SPARES PURCHASE | NL-N-TS2-002-05-03-59 | 2985990 | 0 | 2985990 | 2985990 | 0 | 0 | 0 | 0 | 0 | 0 | 2985990 | 0 | 2985990 | 2985990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2985990 | 0 | 2985990 | 2985990 | 0
377 | * | SKY CLIMBERS | NL-N-TS2-002-05-03-60 | 16884502 | 0 | 16884502 | 16884502 | 0 | 0 | 0 | 0 | 0 | 0 | 16884502 | 0 | 16884502 | 16884502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16884502 | 0 | 16884502 | 16884502 | 0
378 | * | RLA STUDY IN UNIT 1 BOILER AND ITS AUX | NL-N-TS2-002-05-03-61 | 1539100.29 | 547127.75 | 991972.54 | 1539100.29 | 0 | 547127.75 | 547127.75 | 0 | 547127.75 | 0 | 991972.54 | 0 | 991972.54 | 991972.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1539100.29 | 547127.75 | 991972.54 | 1539100.29 | 0
379 | * | PROC STRAIGHT TYPE WATERWALL PANELS S1 | NL-N-TS2-002-05-03-62 | 26435447.5 | 0 | 26435447.5 | 26435447.5 | 0 | 0 | 0 | 0 | 0 | 0 | 26435447.5 | 0 | 26435447.5 | 26435447.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26435447.5 | 0 | 26435447.5 | 26435447.5 | 0
380 | * | PROC- WW HOPPER BENDS -STAGE2 | NL-N-TS2-002-05-03-63 | 4460940 | 0 | 4460940 | 4460940 | 0 | 0 | 0 | 0 | 0 | 0 | 4460940 | 0 | 4460940 | 4460940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4460940 | 0 | 4460940 | 4460940 | 0
381 | * |  | NL-N-TS2-002-05-03-64 | 5836598.6 | 0 | 5836598.6 | 5836598.6 | 0 | 0 | 0 | 0 | 0 | 0 | 5836598.6 | 0 | 5836598.6 | 5836598.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5836598.6 | 0 | 5836598.6 | 5836598.6 | 0
382 | * |  | NL-N-TS2-002-05-03-65 | 13406180 | 0 | 13406180 | 13406180 | 0 | 0 | 0 | 0 | 0 | 0 | 13406180 | 0 | 13406180 | 13406180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13406180 | 0 | 13406180 | 13406180 | 0
383 | * |  | NL-N-TS2-002-05-03-66 | 23472794.4 | 0 | 23472794.4 | 23472794.4 | 0 | 0 | 0 | 0 | 0 | 0 | 23472794.4 | 0 | 23472794.4 | 23472794.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23472794.4 | 0 | 23472794.4 | 23472794.4 | 0
384 | * |  | NL-N-TS2-002-05-03-67 | 10552150.64 | 0 | 10552150.64 | 10552150.64 | 0 | 0 | 0 | 0 | 0 | 0 | 10552150.64 | 0 | 10552150.64 | 10552150.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10552150.64 | 0 | 10552150.64 | 10552150.64 | 0
385 | * |  | NL-N-TS2-002-05-03-68 | 7960811.42 | 0 | 7960811.42 | 7960811.42 | 0 | 0 | 0 | 0 | 0 | 0 | 7960811.42 | 0 | 7960811.42 | 7960811.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7960811.42 | 0 | 7960811.42 | 7960811.42 | 0
386 | * |  | NL-N-TS2-002-05-03-69 | 9048729.45 | 0 | 9048729.45 | 9048729.45 | 0 | 0 | 0 | 0 | 0 | 0 | 9048729.45 | 0 | 9048729.45 | 9048729.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9048729.45 | 0 | 9048729.45 | 9048729.45 | 0
387 | * |  | NL-N-TS2-002-05-03-70 | 11260169.12 | 0 | 11260169.12 | 11260169.12 | 0 | 0 | 0 | 0 | 0 | 0 | 11260169.12 | 0 | 11260169.12 | 11260169.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11260169.12 | 0 | 11260169.12 | 11260169.12 | 0
388 | * |  | NL-N-TS2-002-05-03-71 | 12194741 | 0 | 12194741 | 12194741 | 0 | 0 | 0 | 0 | 0 | 0 | 12194741 | 0 | 12194741 | 12194741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12194741 | 0 | 12194741 | 12194741 | 0
389 | * |  | NL-N-TS2-002-05-03-72 | 957500.6 | 0 | 957500.6 | 957500.6 | 0 | 0 | 0 | 0 | 0 | 0 | 957500.6 | 0 | 957500.6 | 957500.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 957500.6 | 0 | 957500.6 | 957500.6 | 0
390 | * |  | NL-N-TS2-002-05-03-73 | 2995613.51 | 0 | 2995613.51 | 2995613.51 | 0 | 0 | 0 | 0 | 0 | 0 | 2995613.51 | 0 | 2995613.51 | 2995613.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995613.51 | 0 | 2995613.51 | 2995613.51 | 0
391 | * |  | NL-N-TS2-002-05-03-74 | 2386190.1 | 0 | 2386190.1 | 2386190.1 | 0 | 0 | 0 | 0 | 0 | 0 | 2386190.1 | 0 | 2386190.1 | 2386190.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2386190.1 | 0 | 2386190.1 | 2386190.1 | 0
392 | * |  | NL-N-TS2-002-05-03-75 | 200533802 | 0 | 200533802 | 200533802 | 0 | 0 | 0 | 0 | 0 | 0 | 200533802 | 0 | 200533802 | 200533802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200533802 | 0 | 200533802 | 200533802 | 0
393 | * |  | NL-N-TS2-002-05-03-76 | 17000000 | 0 | 17000000 | 17000000 | 0 | 0 | 0 | 0 | 0 | 0 | 17000000 | 0 | 17000000 | 17000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000000 | 0 | 17000000 | 17000000 | 0
394 | ** | RAPH & FANS | NL-N-TS2-002-05-04 | 298224054.21 | 163331929.34 | 127064813.84 | 290407464.17 | 7816590.04 | 171159240.37 | 163331929.34 | 0 | 163342650.33 | 7816590.04 | 127064813.84 | 0 | 127064813.84 | 127064813.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299500105.59 | 163331929.34 | 127064813.84 | 290407464.17 | 9092641.42
395 | * | RAPH BASKETS AND BEARINGS | NL-N-TS2-002-05-04-01 | 29453703.18 | 20105055.28 | 9348647.9 | 29453703.18 | 0 | 20105055.28 | 20105055.28 | 0 | 20105055.28 | 0 | 9348647.9 | 0 | 9348647.9 | 9348647.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29453703.18 | 20105055.28 | 9348647.9 | 29453703.18 | 0
396 | * | Lub Oil Pump for RAPH | NL-N-TS2-002-05-04-02 | 702336 | 702336 | 0 | 702336 | 0 | 702336 | 702336 | 0 | 702336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702336 | 702336 | 0 | 702336 | 0
397 | * | Electric operate Hydrulic Synhns of RAPH | NL-N-TS2-002-05-04-03 | 1618272 | 1618272 | 0 | 1618272 | 0 | 1618272 | 1618272 | 0 | 1618272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1618272 | 1618272 | 0 | 1618272 | 0
398 | * | Single Bellow Compensator Corner Piece | NL-N-TS2-002-05-04-04 | 446438.08 | 446438.08 | 0 | 446438.08 | 0 | 446438.08 | 446438.08 | 0 | 446438.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446438.08 | 446438.08 | 0 | 446438.08 | 0
399 | * | Electric Power Winch - 5 Ton Capacity | NL-N-TS2-002-05-04-06 | 1087716 | 1087716 | 0 | 1087716 | 0 | 1087716 | 1087716 | 0 | 1087716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1087716 | 1087716 | 0 | 1087716 | 0
400 | * | Spiral Bevel Gear and Pinion | NL-N-TS2-002-05-04-07 | 95968.82 | 95968.82 | 0 | 95968.82 | 0 | 95968.82 | 95968.82 | 0 | 95968.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95968.82 | 95968.82 | 0 | 95968.82 | 0
401 |  |  | spira | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | * | RAPH Stage-I Gear Box | NL-N-TS2-002-05-04-10 | 1065370.35 | 1060060.32 | 5310.03 | 1065370.35 | 0 | 1060060.32 | 1060060.32 | 0 | 1060060.32 | 0 | 5310.03 | 0 | 5310.03 | 5310.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1065370.35 | 1060060.32 | 5310.03 | 1065370.35 | 0
403 |  | Bore corre work GB housing of Raph st-I | NL-N-TS2-002-05-04-10-01 | 354000.03 | 348690 | 5310.03 | 354000.03 | 0 | 348690 | 348690 | 0 | 348690 | 0 | 5310.03 | 0 | 5310.03 | 5310.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354000.03 | 348690 | 5310.03 | 354000.03 | 0
404 |  | Gear Box spares for stage-1 | NL-N-TS2-002-05-04-10-02 | 711370.32 | 711370.32 | 0 | 711370.32 | 0 | 711370.32 | 711370.32 | 0 | 711370.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711370.32 | 711370.32 | 0 | 711370.32 | 0
405 | * | ID fan Blades with Countersunk Screws | NL-N-TS2-002-05-04-14 | 7827311.03 | 0 | 0 | 10720.99 | 7816590.04 | 7827311.03 | 0 | 0 | 10720.99 | 7816590.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7827311.03 | 0 | 0 | 10720.99 | 7816590.04
406 |  |  | open | 0 | 2781318.51 | 0 | 2781318.51 | -2781318.51 | 0 | 2781318.51 | 0 | 2781318.51 | -2781318.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781318.51 | 0 | 2781318.51 | -2781318.51
407 |  |  | ope | 0 | 3024188.71 | 0 | 3024188.71 | -3024188.71 | 0 | 3024188.71 | 0 | 3024188.71 | -3024188.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3024188.71 | 0 | 3024188.71 | -3024188.71
408 | * | RAPH HE Basket | NL-N-TS2-002-05-04-21 | 9991927.13 | 9991927.13 | 0 | 9991927.13 | 0 | 9991927.13 | 9991927.13 | 0 | 9991927.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9991927.13 | 9991927.13 | 0 | 9991927.13 | 0
409 | * | Dambers Gearbox | NL-N-TS2-002-05-04-24 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0
410 |  | Damper Gear box-AD2/GD1/GD2/AD3,4&5 | NL-N-TS2-002-05-04-24-01 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451625.18 | 2451625.18 | 0 | 2451625.18 | 0
411 | * | thochoid lub oil pump for St-II gear box | NL-N-TS2-002-05-04-28 | 375240 | 375240 | 0 | 375240 | 0 | 375240 | 375240 | 0 | 375240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375240 | 375240 | 0 | 375240 | 0
412 | * | Lub oil pump for SB&GB of RAPH Stage-II | NL-N-TS2-002-05-04-29 | 1974000.62 | 1974000.02 | 0.6 | 1974000.62 | 0 | 1974000.02 | 1974000.02 | 0 | 1974000.02 | 0 | 0.6 | 0 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1974000.62 | 1974000.02 | 0.6 | 1974000.62 | 0
413 | * | Disman and Erection of RSD below 15 ML | NL-N-TS2-002-05-04-30 | 9412800.03 | 778800 | 8634000.03 | 9412800.03 | 0 | 778800 | 778800 | 0 | 778800 | 0 | 8634000.03 | 0 | 8634000.03 | 8634000.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9412800.03 | 778800 | 8634000.03 | 9412800.03 | 0
414 | * | Single/Double fold bellow and corner pie | NL-N-TS2-002-05-04-31 | 1595420.44 | 1595420.44 | 0 | 1595420.44 | 0 | 1595420.44 | 1595420.44 | 0 | 1595420.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1595420.44 | 1595420.44 | 0 | 1595420.44 | 0
415 | * | ID Fan Blades | NL-N-TS2-002-05-04-32 | 10974000 | 10974000 | 0 | 10974000 | 0 | 10974000 | 10974000 | 0 | 10974000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10974000 | 10974000 | 0 | 10974000 | 0
416 | * | Replacement of Support & Guide bearing | NL-N-TS2-002-05-04-33 | 2474516.67 | 1237258.32 | 1237258.35 | 2474516.67 | 0 | 1237258.32 | 1237258.32 | 0 | 1237258.32 | 0 | 1237258.35 | 0 | 1237258.35 | 1237258.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2474516.67 | 1237258.32 | 1237258.35 | 2474516.67 | 0
417 | * | ID Fan Bearing shaft | NL-N-TS2-002-05-04-34 | 4600000 | 4600000 | 0 | 4600000 | 0 | 4600000 | 4600000 | 0 | 4600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600000 | 4600000 | 0 | 4600000 | 0
418 | * | FD fan Impeller blades with Cylindrical | NL-N-TS2-002-05-04-35 | 7210000 | 7210000 | 0 | 7210000 | 0 | 7210000 | 7210000 | 0 | 7210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7210000 | 7210000 | 0 | 7210000 | 0
419 | * | ID Fan Pressure Releif valves | NL-N-TS2-002-05-04-36 | 2582999.98 | 2582999.98 | 0 | 2582999.98 | 0 | 2582999.98 | 2582999.98 | 0 | 2582999.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2582999.98 | 2582999.98 | 0 | 2582999.98 | 0
420 | * | SEISA GEAR BOX FOR STAGE-II RAPH MAIN DR | NL-N-TS2-002-05-04-37 | 37524000 | 37524000 | 0 | 37524000 | 0 | 37524000 | 37524000 | 0 | 37524000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37524000 | 37524000 | 0 | 37524000 | 0
421 | * | Stage-I RAPH BASKETS Spares | NL-N-TS2-002-05-04-38 | 56920811.77 | 56920811.77 | 0 | 56920811.77 | 0 | 56920811.77 | 56920811.77 | 0 | 56920811.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56920811.77 | 56920811.77 | 0 | 56920811.77 | 0
422 | * | Assembly of heating Element Hot and cold | NL-N-TS2-002-05-04-39 | 41094625.22 | 0 | 41094625.22 | 41094625.22 | 0 | 0 | 0 | 0 | 0 | 0 | 41094625.22 | 0 | 41094625.22 | 41094625.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41094625.22 | 0 | 41094625.22 | 41094625.22 | 0
423 | * | ID/FD fan lub oil cooler-satage-II | NL-N-TS2-002-05-04-40 | 1187939.86 | 0 | 1187939.86 | 1187939.86 | 0 | 0 | 0 | 0 | 0 | 0 | 1187939.86 | 0 | 1187939.86 | 1187939.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2463991.24 | 0 | 1187939.86 | 1187939.86 | 1276051.38
424 | * | ID fan impeller blades & bearing | NL-N-TS2-002-05-04-41 | 54429121.4 | 0 | 54429121.4 | 54429121.4 | 0 | 0 | 0 | 0 | 0 | 0 | 54429121.4 | 0 | 54429121.4 | 54429121.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54429121.4 | 0 | 54429121.4 | 54429121.4 | 0
425 | * | RAPH PRV & LOP for Stage-I | NL-N-TS2-002-05-04-42 | 2372980 | 0 | 2372980 | 2372980 | 0 | 0 | 0 | 0 | 0 | 0 | 2372980 | 0 | 2372980 | 2372980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2372980 | 0 | 2372980 | 2372980 | 0
426 | * |  | NL-N-TS2-002-05-04-43 | 8754930.45 | 0 | 8754930.45 | 8754930.45 | 0 | 0 | 0 | 0 | 0 | 0 | 8754930.45 | 0 | 8754930.45 | 8754930.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8754930.45 | 0 | 8754930.45 | 8754930.45 | 0
427 | *** | C & I | NL-N-TS2-002-06 | 944871479.19 | 315818933.38 | 629052545.81 | 944871479.19 | 0 | 300631953.12 | 300599503.01 | 0 | 300599503.01 | 32450.11 | 644239526.07 | 15219430.37 | 629052545.81 | 644271976.18 | -32450.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944871479.19 | 315818933.38 | 629052545.81 | 944871479.19 | 0
428 | ** | Slag Conveyor camera and TV replaceme | NL-N-TS2-002-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | ** | Temperature transmitter | NL-N-TS2-002-06-02 | 1684056.08 | 1684056.08 | 0 | 1684056.08 | 0 | 1684056.08 | 1684056.08 | 0 | 1684056.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684056.08 | 1684056.08 | 0 | 1684056.08 | 0
430 | ** | Water Lance spares- BV, Freq conv, Choke | NL-N-TS2-002-06-09 | 2303180.93 | 2303180.93 | 0 | 2303180.93 | 0 | 0 | 0 | 0 | 0 | 0 | 2303180.93 | 2303180.93 | 0 | 2303180.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2303180.93 | 2303180.93 | 0 | 2303180.93 | 0
431 | ** | CO Analyser | NL-N-TS2-002-06-11 | 2076405 | 0 | 2076405 | 2076405 | 0 | 0 | 0 | 0 | 0 | 0 | 2076405 | 0 | 2076405 | 2076405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2076405 | 0 | 2076405 | 2076405 | 0
432 | ** | Flame Scanner (OIL) | NL-N-TS2-002-06-13 | 2277375.9 | 2277375.9 | 0 | 2277375.9 | 0 | 2277375.9 | 2277375.9 | 0 | 2277375.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2277375.9 | 2277375.9 | 0 | 2277375.9 | 0
433 | ** | Thermal Imaging camera | NL-N-TS2-002-06-14 | 826000 | 826000 | 0 | 826000 | 0 | 826000 | 826000 | 0 | 826000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826000 | 826000 | 0 | 826000 | 0
434 | ** | Zirconia Oxygen Analyser & Spares | NL-N-TS2-002-06-15 | 8009162.61 | 8009162.61 | 0 | 8009162.61 | 0 | 8009162.61 | 8009162.61 | 0 | 8009162.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8009162.61 | 8009162.61 | 0 | 8009162.61 | 0
435 | ** | Flame Scanner (LIGNITE) | NL-N-TS2-002-06-16 | 1801231.28 | 1801231.28 | 0 | 1801231.28 | 0 | 1801231.28 | 1801231.28 | 0 | 1801231.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801231.28 | 1801231.28 | 0 | 1801231.28 | 0
436 | ** | Hydrogen Purity Analyser | NL-N-TS2-002-06-17 | 6226614.44 | 6226614.44 | 0 | 6226614.44 | 0 | 6226614.44 | 6226614.44 | 0 | 6226614.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6226614.44 | 6226614.44 | 0 | 6226614.44 | 0
437 | ** | Chlorine Leak Detector & Scanner | NL-N-TS2-002-06-18 | 365890 | 0 | 365890 | 365890 | 0 | 0 | 0 | 0 | 0 | 0 | 365890 | 0 | 365890 | 365890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365890 | 0 | 365890 | 365890 | 0
438 | ** | Ultra Sonic Flow Meters | NL-N-TS2-002-06-19 | 1100888.26 | 1100888.26 | 0 | 1100888.26 | 0 | 1100888.26 | 1100888.26 | 0 | 1100888.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100888.26 | 1100888.26 | 0 | 1100888.26 | 0
439 | ** | Coriolis Mass Flow Meters With Tanker Un | NL-N-TS2-002-06-23 | 6646586 | 6646586 | 0 | 6646586 | 0 | 6646586 | 6646586 | 0 | 6646586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6646586 | 6646586 | 0 | 6646586 | 0
440 | ** | Opacity Monitors | NL-N-TS2-002-06-24 | 1258556.98 | 1258556.98 | 0 | 1258556.98 | 0 | 1258556.98 | 1258556.98 | 0 | 1258556.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258556.98 | 1258556.98 | 0 | 1258556.98 | 0
441 | ** | Gas Detectors-Portable | NL-N-TS2-002-06-25 | 139649.99 | 139649.99 | 0 | 139649.99 | 0 | 139649.99 | 139649.99 | 0 | 139649.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139649.99 | 139649.99 | 0 | 139649.99 | 0
442 | ** | Coriolis Flow Meters for Boiler HFO line | NL-N-TS2-002-06-26 | 6153700 | 6153700 | 0 | 6153700 | 0 | 6153700 | 6153700 | 0 | 6153700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6153700 | 6153700 | 0 | 6153700 | 0
443 | ** | Hydrogen Dew Point Meters | NL-N-TS2-002-06-27 | 1138700 | 1138700 | 0 | 1138700 | 0 | 1138700 | 1138700 | 0 | 1138700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1138700 | 1138700 | 0 | 1138700 | 0
444 | ** | CPU with LAN & LCM Power Controller | NL-N-TS2-002-06-28 | 9027000 | 9027000 | 0 | 9027000 | 0 | 9027000 | 9027000 | 0 | 9027000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9027000 | 9027000 | 0 | 9027000 | 0
445 | ** | SWAS with Wet & Dry Panel Analysers | NL-N-TS2-002-06-29 | 28461837.42 | 12916249.44 | 15545587.98 | 28461837.42 | 0 | 0 | 0 | 0 | 0 | 0 | 28461837.42 | 12916249.44 | 15545587.98 | 28461837.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28461837.42 | 12916249.44 | 15545587.98 | 28461837.42 | 0
446 | ** | Hydrogen Gas Density Analyser | NL-N-TS2-002-06-30 | 952850 | 952850 | 0 | 952850 | 0 | 952850 | 952850 | 0 | 952850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952850 | 952850 | 0 | 952850 | 0
447 | ** | Control System and HMI for Water Lancer | NL-N-TS2-002-06-31 | 29500 | 0 | 29500 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 29500 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 29500 | 29500 | 0
448 | ** | Electronic DLI for Boiler Drum | NL-N-TS2-002-06-32 | 295000 | 0 | 295000 | 295000 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 0 | 295000 | 295000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295000 | 0 | 295000 | 295000 | 0
449 | ** | Common Monitoring Controller for WCTP | NL-N-TS2-002-06-33 | 3929400 | 0 | 3929400 | 3929400 | 0 | 0 | 0 | 0 | 0 | 0 | 3929400 | 0 | 3929400 | 3929400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3929400 | 0 | 3929400 | 3929400 | 0
450 | ** | Steam & Water Analysis System-Stage-I | NL-N-TS2-002-06-34 | 2050722 | 2050722 | 0 | 2050722 | 0 | 2050722 | 2050722 | 0 | 2050722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050722 | 2050722 | 0 | 2050722 | 0
451 | ** | Single Compartment Temp Transmitter | NL-N-TS2-002-06-35 | 2248815 | 0 | 2248815 | 2248815 | 0 | 0 | 0 | 0 | 0 | 0 | 2248815 | 0 | 2248815 | 2248815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2248815 | 0 | 2248815 | 2248815 | 0
452 | ** | Positioner Cylinder for BFP Scoop | NL-N-TS2-002-06-36 | 1973640.02 | 1973640.02 | 0 | 1973640.02 | 0 | 1973640.02 | 1973640.02 | 0 | 1973640.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1973640.02 | 1973640.02 | 0 | 1973640.02 | 0
453 | ** | Erection of Venturi&Impules Line/U-4,6,7 | NL-N-TS2-002-06-37 | 3159450 | 2933775 | 225675 | 3159450 | 0 | 2933775 | 2933775 | 0 | 2933775 | 0 | 225675 | 0 | 225675 | 225675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3159450 | 2933775 | 225675 | 3159450 | 0
454 | ** | Erection of Venturi&Impules Line/Unit-1 | NL-N-TS2-002-06-38 | 1215282 | 1173694.08 | 41587.92 | 1215282 | 0 | 1173694.08 | 1173694.08 | 0 | 1173694.08 | 0 | 41587.92 | 0 | 41587.92 | 41587.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215282 | 1173694.08 | 41587.92 | 1215282 | 0
455 | ** | Effluent Outlet Flow measurement System | NL-N-TS2-002-06-39 | 649000 | 616549.89 | 32450.11 | 649000 | 0 | 649000 | 616549.89 | 0 | 616549.89 | 32450.11 | 0 | 0 | 32450.11 | 32450.11 | -32450.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649000 | 616549.89 | 32450.11 | 649000 | 0
456 | ** | water lanceblowing valve GSR | NL-N-TS2-002-06-56 | 1390512 | 1390512 | 0 | 1390512 | 0 | 1390512 | 1390512 | 0 | 1390512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1390512 | 1390512 | 0 | 1390512 | 0
457 | ** | Turbo Supervisory instrument modules 12 | NL-N-TS2-002-06-57 | 9468492.45 | 0 | 9468492.45 | 9468492.45 | 0 | 0 | 0 | 0 | 0 | 0 | 9468492.45 | 0 | 9468492.45 | 9468492.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9468492.45 | 0 | 9468492.45 | 9468492.45 | 0
458 | ** | Keltron Make Pneu Actuators for ID&FD | NL-N-TS2-002-06-58 | 2227009.91 | 2227009.91 | 0 | 2227009.91 | 0 | 2227009.91 | 2227009.91 | 0 | 2227009.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2227009.91 | 2227009.91 | 0 | 2227009.91 | 0
459 | ** | Purchase of pfb transmitter for HP bp | NL-N-TS2-002-06-59 | 2422486.41 | 2422486.41 | 0 | 2422486.41 | 0 | 2422486.41 | 2422486.41 | 0 | 2422486.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2422486.41 | 2422486.41 | 0 | 2422486.41 | 0
460 | ** | Purchase of DCS Spares for SIEMENS St-I | NL-N-TS2-002-06-60 | 2404956.69 | 2404956.69 | 0 | 2404956.69 | 0 | 2404956.69 | 2404956.69 | 0 | 2404956.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2404956.69 | 2404956.69 | 0 | 2404956.69 | 0
461 | ** | Purchase of Rockwin Turbine Flowmeter | NL-N-TS2-002-06-61 | 434018.16 | 434018.16 | 0 | 434018.16 | 0 | 434018.16 | 434018.16 | 0 | 434018.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434018.16 | 434018.16 | 0 | 434018.16 | 0
462 | ** | Pur & Comm of radar type level transmitt | NL-N-TS2-002-06-62 | 626095.02 | 574004.2 | 52090.82 | 626095.02 | 0 | 574004.2 | 574004.2 | 0 | 574004.2 | 0 | 52090.82 | 0 | 52090.82 | 52090.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626095.02 | 574004.2 | 52090.82 | 626095.02 | 0
463 | ** | Online weighing system for stacker | NL-N-TS2-002-06-63 | 803186 | 0 | 803186 | 803186 | 0 | 0 | 0 | 0 | 0 | 0 | 803186 | 0 | 803186 | 803186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803186 | 0 | 803186 | 803186 | 0
464 | ** | Flue gas Detector 3Nos | NL-N-TS2-002-06-64 | 2484606 | 0 | 2484606 | 2484606 | 0 | 0 | 0 | 0 | 0 | 0 | 2484606 | 0 | 2484606 | 2484606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2484606 | 0 | 2484606 | 2484606 | 0
465 | ** | Design Engg manufacturing&supply of DCS | NL-N-TS2-002-06-65 | 212681688.45 | 191879139.56 | 20802548.89 | 212681688.45 | 0 | 191879139.56 | 191879139.56 | 0 | 191879139.56 | 0 | 20802548.89 | 0 | 20802548.89 | 20802548.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212681688.45 | 191879139.56 | 20802548.89 | 212681688.45 | 0
466 | ** | Purchase of Metso DNA DCS Controller spa | NL-N-TS2-002-06-66 | 9209900 | 9209900 | 0 | 9209900 | 0 | 9209900 | 9209900 | 0 | 9209900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9209900 | 9209900 | 0 | 9209900 | 0
467 | ** | Purchase of Temperature Transmitters | NL-N-TS2-002-06-67 | 2102551.49 | 2102551.49 | 0 | 2102551.49 | 0 | 2102551.49 | 2102551.49 | 0 | 2102551.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2102551.49 | 2102551.49 | 0 | 2102551.49 | 0
468 | ** | Purchase of Metso DNA spares-IPSP &IBC | NL-N-TS2-002-06-68 | 31964172.06 | 31964172.06 | 0 | 31964172.06 | 0 | 31964172.06 | 31964172.06 | 0 | 31964172.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31964172.06 | 31964172.06 | 0 | 31964172.06 | 0
469 | ** | Power supply Unit for Siemens DCS | NL-N-TS2-002-06-69 | 8838550 | 0 | 8838550 | 8838550 | 0 | 0 | 0 | 0 | 0 | 0 | 8838550 | 0 | 8838550 | 8838550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8838550 | 0 | 8838550 | 8838550 | 0
470 | ** | RTD Input Module for Stage-I DCS | NL-N-TS2-002-06-70 | 10550498.15 | 0 | 10550498.15 | 10550498.15 | 0 | 0 | 0 | 0 | 0 | 0 | 10550498.15 | 0 | 10550498.15 | 10550498.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10550498.15 | 0 | 10550498.15 | 10550498.15 | 0
471 | ** | PUR-NOX GAS ANALYZER WITH NO CONVERTER | NL-N-TS2-002-06-71 | 3220759.25 | 0 | 3220759.25 | 3220759.25 | 0 | 0 | 0 | 0 | 0 | 0 | 3220759.25 | 0 | 3220759.25 | 3220759.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220759.25 | 0 | 3220759.25 | 3220759.25 | 0
472 | ** | PUR OF PRESSURE TRANSMITTERS | NL-N-TS2-002-06-72 | 17586725.25 | 0 | 17586725.25 | 17586725.25 | 0 | 0 | 0 | 0 | 0 | 0 | 17586725.25 | 0 | 17586725.25 | 17586725.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17586725.25 | 0 | 17586725.25 | 17586725.25 | 0
473 | ** | Purc 16 nos of High energy igniter | NL-N-TS2-002-06-73 | 6321024 | 0 | 6321024 | 6321024 | 0 | 0 | 0 | 0 | 0 | 0 | 6321024 | 0 | 6321024 | 6321024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6321024 | 0 | 6321024 | 6321024 | 0
474 | ** | Purchase of 7 Nos. of Positioner Cylinde | NL-N-TS2-002-06-74 | 7410343.99 | 0 | 7410343.99 | 7410343.99 | 0 | 0 | 0 | 0 | 0 | 0 | 7410343.99 | 0 | 7410343.99 | 7410343.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7410343.99 | 0 | 7410343.99 | 7410343.99 | 0
475 | ** | PURS-1 NUMBER OUTDOOR LED DISPLAY UNIT | NL-N-TS2-002-06-75 | 776000 | 0 | 776000 | 776000 | 0 | 0 | 0 | 0 | 0 | 0 | 776000 | 0 | 776000 | 776000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776000 | 0 | 776000 | 776000 | 0
476 | ** |  | NL-N-TS2-002-06-76 | 2888640 | 0 | 2888640 | 2888640 | 0 | 0 | 0 | 0 | 0 | 0 | 2888640 | 0 | 2888640 | 2888640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2888640 | 0 | 2888640 | 2888640 | 0
477 | ** |  | NL-N-TS2-002-06-77 | 8772565 | 0 | 8772565 | 8772565 | 0 | 0 | 0 | 0 | 0 | 0 | 8772565 | 0 | 8772565 | 8772565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8772565 | 0 | 8772565 | 8772565 | 0
478 | ** |  | NL-N-TS2-002-06-78 | 5534676 | 0 | 5534676 | 5534676 | 0 | 0 | 0 | 0 | 0 | 0 | 5534676 | 0 | 5534676 | 5534676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5534676 | 0 | 5534676 | 5534676 | 0
479 | ** |  | NL-N-TS2-002-06-79 | 489872029 | 0 | 489872029 | 489872029 | 0 | 0 | 0 | 0 | 0 | 0 | 489872029 | 0 | 489872029 | 489872029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489872029 | 0 | 489872029 | 489872029 | 0
480 | ** |  | NL-N-TS2-002-06-80 | 8879500 | 0 | 8879500 | 8879500 | 0 | 0 | 0 | 0 | 0 | 0 | 8879500 | 0 | 8879500 | 8879500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8879500 | 0 | 8879500 | 8879500 | 0
481 | *** | LHS MAINTENANCE | NL-N-TS2-002-07 | 676607241.44 | 651854218.76 | 24753022.68 | 676607241.44 | 0 | 651633795.54 | 651633795.54 | 0 | 651633795.54 | 0 | 24973445.9 | 220423.22 | 24753022.68 | 24973445.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 676607241.44 | 651854218.76 | 24753022.68 | 676607241.44 | 0
482 | ** | CONVEYORS AND SYSTEM ASSEMBLY | NL-N-TS2-002-07-01 | 20939218.48 | 20412230.46 | 526988.02 | 20939218.48 | 0 | 20412230.46 | 20412230.46 | 0 | 20412230.46 | 0 | 526988.02 | 0 | 526988.02 | 526988.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20939218.48 | 20412230.46 | 526988.02 | 20939218.48 | 0
483 | ** | LIGNITE YARD RAILS REPLACEMENT | NL-N-TS2-002-07-02 | 26848891.29 | 26848891.29 | 0 | 26848891.29 | 0 | 26848891.29 | 26848891.29 | 0 | 26848891.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26848891.29 | 26848891.29 | 0 | 26848891.29 | 0
484 | ** | BELT EQUIPMENT SYSTEM | NL-N-TS2-002-07-03 | 705000 | 705000 | 0 | 705000 | 0 | 705000 | 705000 | 0 | 705000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705000 | 705000 | 0 | 705000 | 0
485 | ** | Replacement of Two Reclaimers | NL-N-TS2-002-07-04 | 549498106.49 | 549498102.27 | 4.22 | 549498106.49 | 0 | 549498102.27 | 549498102.27 | 0 | 549498102.27 | 0 | 4.22 | 0 | 4.22 | 4.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549498106.49 | 549498102.27 | 4.22 | 549498106.49 | 0
486 | ** | Vacuum Cleaners for Bunker bay | NL-N-TS2-002-07-05 | 1803473.97 | 1803473.97 | 0 | 1803473.97 | 0 | 1803473.97 | 1803473.97 | 0 | 1803473.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1803473.97 | 1803473.97 | 0 | 1803473.97 | 0
487 | ** | Vulcanizing Equipments | NL-N-TS2-002-07-06 | 6071695.81 | 6071695.81 | 0 | 6071695.81 | 0 | 6071695.81 | 6071695.81 | 0 | 6071695.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6071695.81 | 6071695.81 | 0 | 6071695.81 | 0
488 | ** | Various Idlers | NL-N-TS2-002-07-07 | 10289087.91 | 10289087.91 | 0 | 10289087.91 | 0 | 10289087.91 | 10289087.91 | 0 | 10289087.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10289087.91 | 10289087.91 | 0 | 10289087.91 | 0
489 | ** | Cam Shafts | NL-N-TS2-002-07-08 | 4196352.41 | 4196352.41 | 0 | 4196352.41 | 0 | 4196352.41 | 4196352.41 | 0 | 4196352.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4196352.41 | 4196352.41 | 0 | 4196352.41 | 0
490 | ** | Structural Repair Works | NL-N-TS2-002-07-09 | 12477113.66 | 9221777.39 | 3255336.27 | 12477113.66 | 0 | 9221777.39 | 9221777.39 | 0 | 9221777.39 | 0 | 3255336.27 | 0 | 3255336.27 | 3255336.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12477113.66 | 9221777.39 | 3255336.27 | 12477113.66 | 0
491 | ** | Compressor for DSS system at LHS | NL-N-TS2-002-07-10 | 4496421.39 | 4496421.39 | 0 | 4496421.39 | 0 | 4496421.39 | 4496421.39 | 0 | 4496421.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4496421.39 | 4496421.39 | 0 | 4496421.39 | 0
492 | ** | Rack for Shuttle Conveyors | NL-N-TS2-002-07-11 | 810661.86 | 810661.86 | 0 | 810661.86 | 0 | 810661.86 | 810661.86 | 0 | 810661.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810661.86 | 810661.86 | 0 | 810661.86 | 0
493 | ** | Bunker Grill_size2400x1120x100 | NL-N-TS2-002-07-12 | 1613507.14 | 1613507.14 | 0 | 1613507.14 | 0 | 1613507.14 | 1613507.14 | 0 | 1613507.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1613507.14 | 1613507.14 | 0 | 1613507.14 | 0
494 | ** | Gear Box Spares | NL-N-TS2-002-07-13 | 8197748.27 | 8197748.27 | 0 | 8197748.27 | 0 | 8197748.27 | 8197748.27 | 0 | 8197748.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8197748.27 | 8197748.27 | 0 | 8197748.27 | 0
495 | ** | Hydraulic Cylinders for Conveyors | NL-N-TS2-002-07-14 | 1580113.77 | 1580113.77 | 0 | 1580113.77 | 0 | 1580113.77 | 1580113.77 | 0 | 1580113.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1580113.77 | 1580113.77 | 0 | 1580113.77 | 0
496 | ** | Gear box spares for Bunker Conveyors | NL-N-TS2-002-07-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | ** | Structural repair Works | NL-N-TS2-002-07-16 | 14125242.9 | 5738804.81 | 8386438.09 | 14125242.9 | 0 | 5518381.59 | 5518381.59 | 0 | 5518381.59 | 0 | 8606861.31 | 220423.22 | 8386438.09 | 8606861.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14125242.9 | 5738804.81 | 8386438.09 | 14125242.9 | 0
498 | ** | PROCUREMENT OF GEAR BOX SPARES | NL-N-TS2-002-07-17 | 8469339.08 | 0 | 8469339.08 | 8469339.08 | 0 | 0 | 0 | 0 | 0 | 0 | 8469339.08 | 0 | 8469339.08 | 8469339.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8469339.08 | 0 | 8469339.08 | 8469339.08 | 0
499 | ** | PROCUREMENT-STACKER HYDRAULIC CYLINDER | NL-N-TS2-002-07-20 | 370350.01 | 370350.01 | 0 | 370350.01 | 0 | 370350.01 | 370350.01 | 0 | 370350.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370350.01 | 370350.01 | 0 | 370350.01 | 0
500 | ** | DECK PLATE FOR CONVEYOR 2 & 4 A/B | NL-N-TS2-002-07-24 | 2486850 | 0 | 2486850 | 2486850 | 0 | 0 | 0 | 0 | 0 | 0 | 2486850 | 0 | 2486850 | 2486850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2486850 | 0 | 2486850 | 2486850 | 0
501 | ** |  | NL-N-TS2-002-07-25 | 1628067 | 0 | 1628067 | 1628067 | 0 | 0 | 0 | 0 | 0 | 0 | 1628067 | 0 | 1628067 | 1628067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1628067 | 0 | 1628067 | 1628067 | 0
502 | *** | TURBINE MAINTENANCE | NL-N-TS2-002-08 | 381728070.66 | 232555465.1 | 149173303.28 | 381728768.38 | -697.72 | 225825542.92 | 225826240.64 | 0 | 225826240.64 | -697.72 | 155902527.74 | 6729224.46 | 142369102.52 | 149098326.98 | 6804200.76 | 0 | 0 | 6804200.76 | 6804200.76 | -6804200.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385247107.83 | 232555465.1 | 149173303.28 | 381728768.38 | 3518339.45
503 | ** | MAIN TURBINE | NL-N-TS2-002-08-01 | 63947591.59 | 34965672.79 | 28981918.8 | 63947591.59 | 0 | 34965672.79 | 34965672.79 | 0 | 34965672.79 | 0 | 28981918.8 | 0 | 28981918.8 | 28981918.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66264561.39 | 34965672.79 | 28981918.8 | 63947591.59 | 2316969.8
504 | * | HP Module Purchase | NL-N-TS2-002-08-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
505 | * | Turbine Gov system Internals | NL-N-TS2-002-08-01-04 | 2009824.02 | 2009824.02 | 0 | 2009824.02 | 0 | 2009824.02 | 2009824.02 | 0 | 2009824.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009824.02 | 2009824.02 | 0 | 2009824.02 | 0
506 | * | Turbine fasteners & Coupling Bolts | NL-N-TS2-002-08-01-05 | 1547157.78 | 1547157.78 | 0 | 1547157.78 | 0 | 1547157.78 | 1547157.78 | 0 | 1547157.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1547157.78 | 1547157.78 | 0 | 1547157.78 | 0
507 | * | Clam pie T lp rotor last stage blades | NL-N-TS2-002-08-01-11 | 5224129.15 | 5224129.15 | 0 | 5224129.15 | 0 | 5224129.15 | 5224129.15 | 0 | 5224129.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5224129.15 | 5224129.15 | 0 | 5224129.15 | 0
508 | * | Turbine Gl seal segment BHELmake 12items | NL-N-TS2-002-08-01-17 | 7020664.2 | 0 | 7020664.2 | 7020664.2 | 0 | 0 | 0 | 0 | 0 | 0 | 7020664.2 | 0 | 7020664.2 | 7020664.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9337634 | 0 | 7020664.2 | 7020664.2 | 2316969.8
509 | * | Helical com spring for T G Sealing 2ite | NL-N-TS2-002-08-01-18 | 1232753 | 1232753 | 0 | 1232753 | 0 | 1232753 | 1232753 | 0 | 1232753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232753 | 1232753 | 0 | 1232753 | 0
510 | * | IP Plane fastener GS spares ST-2 | NL-N-TS2-002-08-01-19 | 16255330.34 | 15367349.28 | 887981.06 | 16255330.34 | 0 | 15367349.28 | 15367349.28 | 0 | 15367349.28 | 0 | 887981.06 | 0 | 887981.06 | 887981.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16255330.34 | 15367349.28 | 887981.06 | 16255330.34 | 0
511 | * | Spares for main Turbine Sealing Strip | NL-N-TS2-002-08-01-20 | 5449596.53 | 5368077.53 | 81519 | 5449596.53 | 0 | 5368077.53 | 5368077.53 | 0 | 5368077.53 | 0 | 81519 | 0 | 81519 | 81519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5449596.53 | 5368077.53 | 81519 | 5449596.53 | 0
512 | * | Condenser Manhole Cover assembly | NL-N-TS2-002-08-01-21 | 1975320 | 0 | 1975320 | 1975320 | 0 | 0 | 0 | 0 | 0 | 0 | 1975320 | 0 | 1975320 | 1975320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1975320 | 0 | 1975320 | 1975320 | 0
513 | * | Planetary unit sub assembly for Main hoi | NL-N-TS2-002-08-01-22 | 726500 | 726500 | 0 | 726500 | 0 | 726500 | 726500 | 0 | 726500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726500 | 726500 | 0 | 726500 | 0
514 | * | Portable single phase welding machine | NL-N-TS2-002-08-01-23 | 20814 | 20814 | 0 | 20814 | 0 | 20814 | 20814 | 0 | 20814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20814 | 20814 | 0 | 20814 | 0
515 | * | MOP Spares,HP stop valves spares&HP casi | NL-N-TS2-002-08-01-24 | 5676399.64 | 0 | 5676399.64 | 5676399.64 | 0 | 0 | 0 | 0 | 0 | 0 | 5676399.64 | 0 | 5676399.64 | 5676399.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5676399.64 | 0 | 5676399.64 | 5676399.64 | 0
516 | * | Main Oil pump impeller for St-II Turbine | NL-N-TS2-002-08-01-25 | 10775099.9 | 0 | 10775099.9 | 10775099.9 | 0 | 0 | 0 | 0 | 0 | 0 | 10775099.9 | 0 | 10775099.9 | 10775099.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10775099.9 | 0 | 10775099.9 | 10775099.9 | 0
517 | * | Boll &Kirch Filter Element for Duplex | NL-N-TS2-002-08-01-26 | 3469068.03 | 3469068.03 | 0 | 3469068.03 | 0 | 3469068.03 | 3469068.03 | 0 | 3469068.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3469068.03 | 3469068.03 | 0 | 3469068.03 | 0
518 | * | Over speed trip release unit | NL-N-TS2-002-08-01-27 | 2564935 | 0 | 2564935 | 2564935 | 0 | 0 | 0 | 0 | 0 | 0 | 2564935 | 0 | 2564935 | 2564935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2564935 | 0 | 2564935 | 2564935 | 0
519 | ** | BOILER FEED PUMP | NL-N-TS2-002-08-02 | 110071632.97 | 38074023 | 71998307.69 | 110072330.69 | -697.72 | 35382695.53 | 35383393.25 | 0 | 35383393.25 | -697.72 | 74688937.44 | 2690629.75 | 65194106.93 | 67884736.68 | 6804200.76 | 0 | 0 | 6804200.76 | 6804200.76 | -6804200.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110071632.97 | 38074023 | 71998307.69 | 110072330.69 | -697.72
520 | * | CWP impellers & brg | NL-N-TS2-002-08-02-02 | 3442521.36 | 3442521.36 | 0 | 3442521.36 | 0 | 3442521.36 | 3442521.36 | 0 | 3442521.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3442521.36 | 3442521.36 | 0 | 3442521.36 | 0
521 | * | CWP impellers & bearings | NL-N-TS2-002-08-02-09 | 3280819.79 | 3280819.79 | 0 | 3280819.79 | 0 | 3280819.79 | 3280819.79 | 0 | 3280819.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3280819.79 | 3280819.79 | 0 | 3280819.79 | 0
522 | * | CWP REJ | NL-N-TS2-002-08-02-10 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0
523 | * | Chlorination Plant Spares | NL-N-TS2-002-08-02-20 | 817691.02 | 817691.02 | 0 | 817691.02 | 0 | 817691.02 | 817691.02 | 0 | 817691.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 817691.02 | 817691.02 | 0 | 817691.02 | 0
524 | * | BFP Wear rings for stage-1&2 | NL-N-TS2-002-08-02-21 | 1123782.88 | 1123782.88 | 0 | 1123782.88 | 0 | 1123782.88 | 1123782.88 | 0 | 1123782.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123782.88 | 1123782.88 | 0 | 1123782.88 | 0
525 | * | Boiler Feed Pump Wear Rings Stage-I | NL-N-TS2-002-08-02-23 | 602689.09 | 602689.09 | 0 | 602689.09 | 0 | 602689.09 | 602689.09 | 0 | 602689.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602689.09 | 602689.09 | 0 | 602689.09 | 0
526 | * | Condensate Extraction Pump Spares | NL-N-TS2-002-08-02-24 | 4103744.54 | 4103744.54 | 0 | 4103744.54 | 0 | 4103744.54 | 4103744.54 | 0 | 4103744.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4103744.54 | 4103744.54 | 0 | 4103744.54 | 0
527 | * | Spares for BFP 6WC-137/C Mech seal st-I | NL-N-TS2-002-08-02-25 | 2325187.36 | 2325187.36 | 0 | 2325187.36 | 0 | 2325187.36 | 2325187.36 | 0 | 2325187.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2325187.36 | 2325187.36 | 0 | 2325187.36 | 0
528 | * | Spares for BFP FK6D30 Mech Seal Stage-II | NL-N-TS2-002-08-02-26 | 2373599.1 | 2374296.82 | 0 | 2374296.82 | -697.72 | 2373599.1 | 2374296.82 | 0 | 2374296.82 | -697.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2373599.1 | 2374296.82 | 0 | 2374296.82 | -697.72
529 | * | Spares for st-I BFP Shaft Type-6WC 137/C | NL-N-TS2-002-08-02-27 | 2726139.34 | 2726139.34 | 0 | 2726139.34 | 0 | 2726139.34 | 2726139.34 | 0 | 2726139.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2726139.34 | 2726139.34 | 0 | 2726139.34 | 0
530 | * | Spares for BFP Thrust Collar Spring O ri | NL-N-TS2-002-08-02-28 | 2237567.26 | 2237567.26 | 0 | 2237567.26 | 0 | 2237567.26 | 2237567.26 | 0 | 2237567.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2237567.26 | 2237567.26 | 0 | 2237567.26 | 0
531 | * | BFP Type 6WC 137/C "C" Ring | NL-N-TS2-002-08-02-29 | 4459356.01 | 4459356.01 | 0 | 4459356.01 | 0 | 4459356.01 | 4459356.01 | 0 | 4459356.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4459356.01 | 4459356.01 | 0 | 4459356.01 | 0
532 | * | BFP Mech seals Spares for St-II Eagle ma | NL-N-TS2-002-08-02-30 | 2423959.25 | 2423959.25 | 0 | 2423959.25 | 0 | 2423959.25 | 2423959.25 | 0 | 2423959.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2423959.25 | 2423959.25 | 0 | 2423959.25 | 0
533 | * | Duplex Filter for Stage-2 CWP | NL-N-TS2-002-08-02-31 | 606015.39 | 606015.39 | 0 | 606015.39 | 0 | 606015.39 | 606015.39 | 0 | 606015.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606015.39 | 606015.39 | 0 | 606015.39 | 0
534 | * | BFP TYPE FK 6D 30 IMPELLER STG-2 | NL-N-TS2-002-08-02-32 | 1248485.02 | 1248485.02 | 0 | 1248485.02 | 0 | 1248485.02 | 1248485.02 | 0 | 1248485.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1248485.02 | 1248485.02 | 0 | 1248485.02 | 0
535 | * | BFP type FK 6D 30 Diffusers and Diapharm | NL-N-TS2-002-08-02-33 | 1272173.35 | 0 | 1272173.35 | 1272173.35 | 0 | 0 | 0 | 0 | 0 | 0 | 1272173.35 | 0 | 1272173.35 | 1272173.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1272173.35 | 0 | 1272173.35 | 1272173.35 | 0
536 | * | BRG Bracket/Lantern ring-Booster pump | NL-N-TS2-002-08-02-34 | 2386298.72 | 2386298.72 | 0 | 2386298.72 | 0 | 2386298.72 | 2386298.72 | 0 | 2386298.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2386298.72 | 2386298.72 | 0 | 2386298.72 | 0
537 | * | WOC/LOC stack assembly | NL-N-TS2-002-08-02-35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
538 | * | Spare for BFP working oil cooler tube | NL-N-TS2-002-08-02-36 | 2690629.75 | 2690629.75 | 0 | 2690629.75 | 0 | 0 | 0 | 0 | 0 | 0 | 2690629.75 | 2690629.75 | 0 | 2690629.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2690629.75 | 2690629.75 | 0 | 2690629.75 | 0
539 | * | Finostos B Bearing as per Dimension | NL-N-TS2-002-08-02-37 | 1224839.4 | 1224839.4 | 0 | 1224839.4 | 0 | 1224839.4 | 1224839.4 | 0 | 1224839.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224839.4 | 1224839.4 | 0 | 1224839.4 | 0
540 | * | Providing energy efficient coating CWP | NL-N-TS2-002-08-02-38 | 1374750.01 | 0 | 1374750.01 | 1374750.01 | 0 | 0 | 0 | 0 | 0 | 0 | 1374750.01 | 0 | 1374750.01 | 1374750.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1374750.01 | 0 | 1374750.01 | 1374750.01 | 0
541 | * | Impeller Shaft and Top Shaft for CWP | NL-N-TS2-002-08-02-39 | 3044487.52 | 0 | 3044487.52 | 3044487.52 | 0 | 0 | 0 | 0 | 0 | 0 | 3044487.52 | 0 | 3044487.52 | 3044487.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3044487.52 | 0 | 3044487.52 | 3044487.52 | 0
542 | * | SPARES FOR BFP TYPE FK6D30 | NL-N-TS2-002-08-02-40 | 2491320.14 | 0 | 2491320.14 | 2491320.14 | 0 | 0 | 0 | 0 | 0 | 0 | 2491320.14 | 0 | 2491320.14 | 2491320.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2491320.14 | 0 | 2491320.14 | 2491320.14 | 0
543 | * | Rotor assembly of BFP Booster pump St-I | NL-N-TS2-002-08-02-41 | 6721500.56 | 0 | 6721500.56 | 6721500.56 | 0 | 0 | 0 | 0 | 0 | 0 | 6721500.56 | 0 | 6721500.56 | 6721500.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6721500.56 | 0 | 6721500.56 | 6721500.56 | 0
544 | * | Complete set of BFP Booster pump | NL-N-TS2-002-08-02-42 | 6804200.76 | 0 | 6804200.76 | 6804200.76 | 0 | 0 | 0 | 0 | 0 | 0 | 6804200.76 | 0 | 0 | 0 | 6804200.76 | 0 | 0 | 6804200.76 | 6804200.76 | -6804200.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6804200.76 | 0 | 6804200.76 | 6804200.76 | 0
545 | * | Feed Pump Recirculation Valve | NL-N-TS2-002-08-02-43 | 8891025.48 | 0 | 8891025.48 | 8891025.48 | 0 | 0 | 0 | 0 | 0 | 0 | 8891025.48 | 0 | 8891025.48 | 8891025.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8891025.48 | 0 | 8891025.48 | 8891025.48 | 0
546 | * | BEARINGS FOR HYDROCOUPLINGS OF BFP | NL-N-TS2-002-08-02-44 | 5606522.24 | 0 | 5606522.24 | 5606522.24 | 0 | 0 | 0 | 0 | 0 | 0 | 5606522.24 | 0 | 5606522.24 | 5606522.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5606522.24 | 0 | 5606522.24 | 5606522.24 | 0
547 | * | SPARES FOR BFP EAGLEBURGMANN-TYPE 6 | NL-N-TS2-002-08-02-45 | 2846879.33 | 0 | 2846879.33 | 2846879.33 | 0 | 0 | 0 | 0 | 0 | 0 | 2846879.33 | 0 | 2846879.33 | 2846879.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2846879.33 | 0 | 2846879.33 | 2846879.33 | 0
548 | * | SPARES OF BFP HYDROCOUPLING | NL-N-TS2-002-08-02-46 | 22492669.44 | 0 | 22492669.44 | 22492669.44 | 0 | 0 | 0 | 0 | 0 | 0 | 22492669.44 | 0 | 22492669.44 | 22492669.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22492669.44 | 0 | 22492669.44 | 22492669.44 | 0
549 | * | SPARES OF IMPELLERS OF BFP FOR STAGE 1 | NL-N-TS2-002-08-02-47 | 7005986.86 | 0 | 7005986.86 | 7005986.86 | 0 | 0 | 0 | 0 | 0 | 0 | 7005986.86 | 0 | 7005986.86 | 7005986.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7005986.86 | 0 | 7005986.86 | 7005986.86 | 0
550 | * |  | NL-N-TS2-002-08-02-48 | 3446790 | 0 | 3446790 | 3446790 | 0 | 0 | 0 | 0 | 0 | 0 | 3446790 | 0 | 3446790 | 3446790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3446790 | 0 | 3446790 | 3446790 | 0
551 | ** | PIPING & VALVES | NL-N-TS2-002-08-03 | 25744701.17 | 12524091.22 | 13220609.95 | 25744701.17 | 0 | 8485496.51 | 8485496.51 | 0 | 8485496.51 | 0 | 17259204.66 | 4038594.71 | 13220609.95 | 17259204.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25744701.17 | 12524091.22 | 13220609.95 | 25744701.17 | 0
552 | * | Hand operated valves | NL-N-TS2-002-08-03-01 | 56050 | 56050 | 0 | 56050 | 0 | 56050 | 56050 | 0 | 56050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56050 | 56050 | 0 | 56050 | 0
553 | * | MOV | NL-N-TS2-002-08-03-02 | 418923.6 | 418923.6 | 0 | 418923.6 | 0 | 418923.6 | 418923.6 | 0 | 418923.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418923.6 | 418923.6 | 0 | 418923.6 | 0
554 | * | PCV | NL-N-TS2-002-08-03-03 | 350861.68 | 350861.68 | 0 | 350861.68 | 0 | 350861.68 | 350861.68 | 0 | 350861.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350861.68 | 350861.68 | 0 | 350861.68 | 0
555 | * | RC valves replacement | NL-N-TS2-002-08-03-04 | 4038594.71 | 4038594.71 | 0 | 4038594.71 | 0 | 0 | 0 | 0 | 0 | 0 | 4038594.71 | 4038594.71 | 0 | 4038594.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4038594.71 | 4038594.71 | 0 | 4038594.71 | 0
556 | * | Pipes | NL-N-TS2-002-08-03-06 | 1586164.27 | 59619.27 | 1526545 | 1586164.27 | 0 | 59619.27 | 59619.27 | 0 | 59619.27 | 0 | 1526545 | 0 | 1526545 | 1526545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1586164.27 | 59619.27 | 1526545 | 1586164.27 | 0
557 | * | Bore Well Pipes Replacement | NL-N-TS2-002-08-03-08 | 7600041.96 | 7600041.96 | 0 | 7600041.96 | 0 | 7600041.96 | 7600041.96 | 0 | 7600041.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7600041.96 | 7600041.96 | 0 | 7600041.96 | 0
558 | * | Purchase of pressure seal gaskets for HP | NL-N-TS2-002-08-03-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
559 | * | MAL Valves | NL-N-TS2-002-08-03-10 | 4353531 | 0 | 4353531 | 4353531 | 0 | 0 | 0 | 0 | 0 | 0 | 4353531 | 0 | 4353531 | 4353531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4353531 | 0 | 4353531 | 4353531 | 0
560 | * | LP by pass Limiting regulator | NL-N-TS2-002-08-03-11 | 5600040 | 0 | 5600040 | 5600040 | 0 | 0 | 0 | 0 | 0 | 0 | 5600040 | 0 | 5600040 | 5600040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600040 | 0 | 5600040 | 5600040 | 0
561 | * | LP by pass Governing system spare parts | NL-N-TS2-002-08-03-12 | 1740493.95 | 0 | 1740493.95 | 1740493.95 | 0 | 0 | 0 | 0 | 0 | 0 | 1740493.95 | 0 | 1740493.95 | 1740493.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1740493.95 | 0 | 1740493.95 | 1740493.95 | 0
562 | ** | AC PLANT | NL-N-TS2-002-08-04 | 12627000.63 | 9330188.67 | 3296811.96 | 12627000.63 | 0 | 9330188.67 | 9330188.67 | 0 | 9330188.67 | 0 | 3296811.96 | 0 | 3296811.96 | 3296811.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13829068 | 9330188.67 | 3296811.96 | 12627000.63 | 1202067.37
563 | * | AC Plant Pumps Spares | NL-N-TS2-002-08-04-02 | 4685998.45 | 3698448.94 | 987549.51 | 4685998.45 | 0 | 3698448.94 | 3698448.94 | 0 | 3698448.94 | 0 | 987549.51 | 0 | 987549.51 | 987549.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4685998.45 | 3698448.94 | 987549.51 | 4685998.45 | 0
564 | * | Accel 4-100 compressor replacement | NL-N-TS2-002-08-04-04 | 1654231.13 | 1654231.13 | 0 | 1654231.13 | 0 | 1654231.13 | 1654231.13 | 0 | 1654231.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1654231.13 | 1654231.13 | 0 | 1654231.13 | 0
565 | * | Air washer unit replacement | NL-N-TS2-002-08-04-07 | 2980261.13 | 2980261.1 | 0.03 | 2980261.13 | 0 | 2980261.1 | 2980261.1 | 0 | 2980261.1 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2980261.13 | 2980261.1 | 0.03 | 2980261.13 | 0
566 | * | Kirloskar make KC6 Compressor spares | NL-N-TS2-002-08-04-08 | 666847.5 | 666847.5 | 0 | 666847.5 | 0 | 666847.5 | 666847.5 | 0 | 666847.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 666847.5 | 666847.5 | 0 | 666847.5 | 0
567 | * | Rep of Unit-2 Air washer Pre Suc Filter | NL-N-TS2-002-08-04-09 | 370400 | 330400 | 40000 | 370400 | 0 | 330400 | 330400 | 0 | 330400 | 0 | 40000 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370400 | 330400 | 40000 | 370400 | 0
568 | * | AC plant St-II Beacon weir pump spares | NL-N-TS2-002-08-04-10 | 2269262.42 | 0 | 2269262.42 | 2269262.42 | 0 | 0 | 0 | 0 | 0 | 0 | 2269262.42 | 0 | 2269262.42 | 2269262.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3471329.79 | 0 | 2269262.42 | 2269262.42 | 1202067.37
569 | ** | MAIN TURBINE CONTRACTS | NL-N-TS2-002-08-05 | 151382367.96 | 137661489.42 | 13720878.54 | 151382367.96 | 0 | 137661489.42 | 137661489.42 | 0 | 137661489.42 | 0 | 13720878.54 | 0 | 13720878.54 | 13720878.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151382367.96 | 137661489.42 | 13720878.54 | 151382367.96 | 0
570 | * | LEP Works : U-4 | NL-N-TS2-002-08-05-01 | 21122000 | 19059360 | 2062640 | 21122000 | 0 | 19059360 | 19059360 | 0 | 19059360 | 0 | 2062640 | 0 | 2062640 | 2062640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21122000 | 19059360 | 2062640 | 21122000 | 0
571 | * | U-4 CONDITION ASSESSMENT | NL-N-TS2-002-08-05-02 | 2891000 | 2891000 | 0 | 2891000 | 0 | 2891000 | 2891000 | 0 | 2891000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2891000 | 2891000 | 0 | 2891000 | 0
572 | * | U-2 WORKS CONTRACTS | NL-N-TS2-002-08-05-03 | 83622309.67 | 76702121.77 | 6920187.9 | 83622309.67 | 0 | 76702121.77 | 76702121.77 | 0 | 76702121.77 | 0 | 6920187.9 | 0 | 6920187.9 | 6920187.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83622309.67 | 76702121.77 | 6920187.9 | 83622309.67 | 0
573 | * | U-2 CONDITION ASSESSMENT | NL-N-TS2-002-08-05-04 | 1412460.02 | 1355961.6 | 56498.42 | 1412460.02 | 0 | 1355961.6 | 1355961.6 | 0 | 1355961.6 | 0 | 56498.42 | 0 | 56498.42 | 56498.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1412460.02 | 1355961.6 | 56498.42 | 1412460.02 | 0
574 | * | U-2 INSULATION CONTRACT | NL-N-TS2-002-08-05-05 | 1274400.03 | 1274400 | 0.03 | 1274400.03 | 0 | 1274400 | 1274400 | 0 | 1274400 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1274400.03 | 1274400 | 0.03 | 1274400.03 | 0
575 | * | Unit-4 Insulation Work | NL-N-TS2-002-08-05-07 | 1474999.98 | 1474999.97 | 0.01 | 1474999.98 | 0 | 1474999.97 | 1474999.97 | 0 | 1474999.97 | 0 | 0.01 | 0 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1474999.98 | 1474999.97 | 0.01 | 1474999.98 | 0
576 | * | Unit-6 Condition assesment | NL-N-TS2-002-08-05-09 | 2607800.02 | 2607800 | 0.02 | 2607800.02 | 0 | 2607800 | 2607800 | 0 | 2607800 | 0 | 0.02 | 0 | 0.02 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2607800.02 | 2607800 | 0.02 | 2607800.02 | 0
577 | * | Unit-6 Insulation contract | NL-N-TS2-002-08-05-10 | 1983580.03 | 1983580 | 0.03 | 1983580.03 | 0 | 1983580 | 1983580 | 0 | 1983580 | 0 | 0.03 | 0 | 0.03 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1983580.03 | 1983580 | 0.03 | 1983580.03 | 0
578 | * | U-6 Turbine Capital Overhaul | NL-N-TS2-002-08-05-18 | 33172320.98 | 28506228.88 | 4666092.1 | 33172320.98 | 0 | 28506228.88 | 28506228.88 | 0 | 28506228.88 | 0 | 4666092.1 | 0 | 4666092.1 | 4666092.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33172320.98 | 28506228.88 | 4666092.1 | 33172320.98 | 0
579 | * | Duromar coating on condenser Tube sheet | NL-N-TS2-002-08-05-19 | 1821497.23 | 1806037.2 | 15460.03 | 1821497.23 | 0 | 1806037.2 | 1806037.2 | 0 | 1806037.2 | 0 | 15460.03 | 0 | 15460.03 | 15460.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1821497.23 | 1806037.2 | 15460.03 | 1821497.23 | 0
580 | ** | Turbine Miscelaneous | NL-N-TS2-002-08-07 | 1428899.02 | 0 | 1428899.02 | 1428899.02 | 0 | 0 | 0 | 0 | 0 | 0 | 1428899.02 | 0 | 1428899.02 | 1428899.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428899.02 | 0 | 1428899.02 | 1428899.02 | 0
581 | * | Purchase of Mukund Crane Spares | NL-N-TS2-002-08-07-01 | 1428899.02 | 0 | 1428899.02 | 1428899.02 | 0 | 0 | 0 | 0 | 0 | 0 | 1428899.02 | 0 | 1428899.02 | 1428899.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428899.02 | 0 | 1428899.02 | 1428899.02 | 0
582 | ** | Ciculating Water Pump | NL-N-TS2-002-08-08 | 16525877.32 | 0 | 16525877.32 | 16525877.32 | 0 | 0 | 0 | 0 | 0 | 0 | 16525877.32 | 0 | 16525877.32 | 16525877.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16525877.32 | 0 | 16525877.32 | 16525877.32 | 0
583 | * | Impeller for Mather &Plate Make CWP | NL-N-TS2-002-08-08-01 | 3717973.56 | 0 | 3717973.56 | 3717973.56 | 0 | 0 | 0 | 0 | 0 | 0 | 3717973.56 | 0 | 3717973.56 | 3717973.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3717973.56 | 0 | 3717973.56 | 3717973.56 | 0
584 | * | Line shaft and Intermediat shaft for CWP | NL-N-TS2-002-08-08-02 | 12807903.76 | 0 | 12807903.76 | 12807903.76 | 0 | 0 | 0 | 0 | 0 | 0 | 12807903.76 | 0 | 12807903.76 | 12807903.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12807903.76 | 0 | 12807903.76 | 12807903.76 | 0
585 | *** | WCTP | NL-N-TS2-002-09 | 152764199.2 | 145181493.48 | 7582705.72 | 152764199.2 | 0 | 145181493.48 | 145181493.48 | 0 | 145181493.48 | 0 | 7582705.72 | 0 | 7582705.72 | 7582705.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152764199.2 | 145181493.48 | 7582705.72 | 152764199.2 | 0
586 | ** | UV Spectrophotometer | NL-N-TS2-002-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
587 | ** | Portable Dissolved Oxygen Analyser | NL-N-TS2-002-09-02 | 612017.6 | 612017.6 | 0 | 612017.6 | 0 | 612017.6 | 612017.6 | 0 | 612017.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612017.6 | 612017.6 | 0 | 612017.6 | 0
588 | ** | CW Treatment System for Higher COC | NL-N-TS2-002-09-03 | 151508431.53 | 143925725.81 | 7582705.72 | 151508431.53 | 0 | 143925725.81 | 143925725.81 | 0 | 143925725.81 | 0 | 7582705.72 | 0 | 7582705.72 | 7582705.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151508431.53 | 143925725.81 | 7582705.72 | 151508431.53 | 0
589 | ** | UV-VISIBLE SPECTROMETER | NL-N-TS2-002-09-04 | 643750.07 | 643750.07 | 0 | 643750.07 | 0 | 643750.07 | 643750.07 | 0 | 643750.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643750.07 | 643750.07 | 0 | 643750.07 | 0
590 | *** | COMPUTER | NL-N-TS2-002-10 | 55245317.11 | 10683536.92 | 44561780.19 | 55245317.11 | 0 | 10683536.92 | 10683536.92 | 0 | 10683536.92 | 0 | 44561780.19 | 0 | 44561780.19 | 44561780.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55245317.11 | 10683536.92 | 44561780.19 | 55245317.11 | 0
591 | ** | Simulator for PSTC | NL-N-TS2-002-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
592 | ** | CCTV & Network for Watch Tower | NL-N-TS2-002-10-02 | 2527725.2 | 2527725.2 | 0 | 2527725.2 | 0 | 2527725.2 | 2527725.2 | 0 | 2527725.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2527725.2 | 2527725.2 | 0 | 2527725.2 | 0
593 | ** | CCTV Network System for Peripheral area | NL-N-TS2-002-10-03 | 8180811.72 | 8155811.72 | 25000 | 8180811.72 | 0 | 8155811.72 | 8155811.72 | 0 | 8155811.72 | 0 | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8180811.72 | 8155811.72 | 25000 | 8180811.72 | 0
594 | ** | Phase-III -Proposal for the STWC OF CCTV | NL-N-TS2-002-10-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
595 | ** |  | NL-N-TS2-002-10-06 | 44536780.19 | 0 | 44536780.19 | 44536780.19 | 0 | 0 | 0 | 0 | 0 | 0 | 44536780.19 | 0 | 44536780.19 | 44536780.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44536780.19 | 0 | 44536780.19 | 44536780.19 | 0
596 | *** | PLANNING & TECHNICAL | NL-N-TS2-002-11 | 13338310.78 | 12446234.33 | 892076.45 | 13338310.78 | 0 | 12446234.33 | 12446234.33 | 0 | 12446234.33 | 0 | 892076.45 | 0 | 892076.45 | 892076.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13338310.78 | 12446234.33 | 892076.45 | 13338310.78 | 0
597 | ** | Study of MoEF Norms for FGD & WC Project | NL-N-TS2-002-11-01 | 3467810.79 | 2575734.34 | 892076.45 | 3467810.79 | 0 | 2575734.34 | 2575734.34 | 0 | 2575734.34 | 0 | 892076.45 | 0 | 892076.45 | 892076.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3467810.79 | 2575734.34 | 892076.45 | 3467810.79 | 0
598 | ** | Special Purpose Vehicle Mounted De-silt | NL-N-TS2-002-11-02 | 9870499.99 | 9870499.99 | 0 | 9870499.99 | 0 | 9870499.99 | 9870499.99 | 0 | 9870499.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9870499.99 | 9870499.99 | 0 | 9870499.99 | 0
599 | *** | BOILER AUXILLARY MAINTENANCE | NL-N-TS2-002-12 | 30429314.64 | 4749568.64 | 25679746 | 30429314.64 | 0 | 4749568.64 | 4749568.64 | 0 | 4749568.64 | 0 | 25679746 | 0 | 25679746 | 25679746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30429314.64 | 4749568.64 | 25679746 | 30429314.64 | 0
600 | ** | FIRE PROTECTION SYSTEM | NL-N-TS2-002-12-01 | 8541077.64 | 2178677.64 | 6362400 | 8541077.64 | 0 | 2178677.64 | 2178677.64 | 0 | 2178677.64 | 0 | 6362400 | 0 | 6362400 | 6362400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8541077.64 | 2178677.64 | 6362400 | 8541077.64 | 0
601 | * | Renovation of Fire Alarm System | NL-N-TS2-002-12-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
602 | * | 9 Ltr Mechanical Foam fire extingushers | NL-N-TS2-002-12-01-06 | 376998.2 | 376998.2 | 0 | 376998.2 | 0 | 376998.2 | 376998.2 | 0 | 376998.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376998.2 | 376998.2 | 0 | 376998.2 | 0
603 | * | 4 Ton capacity Battery Platform trolley | NL-N-TS2-002-12-01-07 | 705679 | 705679 | 0 | 705679 | 0 | 705679 | 705679 | 0 | 705679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705679 | 705679 | 0 | 705679 | 0
604 | * | Procurement of Dry Chemical Powder fire | NL-N-TS2-002-12-01-08 | 185000.41 | 185000.41 | 0 | 185000.41 | 0 | 185000.41 | 185000.41 | 0 | 185000.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185000.41 | 185000.41 | 0 | 185000.41 | 0
605 | * | Procurement of Fire water Booster pump | NL-N-TS2-002-12-01-09 | 891000.01 | 891000.01 | 0 | 891000.01 | 0 | 891000.01 | 891000.01 | 0 | 891000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 891000.01 | 891000.01 | 0 | 891000.01 | 0
606 | * | Procure of Pump/Motor Coupling for FWP | NL-N-TS2-002-12-01-10 | 20000.02 | 20000.02 | 0 | 20000.02 | 0 | 20000.02 | 20000.02 | 0 | 20000.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000.02 | 20000.02 | 0 | 20000.02 | 0
607 | * | Procure of 22 Tons of 150 NB ERW Pipe | NL-N-TS2-002-12-01-11 | 2046000 | 0 | 2046000 | 2046000 | 0 | 0 | 0 | 0 | 0 | 0 | 2046000 | 0 | 2046000 | 2046000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2046000 | 0 | 2046000 | 2046000 | 0
608 | * | PROCUREMENT-1100M-200NB-HYDRANT MODIFICI | NL-N-TS2-002-12-01-12 | 4316400 | 0 | 4316400 | 4316400 | 0 | 0 | 0 | 0 | 0 | 0 | 4316400 | 0 | 4316400 | 4316400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4316400 | 0 | 4316400 | 4316400 | 0
609 | ** | MECHANICAL MAINTENANCE | NL-N-TS2-002-12-02 | 21888237 | 2570891 | 19317346 | 21888237 | 0 | 2570891 | 2570891 | 0 | 2570891 | 0 | 19317346 | 0 | 19317346 | 19317346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21888237 | 2570891 | 19317346 | 21888237 | 0
610 | * | N2H4 Dozing Pump for Stage-II | NL-N-TS2-002-12-02-03 | 357999.97 | 357999.97 | 0 | 357999.97 | 0 | 357999.97 | 357999.97 | 0 | 357999.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357999.97 | 357999.97 | 0 | 357999.97 | 0
611 | * | Battery Operated Platform Trolley 2 Ton | NL-N-TS2-002-12-02-08 | 1031652.59 | 1031652.59 | 0 | 1031652.59 | 0 | 1031652.59 | 1031652.59 | 0 | 1031652.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1031652.59 | 1031652.59 | 0 | 1031652.59 | 0
612 | * | Phospate dozing Pump &Check valve assemb | NL-N-TS2-002-12-02-09 | 923238.43 | 923238.43 | 0 | 923238.43 | 0 | 923238.43 | 923238.43 | 0 | 923238.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 923238.43 | 923238.43 | 0 | 923238.43 | 0
613 | * | dECANTING SUMP BARE PUMP INCLUDING BASE | NL-N-TS2-002-12-02-10 | 258000.01 | 258000.01 | 0 | 258000.01 | 0 | 258000.01 | 258000.01 | 0 | 258000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258000.01 | 258000.01 | 0 | 258000.01 | 0
614 | * | Degassed water pump assembly w/o motor | NL-N-TS2-002-12-02-11 | 2477646 | 0 | 2477646 | 2477646 | 0 | 0 | 0 | 0 | 0 | 0 | 2477646 | 0 | 2477646 | 2477646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2477646 | 0 | 2477646 | 2477646 | 0
615 | * | supply of service kit and overhaul pumps | NL-N-TS2-002-12-02-12 | 6212000 | 0 | 6212000 | 6212000 | 0 | 0 | 0 | 0 | 0 | 0 | 6212000 | 0 | 6212000 | 6212000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6212000 | 0 | 6212000 | 6212000 | 0
616 | * | degasser water tank tower blowers | NL-N-TS2-002-12-02-13 | 10627700 | 0 | 10627700 | 10627700 | 0 | 0 | 0 | 0 | 0 | 0 | 10627700 | 0 | 10627700 | 10627700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10627700 | 0 | 10627700 | 10627700 | 0
617 | *** | BOILER OPERATION SERVICES | NL-N-TS2-002-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
618 | *** |  | NL-N-TS2-002-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
619 | ** |  | NL-N-TS2-002-14-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0